## All tables combined
June 30, 2004
Mr. Malcolm T. Kerley, P.E.
Chief Engineer for Program Development
Virginia Department of Transportation
1401 E. Broad Street
Richmond, Virginia 23219
Re: | Conceptual proposal pursuant to the Public-Private Transportation Act of
1995 for design, construction and financing of the Third Hampton Roads
Crossing
Dear Mr. Kerley:
Enclosed are twenty (20) copies of the Skanska/Washington/BAM (SWB) conceptual
proposal for the Third Hampton Roads Crossing submitted in accordance with both the
Public-Private |  | Transportation |  |  |  | Act |  | of | 1995 | (PPTA) | and | the | Department |  | of
Transportation's Implementation Guidelines. | [8 empty] | A copy of the proposal is being delivered to
all appropriate jurisdictions as indicated in the attached.
TAB 3 of the proposal, the Project Financing, is considered proprietary and confidential
in its entirety. |  | The attached letter granted exemption from all Freedom of Information
Act requests for this portion of the proposal.
A | cashier's | check | in | the | amount |  | of | $10,000 | is | being | forwarded | separately | to | cover
VDOT's review costs.
SWB | is | looking | forward |  | to | VDOT's |  | favorable consideration |  |  | of | this | proposal | for | the
critical Third Hampton Roads Crossing Project.
I am the designated SWB point of contact for this project.
Sincerely,
F. X. Watson
Project Director
Attachments: |  | 1) Local Jurisdiction Distribution
2) Letter regarding Confidential and Proprietary Information
SKANSKA  WASHINGTON  BAM
| P.O. Box 57, Norfolk, VA |  |  |  |  | 23501 | 809 S. Military Highway, Virginia Beach, VA | [5 empty] | 23464
|  |  |  | Tel: | 757-420-4140 |  |  |  | Fax: | 757-420-3551
Attachment 1. AFFECTED LOCAL JURISDICTIONS
Distribution List
TAB 3 not provided with these copies
Mr. George E. Wallace, City Manager
City of Hampton
22 Lincoln Street |  | Mr. Clarence V. Cuffee, City Manager
Hampton, Virginia 23669 |  | City of Chesapeake
(Mr. Charles A. Wornom, Mayor) |  | 306 Cedar Road
Chesapeake, Virginia 23328
Mr. Ed Maroney, City Manager |  | (Mr. Dalton Edge, Mayor)
City of Newport News
2400 Washington Street |  | Mr. James K. Spore, City Manager
10 th Floor City hall |  | City of Virginia Beach
Newport News, Virginia 23607 |  | 2401 Courthouse Road
(Mr. Joe S. Frank, Mayor) |  | Municipal Center, Bldg. #1
Virginia Beach, Virginia 23456
Mr. Jackson C. Tuttle, City Manager |  | (Mrs. Meyera E. Oberndorf, Mayor)
City of Williamsburg
401 Lafayette Street |  | Mr. Rowland L. Taylor, City Manager
Williamsburg, Virginia 23185 |  | City of Franklin
(Ms. Jeanne Zeidler, Mayor) |  | 207 West Second Street
Franklin, Virginia 23851
Mr. Charles W. Burgess, Jr., City Manager |  | (Mr. James P. Councill, III, Mayor)
City of Poquoson
500 City Hall Avenue |  | Mr. Peter M. Stephenson, Town Manager
Poquoson, Virginia 23662 |  | Town of Smithfield
(Mr. Gordon C. Helsel, Jr., Mayor) |  | 315 Main Street
Smithfield, Virginia 23431
Mr. Robert “Steve” Herbert, City Manager |  | (Mr. Stan D. Clark, Chairman)
City of Suffolk |  | Isle of Wight Board of Supervisors
441 Market Street
Suffolk, Virginia23434 |  | Mr. Sanford B. Wanner, County Administrator
(Mr. Dana W. Dickins, III, Mayor) |  | James City County
101 Mounts Bay Road
Mr. C. W. McCoy, City Manager |  | Williamsburg, Virginia 23187
City of Portsmouth |  | (Mr. Bruce Goodson, Chairman)
801 Crawford Street |  | James City County Board of Supervisors
Portsmouth, Virginia 23704
(Dr. James W. Holley, III, Mayor) |  | Mr. W. Douglas Caskey, County Administrator
Isle of Wight County
Mrs. Regina V. Williams, City Manager |  | 17130 Monument Circle-Suite A
City of Norfolk |  | Isle of Wight, Virginia 23397
810 Union Street |  | (Mr. Stan D. Clark, Chairman)
Norfolk, Virginia 23510 |  | Isle of Wight County Board of Supervisors
(Mr. Paul D. Fraim, Mayor)
SKANSKA  WASHINGTON  BAM
P.O. Box 57, Norfolk, VA | 23501 | 809 S. Military Highway, Virginia Beach, VA |  | 23464
Tel: | 757-420-4140 | Fax: | 757-420-3551
Attachment 1. AFFECTED LOCAL JURISDICTIONS
Distribution List
TAB 3 not provided with these copies
Mr. James O. McReynolds, County Administrator
York County
224 Ballard Street
Yorktown, Virginia 23690
(Mr. James S. Burgett, Chairman)
York County Board of Supervisors
Mr. Michael Johnson, County Administrator
Southampton County
26022 Administration Center Drive
Courtland, Virginia 23837
(Mr. Dallas O. Jones, Chairman)
Southampton County Board of Supervisors
Mr. William H. Whitley, County Administrator
Gloucester County
6467 Main Street
Gloucester, Virginia 23061
(Mr. Charles R. “Rick” Allen, Jr., Chairman)
Gloucester County Board of Supervisors
Mr. Terry D. Lewis, County Administrator
Surry County
45 School Street
Surry, Virginia 23883
(Mr. Reginald O. Harrison, Chairman)
Surry County Board of Supervisors
Mr. Arthur L. Collins, Executive Director
Hampton Roads Planning district Commission
723 Woodlake Drive
Chesapeake, Virginia 23320
SKANSKA  WASHINGTON  BAM
P.O. Box 57, Norfolk, VA | 23501 | 809 S. Military Highway, Virginia Beach, VA |  | 23464
Tel: | 757-420-4140 | Fax: | 757-420-3551
TA BL E OF CO N TE NTS
| TAB | TITLE |  | PAGE
Transmittal Letter
Freedom of Information Act Letter
|  | Table of Contents |  | i
|  | List of Exhibits |  | ii
|  | Executive Summary |  | E-1
| 1 | Qualifications and Experience
|  | 1.a | Organizational Approach | 1
|  | 1.b | Experience | 8
|  | 1.c | Point of Contact | 36
|  | 1.d | References | 37
|  | 1.e | Financial Statements | 38
|  | 1.f | Small, Woman and Minority Owned Business Participation | 39
| 2 | Project Characteristics
|  | 2.a | Project Description | 40
|  | 2.b | VDOT Participation | 43
|  | 2.c | Permits | 44
|  | 2.d | Environmental Issues | 45
|  | 2.e | Critical Success Factors | 47
|  | 2.f | Schedule | 49
|  | 2.g | Timely Completion of the Project | 50
|  | 2.h | Assumptions Related to Ownership, Liability and Operational
|  |  | Responsibility | 51
|  | 2.i | Project Partial Openings | 52
| 3 | Project Financing (Restricted Distribution)
|  | 3.a | Project Cost Estimate | 53
|  | 3.b | Financing Plan | 57
|  | 3.c | Financial Assumptions | 58
|  | 3.d | Risk Factors | 62
|  | 3.e | Additional Resources | 63
|  | 3.f | Sources and Uses of Funds | 64
| 4 | Public Support
|  | 4.a | Community Benefits | 65
|  | 4.b | Government and Community Support | 67
|  | 4.c | Public Involvement Plan | 68
| 5 | Project Benefits/Compatibility
|  | 5.a | Public Benefits | 69
|  | 5.b | Economic Benefits | 70
THiIRD | HAMPTON ROADS CROSSING |  |  | i
CONCEPTUAL PROPOSAL
TA BL E OF CO N TE NTS
| FIGURE | TAB | TITLE | PAGE
| 1.1 | 1.a | Organization Chart | 3
| 2.1 | 2.a | EIS Alignment | 41
| 3.1 | 3.a | Project Alignment | 56
| 3.2 | 3.c | Project Schedule | 58
APPENDICIES |  |  | TITLE
| A | Skanska USA Civil, Inc. Brochure
| B | Washington Group International, Inc. Brochure
| C | Parsons Brinckerhoff Quade & Douglas, Inc. Brochure
| D | Jacobs Civil Inc. Brochure
| E | Annual Report 2003 Skanska AB
| F | Audited Financial Statement of Skanska USA Civil, Inc.
| G | Audited Financial Statement of Tidewater Skanska, Inc.
| H | 10-K Annual Report of Washington Group International, Inc.
| I | Annual Report 2003 Royal BAM Group nv
| J | Flatiron Brochure
THiIiRD | HAMPTON ROADS CROSSING |  |  | ii
CONCEPTUAL PROPOSAL
EX EC UT I VE S UM M AR Y
` | Introduction – Skanska/Washington/BAM (SWB), a joint venture of Skanska USA, Inc. (Skanska),
Washington |  | Group | International |  |  | (Washington) |  |  | and | Royal |  | BAM | Group |  | nv | (BAM) | is | submitting |  | an
unsolicited proposal for the development, design, construction, financing, operation and maintenance of
the Third Hampton Roads Crossing. | [6 empty] | This conceptual proposal is submitted in accordance with the
Virginia | Department |  |  | of | Transportation’s |  |  | (VDOT) |  | implementing |  |  | guidelines |  |  | for | the | Virginia |  | Public
Private Transportation Act of 1995. | [6 empty] | This conceptual proposal is based upon the Major Investment Study
(MIS), the Environmental Impact Statement (EIS) and the 2001 Record of Decision. | [16 empty] | The design team of
Parsons Brinckerhoff Quade & Douglas, Inc. and Jacobs Civil, Inc. (Jacobs) (formerly JE Sverdrup) will
serve as the engineer-of-record. | [5 empty] | The SWB Team members have been involved with the design and/or
construction of all of the tunnels and bridge-tunnels in the Hampton Roads area.
` | Project Configuration - The Third Hampton Roads Crossing involves the construction of 13 miles
of limited access expressway in addition to widening 15 miles of interstate highway. The project will
cross | Hampton | Roads |  | and | the | Elizabeth |  | River | via trestles |  |  | and | two | new | tunnels |  | to | provide |  | greatly
enhanced mobility in the Hampton Roads area.
` | Project Need - The Hampton Roads region is a major residential, commercial and tourist area in
Virginia and home to many military installations. | [8 empty] | Increasing traffic volumes have outstripped capacity.
The MIS and EIS predict traffic levels will become so critical that by the time any solution is in place
the | regions | economy |  | will | be | stifled | and | noxious |  | emissions |  |  | will | impair | the | health |  | of | individuals.
Without | near-term |  | relief, |  | the | quality | of | life | and | the | region’s |  | economy |  | will | decline. |  | Several |  | recent
occurrences of major gridlock are just another indication that the Third Hampton Roads Crossing is
needed earlier rather than later.
` | Consistency | with |  | Concept |  | - | The | EIS | provides |  | an | estimate |  | of | $4.4 | billion | to | construct |  | the
Metropolitan Planning Organization’s (MPO) Locally Preferred Alternative that was approved by the
Commonwealth Transportation Board. In 2000 VDOT anticipated that the project could be completed in
2014. This conceptual proposal contains alternatives that dramatically reduce the project’s cost and
accelerates the completion date of the Third Hampton Roads Crossing. | [13 empty] | The concepts that are offered by
this conceptual proposal are consistent with the Third Hampton Roads Crossing MIS and EIS. | [18 empty] | Specific
recommendations for the project’s financing and development are included.
` | Environmental |  | - | All | known | environmental |  |  | issues |  | can | be | prudently |  | and | economically |  |  | mitigated
based | upon | SWB’s |  | proposed |  | develop-finance-design-build-operate-maintain | [9 empty] | approach |  |  | and | SWB’s
experience with addressing the same issues on previous projects. The entire Conceptual Proposal is
based upon the Record of Decision (ROD) issued on June 4, 2001.
` | Utility Plan – The SWB Team will assume responsibility for utility coordination and relocations.
Proactive communication will be maintained with impacted utility owners to quickly resolve all utility
issues.
` | Property Acquisition – According to the EIS, 38 residences and 11 businesses will need to be
relocated. The SWB Team will be responsible for obtaining real estate and will prepare the necessary
documentation for VDOT in cases where taking by eminent domain is required.
THI1RD | HAMPTON ROADS CROSSING | [18 empty] | E-1
CONCEPTUAL PROPOSAL
EX EC UT I VE S UM M AR Y
` | Design | and | Construction |  |  | Guarantees |  | – | SWB | will | sign | a | Comprehensive |  |  | Agreement |  | and | will
guarantee a fixed price and completion date.
` Institutional and Public Support - Testimony provided during the preparation of the MIS and the
EIS, | discussions |  | with | governmental, |  |  | private |  | sector | groups |  | and | individuals |  |  | indicate |  | overwhelming
support for the project at all levels. | [5 empty] | Most see it as needed now. | [5 empty] | The project is supported by:
 | Metropolitan Planning Organization
 | Hampton Roads Third Crossing Commission
 | Commonwealth Transportation Board
 | Hampton Roads Partnership
 | Hampton Roads Chamber of Commerce
 | U.S. Military
 | Virginia Port Authority
 | Hampton Roads Maritime Association
SWB will initiate a public information program in coordination with VDOT to assure that all interested
parties | are | provided |  | information |  | and | given |  | opportunities |  | to | ask |  | questions |  | and | provide | meaningful
comments. |  | All | available | communication |  |  |  | techniques |  | will | also |  | be | used | to | keep | the | general | public
informed.
` | Construction Process – The SWB Team will manage the construction process to ensure that it is
consistent with established VDOT standards and practices. The maintenance of traffic plans will assure
that an adequate number of lanes will be maintained throughout the construction period. Construction
will be primarily over water on a new alignment and is expected to have minimal traffic impacts. | [18 empty] | The
proposed accelerated design-build schedule will further reduce traffic impacts while providing a greatly
enhanced |  | facility | in | significantly |  | less | time | than | the | design-bid-build |  |  |  | process |  | originally |  | planned | by
VDOT.
` | QC/QA Process – SWB Team members are thoroughly familiar with VDOT’s quality control and
quality assurance requirements. | [5 empty] | SWB will develop a project specific Design Quality Management Plan
and a Quality Assurance/Quality Control Inspection Program. The new crossing will reflect the attention
to | detail | and | quality | that | is | inherent | in | the | transportation |  | projects |  |  | that | the | team | has | designed | and
constructed in the past.
` | Small, Women and Minority-Owned Business (S/W/M) Participation – SWB has developed the
following approach for involving S/W/M owned businesses:
 | Actively solicit the involvement of S/W/M owned firms via announcements and notices published in
local and regional construction journals and other periodicals.
 | Set aside scopes of work for S/W/M owned firms and encourage them to participate in the pre-
qualification process and bidding opportunities.
 | Utilize S/W/M owned businesses who have a long standing relationship with SWB team members.
 | Include provisions regarding S/W/M compliance in all subcontracts.
 | Review the SWB Team's progress, attaining the S/W/M goals, on a regular basis.
THI2RD | HAMPTON ROADS CROSSING | [17 empty] | E-2
CONCEPTUAL PROPOSAL
EX EC UT I VE S UM M AR Y
` | Business Plan – SWB has developed a financial plan that is included in TAB 3. | [11 empty] | This preliminary
plan presents a realistic approach based on conservative assumptions to financing the Third Hampton
Roads Crossing. The plan is based on financing the project by means of tax-exempt toll revenue bonds,
augmented by funds from public sources. | [7 empty] | The total cost of the facility will be between $2.5 billion and
$ 4.0 billion and will require up to $1.8 billion in public funds. | [11 empty] | Toll levels and the amount of public
funds required vary with the alternative selected. | [8 empty] | If the project is built in phases, public funds in the
amount of approximately $0.5 billion plus a reasonable toll will provide the critical first two phases of
the project.
` | Benefits of the SWB Plan - The benefits that are described by this conceptual proposal are a result of
the evolution of the SWB Team’s planning. | [8 empty] | A considerable effort has been made to develop a plan that
is simple and straightforward while offering the most benefit to the public.
 | The Third Hampton Roads Crossing is a multi-modal facility that incorporates an exclusive High
Occupancy Vehicle/Bus Rapid Transit lane reserving space for the future addition of Light Rail
| Transit. |  | This multi-modal solution provides a more flexible facility and extends the life and use of
this transportation corridor.
 | SWB will complete the crossing within 7 years after the Notice to Proceed, while the most recent
| VDOT |  | plan | was | based | on | a | 14-year | period | using | the | traditional | design-bid-build | contracting
| approach. |  | This accelerated schedule will provide the vital traffic handling capacity that is needed
| now | as | well | as | the | capacity | to | accommodate |  | the regions continued demographic and economic
growth.
 | SWB’s proposed public-private partnership approach significantly reduces the time and cost of the
| Third Hampton Roads Crossing. | [6 empty] | Simply put, the use of private sector funding now saves over
$1,000,000,000 compared to the current plan.
 | The SWB plan provides the quickest solution to alternative hurricane evacuation routes and frequent
road system incapacitations due to accidental occurrences.
 | Adequate transportation infrastructure is provided to support the continued growth of the cities that
surround the corridor and new maritime facilities such as the Craney Island port and the new Maersk
Terminal.
 | As an environmentally friendly solution, SWB’s concept will reduce air pollution.
 | An electronic toll collection system such as EZ-Pass or Smart Tag will be used to minimize the
impact of toll collection on riders and permit implementation of variable pricing strategies.
 | Design and construction contracts will emphasize use of local and regional firms.
 | The SWB plan utilizes the most highly experienced team of world class contractors imaginable for
the development, design and construction of the Third Hampton Roads Crossing.
THI3RD | HAMPTON ROADS CROSSING | [12 empty] | E-3
CONCEPTUAL PROPOSAL
|  |  |  | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[8 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
Identify the legal structure of the firm, or consortium of firms making the proposal. | [9 empty] | Identify the
organizational structure for the project, the management approach and how each partner and
major subcontractor in the structure fits into the overall team.
Legal Structure
Skanska USA, Inc. (Skanska), Washington Group International, Inc. (Washington), and Royal BAM
Group nv (BAM) have formed the joint venture Skanska/Washington/BAM (SWB). SWB has been
formed to develop, finance, design, build, operate and maintain the Third Hampton Roads Crossing.
Skanska is the joint venture's managing partner. The project will be executed through the three firms’
respective operating companies: Tidewater Skanska, Inc. (Tidewater), Washington Group International
(Washington), and Flatiron Construction Corp. (Flatiron). | [6 empty] | Tidewater is the joint venture’s operating
manager. | Joining SWB is the design team of Parsons Brinckerhoff Quade & Douglas, Inc. (PB) and
Jacobs Civil, Inc. (Jacobs) (formerly Sverdrup), Goldman Sachs, who will be the financial advisor, and
Kaufman & Canoles, P.C., the legal advisors. |  |  |  |  | Collectively, this group of joint venture partners and
designers is known as the SWB Team. The SWB Team members have experience working together to
successfully | execute | large | and | complex | projects. | As | the | development | proceeds, | SWB | may | add
additional partners and subcontractors to the team. A brief description of each SWB Team member is
presented below.
Organizational Structure
` Tidewater Skanska, Inc. (Tidewater) of Norfolk, Virginia is a long-term VDOT contractor with a
reputation for delivering outstanding marine and transportation facilities under budget and ahead of
schedule. The firm’s more notable projects include the construction of the award-winning Coleman
Bridge, the original Chesapeake Bay Bridge Tunnel, the Hampton Roads Bridge Tunnel, the Cooper
River Bridge in Charleston, SC, the new Woodrow Wilson Bridge Foundations, and the Pinners Point
Interchange. Tidewater is a wholly owned subsidiary of Skanska. | [7 empty] | Skanska’s financial strength and the
broad capabilities of its subsidiary firms, together with those of the other team members, will make the
dream of a Third Hampton Roads Crossing a reality.
` | Washington Group International (Washington) of Boise, Idaho, is a leading transportation design-
build firm with significant project development experience. The firm’s construction history dates to
1912 with the founding of its heritage company, Morrison Knudsen. In joint venture with Interbeton,
Washington Group built the Monitor Merrimac Memorial Bridge Tunnel (the second Hampton Roads
crossing) and the Ted Williams Tunnel in Boston. Project development transportation projects include
the E-470 Toll Road in Denver and the Pocahontas Parkway (Route 895) in Virginia. Washington’s
experience will be used in conjunction with that of the other Partners to provide the depth of capability
needed for this project.
` | Flatiron Construction Corp. (Flatiron) of Longmont, Colorado, is a subsidiary of Royal BAM
Group nv of the Netherlands. Interbeton, Inc. (Interbeton), a Flatiron subsidiary, in joint venture with
Washington, built the Monitor Merrimac Memorial Bridge Tunnel and the Ted Williams Tunnel in
Boston. Interbeton also recently completed the widening of the Chesapeake Bay Bridge Tunnel trestles.
Additionally, BAM has completed many submerged tunnels in Europe. | [7 empty] | BAM’s financial strength and
THI1RD | HAMPTON ROADS CROSSING | [10 empty] | 1
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
experience will be used in conjunction with that of the other team members to provide the resources that
will be required to undertake this project.
` | Parsons Brinckerhoff Quade & Douglas, Inc. (PB) and Jacobs Civil, Inc. (Jacobs) are the premier
marine tunnel and transportation designers in the United States. They have designed all of the tunnel and
bridge-tunnel facilities in the Hampton Roads area and thousands of highways and bridges around the
world. | PB | will | draw | upon | its | extensive |  | environmental | and | permitting | experience |  | to | perform | any
required permit applications or supplements to the environmental document. Additionally, the long and
successful relationship that PB and Jacobs have with the other SWB Team members makes them the
ideal firms to engineer and design the Third Hampton Roads Crossing.
` | Goldman, Sachs & Co. (Goldman Sachs) is one of the nation’s largest, most diversified and most
highly regarded investment banks. | [5 empty] | The firm was founded in 1869 as a dealer of commercial paper, a
product Goldman Sachs created. | [5 empty] | Since the firm’s founding, it has expanded to over 22,000 employees
located in 67 regional offices in 24 countries. It’s Municipal Bond Department, established in 1951, is
part of the firm’s Fixed Income, Currency and Commodities Division and is a leader in transportation
finance. | The Department consists of 130 dedicated municipal bond professionals who coordinate their
activities to underwrite and distribute municipal securities and maintain a liquid secondary market for
issues the firm manages.
` | Kaufman & Canoles, P. C. (K&C) is a full-service commercial law firm with offices in Virginia
Beach, Chesapeake, Hampton, Newport News, Norfolk, Richmond and Williamsburg with over 125
attorneys. |  | K&C has been a nationally recognized firm in the area of tax-exempt and public finance
since 1974 and has served as either bond counsel, underwriters counsel, issuer counsel or borrowers
counsel in hundreds of financing. | [5 empty] | The firm has participated in unsolicited proposals under the Public-
Private | Transportation |  |  | Act | and | financings |  | which | resulted | therefrom, | either | directly | or | indirectly,
including | the | Commonwealth’s |  |  |  | Route | 28 | improvements | in | Loudoun | and | Fairfax | Counties | and | the
Chesapeake Toll Road. |  |  |  | The firm has experience in arranging, structuring and coordinating all aspects of
public-private projects and economic development initiatives.
Figure 1.1, Organization Chart, shows the proposed organizational relationships between the Virginia
Department of Transportation (VDOT), the three SWB joint venture partners, and the designers, PB and
Jacobs and the financial advisors, Goldman Sachs.
THI2RD | HAMPTON ROADS CROSSING | [13 empty] | 2
CONCEPTUAL PROPOSAL
|  |  | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  |  |  | 1 . a | O r g a niza t i o na l Appr o a c h
Figure 1.1 | Organizational Chart
|  | Skanska/Washington/BAM (SWB) |  |  | 63-20
Organization
|  |  | Skanska USA |  | Or
|  | Washington Group International |  |  | Public Agency
Royal BAM Group nv
| Designers | Financial Advisors |  | Legal Advisors
| PB / Jacobs | Goldman Sachs |  | Kaufman & Canoles
The SWB Team members are all recognized leaders in the engineering and construction industry, as
demonstrated by current rankings by Engineering News-Record (ENR) shown on Table 1.1. These firms
are also among the world’s oldest and largest companies in the industry. Their experience in the region
is unparalleled; having been involved with all of the tunnels and bridge-tunnels in the Hampton Roads
area. | Fortune magazine has selected Skanska AB, the parent company of Skanska, USA, as the most
admired company in the world in the category of Engineering and Construction. The ratings were based
on quality of management; quality of products and services; innovativeness; long-term investment value;
financial soundness; ability to attract, develop and retain talent; community responsibility; and use of
corporate assets.
Table 1.1 Engineering News-Record Rankings
SWB Team Member/Ranking
ENR
| Category | Skanska | Washington | BAM | PB | Jacobs
Domestic |  | 6 | 9 | 95
Construction
International |  | 1 | 35 | 36
Construction
Transportation |  | 4 | 10 | 15 | 3 | 5
Bridges |  | 2 |  | 4 | 4 | 3
Highways |  | 4 | 7 | 15 | 2 | 5
Design |  |  | 20 |  | 11 | 4
THI3RD | HAMPTON ROADS CROSSING |  |  |  |  | 3
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
Management Approach
SWB’s management approach is a clear, comprehensive plan to develop the Third Hampton Roads
Crossing. The plan addresses the managerial, financial, technical, legal, environmental, and construction
requirements for the project.
` Program Manager - The SWB executive committee will appoint a program manager to manage the
project with the guidance of the managing partner, Skanska. | [10 empty] | To support the program manager, SWB
will have a full-time and integrated staff consisting of experienced, qualified personnel from the joint
venture team members. This staff will award contracts for planning, design and construction services to
augment | the | services |  | that | will | be | provided | by | the | operating |  | companies. |  | SWB |  | will | function | as | an
integrated staff without any company affiliation under the direction of the program manager.
` | Project | Office | - | The | cornerstone |  | of | SWB’s | approach |  | is | partnering | with |  | a | strong | emphasis |  | on
communication. SWB will facilitate communication by establishing a Project Office that co-locates the
design, | public | information |  |  | and | construction |  | management |  |  | staffs | of | SWB | and | VDOT. |  | All | decision-
makers will be co-located in one office to promote their interaction, which has been crucial to our
successful completion of many other large projects.
Design Management Approach
` | Design Team - PB will lead the design team. PB will make extensive use of the broad experience and
depth of its engineering and design organization, the largest transportation engineering staff in the U.S.
Jacobs will also provide engineering and design personnel to augment the design team. The combined
resources of PB and Jacobs represent an enormous technical capability with extensive experience in
bridge and tunnel design.
` | Preliminary | Engineering |  |  | – | Preliminary |  | engineering |  | activities |  | will | be | performed |  |  | by | PB/Jacobs.
SWB will provide constructibility reviews (including safety) throughout the preliminary engineering
effort to identify practical and expedient construction approaches that will shorten schedules and lower
construction costs. SWB will develop realistic construction cost estimates based on its team members’
local | marine | and | heavy |  | civil | construction |  | experience. |  | This |  | interactive |  | design |  | team | will | prepare
construction |  | cost | estimates |  | and | schedules |  | that | will | be | used | for | the | Plan | of | Finance |  | and | the
Comprehensive Agreement.
` | Design Management Plan – SWB will develop a Design Management Plan (DMP) within three
weeks of receipt of the notice-to-proceed. The DMP will include procedures and processes that take
advantage of the SWB Team's design-build experience. The DMP will promote the efficient execution
of the design effort. Lessons learned in implementing DMPs for previous design-build projects will
contribute to an efficient, effective management plan for the Third Hampton Roads Crossing. The DMP
will prescribe a number of measures to control the design including:
 | Clearly defining the scope of services for each subconsultant. Each subconsultant will be managed
by an assigned manager.
 | Developing of detailed design schedules, consistent with the project's master schedule, for use in
managing the development and production of all construction packages.
THI4RD | HAMPTON ROADS CROSSING | [17 empty] | 4
CONCEPTUAL PROPOSAL
[6 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
 | Ensuring that design quality control will be an integral part of the design management process by
reflecting the procedures outlined in the Design Quality Management Plan.
 | Enhancing coordination and communication with a local area network (LAN) that provides e-mail
and access to standard software, as well as design documents as they are developed.
 | Providing guidance for advance planning requirements to define each construction package.
 | Outlining communication procedures with VDOT and other public agencies.
` | Work Plans - Work plans will be prepared for each design element. A project-specific work plan,
including detailed tasks for each construction package, will be prepared concurrently with the DMP. The
work plans will define managerial and technical approaches that will be used for the engineering and
design of each package. The plans will define the scope of services, staffing requirements, tasks and
their objectives, deliverables, coordination requirements, permitting requirements, lead times, budgets,
schedules, and reporting procedures relative to each package.
Construction Management Approach
SWB’s construction management concept takes full advantage of the team’s strong local presence and
experienced | construction |  |  | supervisors. |  | Over | the | years, | the | SWB | members | have | developed | excellent
relationships with local suppliers and subcontractors.
` | Safety - SWB’s construction concept enhances safety performance by placing safety technicians in
the field to monitor the construction activities of our crews and subcontractors. Safety is a top priority.
The SWB Team’s construction safety manager will report to the program manager.
` | Task Forces - The Project Office will house all members of the task force groups that are responsible
for constructing the crossing. The construction supervisors will be active participants in the task force
groups to facilitate the development of effective and efficient designs. The design team project engineers
and design discipline leads will assume a leadership role. Task force meetings will be convened on a
regular basis to coordinate construction requirements and collaborate on design decisions. The task forces
will also facilitate constructibility by reviewing the construction packages prior to each formal design
review.
` | Task-specific Work Plans - The development of task-specific work plans by the superintendent that is
supervising each construction operation is another cornerstone of SWB’s construction approach. These
detailed | work | plans | will | include | a | work | plan | narrative, | schedule, |  | budget, | staff-hour | factors, | quality
specifications, safety procedures, and testing methods for each operation. SWB’s construction approach
requires the safety, quality, and the production staffs to review these plans before construction begins. The
goal is to increase quality, lower cost, and raise productivity.
` | Constructability - Constructability is built into our construction concept through constructability
reviews and regular construction planning meetings. All field representatives attend these meetings,
including | production |  | supervisors, |  | subcontractors, |  |  | quality | and | safety | personnel, | and | the | construction
management | staff. | Three-week |  | look-ahead |  |  | schedules | are | coordinated |  | during | these | meetings. | These
schedules focus on the current week and following two-week period.
THI5RD | HAMPTON ROADS CROSSING | [12 empty] | 5
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[12 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
` | Permitting | - | The | SWB | Team | will | establish | a | permit | task | force | to | address | all | Commonwealth,
federal, and local requirements. This task force will interface with public agencies to obtain permits in a
timely manner and will serve as the focal point to resolve any permit compliance issues.
Public Information Program
SWB’s approach to public outreach is to use education and information to maintain a high level of
communication. SWB’s two primary public information goals will be to (1) gain and maintain public
support for the Third Hampton Roads Crossing and (2) to provide the support needed for the public to
deal with construction concerns on a daily basis.
It is SWB’s experience that when the traveling public is aware of potential impacts, knows what is
happening, and why, how, and when it will happen, they are more apt to maintain positive opinions
regarding construction. SWB’s public information team will apply this approach to it’s interaction with
residents, businesses, |  |  |  | commuters, |  | local | governments, the Department of Defense, and Virginia Port
Authority. SWB will also use this approach to assist VDOT counterparts to inform the traveling public.
Public information goals will be accomplished by: establishing and maintaining clear and open lines of
communication with internal teams and external audiences; meeting public information needs through
the media, public meetings and a project web site; and providing accurate information through other
audience-appropriate distribution methods. Interaction with neighborhoods and businesses impacted by
SWB’s construction activities will occur via communication between the public information specialists
and the production crews. |  |  |  | As issues/concerns are brought up through a project website or hotline, the
public information specialist will interact with the production crews to develop appropriate resolutions.
Plan of Finance
The SWB Team’s financial consultant will prepare a Plan of Finance that includes sources and uses of
funds. A preliminary Plan of Finance is provided in TAB 3. This plan will be refined as more information
becomes available during the Detailed Technical Proposal Phase.
Non-Recourse Toll Revenue Bond Sale
SWB’s approach to funding includes the sale of non-recourse toll revenue bonds. This is a common
approach that is used for funding transportation improvement throughout the U.S. SWB is prepared to
create, in conjunction with VDOT, an IRS 63-20 not-for-profit private corporation or a public agency,
for such a sale. SWB services would include supporting the 63-20 or public agency in the bond rating
process as well as the bond underwriting and sale.
Comprehensive Agreement
SWB will execute a Comprehensive Agreement with VDOT for the development rights associated with
the Third Hampton Roads Crossing, subject to the mutual satisfaction of both parties regarding the terms
and conditions. SWB will agree to the contract amount and assume liability for the project’s design and
construction. As a public-private venture, VDOT will be responsible for providing services including
design reviews, right-of-way acquisition coordination, assistance with permitting, coordination with the
Federal Highway Administration, and quality assurance acceptance activities.
THI6RD | HAMPTON ROADS CROSSING | [13 empty] | 6
CONCEPTUAL PROPOSAL
[6 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
Contracting Opportunities
Each of the world-renowned companies that constitute the SWB Team relies upon subcontractors to
provide specialty services for selected portions of the work. Based on the team members’ experience and
extensive current operations in the Hampton Roads area, the SWB Team anticipates awarding subcontracts
for the following construction specialties:
 | Tunnel segment fabrication |  |  |  |  | Concrete |  |  |  | Earthwork and paving
 | Pre-cast concrete members |  |  |  |  | QA/QC |  |  |  | Public relations
 | Right-of-way services |  |  |  |  | Diving |  |  |  | Specialty design
 | Electrical |  |  |  |  | Reinforcing steel |  |  |  | Utility relocation
 | Mechanical |  |  |  |  | Slurry walls |  |  |  | Metal finishes
 | Dredging |  |  |  |  | Rip-rap and gravel |  |  |  | Traffic management system
 | Tug boat support |  |  |  |  | Equipment rental
Early indications are that there will be a sufficient number of subcontractors available within the region
to meet the majority of subcontracting needs. It is expected that subcontracts will be competitively
awarded based on price and capabilities.
The | SWB | Team | is | particularly | sensitive | to | contracting | with | minority | and | women-owned | firms. | To
broaden the level of participation of these firms, SWB will conduct workshops and provide written
notice to all known minority and women-owned firms that specialize in the work that SWB will be
subcontracting. Drawings and specifications will be available to all minority and women-owned firms
that express an interest in bidding opportunities. SWB will negotiate in good faith with all potential
subcontractors.
THI7RD | HAMPTON ROADS CROSSING | [11 empty] | 7
CONCEPTUAL PROPOSAL
[5 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . b | Ex pe r i e nc e
Describe the experience of each firm and the key principals involved in the proposed project.
Describe the length of time in business, business experience, public sector experience and other
engagements of the firm(s). |  |  | The lead organization must be identified.
Team Experience
Skanska USA, Inc. (Skanska), Washington Group International (Washington), and Royal BAM Group
nv (BAM) have formed the joint venture Skanska/Washington/BAM (SWB). SWB has been formed to
undertake the development, financing, design, construction, operation and maintenance of the Third
Hampton | Roads | Crossing. | The | SWB | lead | organization | and | the | managing | joint | venture | partner | is
Skanska. | Skanska’s wholly owned subsidiary, Tidewater Skanska, Inc. will be the operating manager.
` | Skanska AB (Sweden) founded 1887
Skanska USA founded 1971
Tidewater Skanska, Inc. founded in 1932 as heritage company Tidewater Construction Corporation
` | Washington Group International founded 1912 as heritage company Morrison Knudsen
` Royal BAM Group nv (Netherlands) founded in 1869
Flatiron Construction Corp. established in the United States in 1970
Interbeton established in the United States in 1986
The SWB Team firms are international leaders of the construction industry, and have successfully built
thousands of projects for both the public and private sectors. Their reputations and experience have
earned them financial stability and unsurpassed capabilities that are crucial to the development of the
Third Hampton Roads Crossing.
SWB was formed to bring together the country’s premier companies with experience in the design and
construction | of | complex | bridges | and | tunnels. | SWB | selected | the | most | experienced | engineering | and
design team in the world, Parsons Brinckerhoff Quade & Douglas, Inc. (PB) and Jacobs Civil, Inc.
(Jacobs), for this type of facility. |  |  |  | These companies, which together with Goldman Sachs as financial
advisor, collectively compose the SWB Team, have long-standing working relationships. The team’s
capabilities are ideally suited to solve the pressing need for a Third Hampton Roads Crossing.
The operating companies of the three joint venture members will self perform a substantial amount of the
construction. Tidewater, Washington, and Flatiron have the demonstrated experience and capability to
develop the Third Hampton Roads Crossing. These firms have consistently proven their capability to
accomplish difficult projects within time and budget constraints.
Table 1.2, Representative Submerged Tunnel Projects, provides a list of similar facilities that have been
designed and/or constructed by SWB Team members. This table illustrates the depth of the teaming
experience on similar projects, and also clearly indicates that one or more of the SWB Team member
firms have designed or built all of the bridge-tunnels in the Hampton Roads area.
THI8RD | HAMPTON ROADS CROSSING | [11 empty] | 8
CONCEPTUAL PROPOSAL
|  | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[5 empty] | 1 . b | Ex pe r i e nc e
Table 1.2 Representative Submerged Tunnel Projects
Year
Tunnel |  | Skanska | Washington | BAM | PB | Jacobs
Completed
Hampton Roads Area
Hampton Roads Bridge | 1957 |  |  |  | 
Tunnel #1
Hampton Roads Bridge | 1976 |  |  |  | 
Tunnel #2
Monitor Merrimac | 1992 |  |  |  |  | 
Memorial Bridge Tunnel
Downtown | 1952 |  |  |  | 
Tunnel #1
Downtown | 1988 |  |  |  | 
Tunnel #2
Midtown Tunnel #1 | 1962 |  |  |  | 
Chesapeake Bay Bridge | 1964 |  |  |  |  | 
Tunnel #1
Other Locations
Ft. McHenry Tunnel | 1986 |  |  |  |  | 
Ted Williams Tunnel | 1995 |  |  |  |  | 
BART Tunnel | 1966 |  |  |  | 
Tunnel de Noord, | 1992 |  |  | 
Netherlands
Willemspoor Tunnel | 1994 |  |  | 
Netherlands
Alphen aan den Rijn, | 1997 |  |  | 
Netherlands
Conway Tunnel, Wales | 1991 |  |  | 
Medway Tunnel, UK | 1995 |  |  | 
THI9RD | HAMPTON ROADS CROSSING |  |  |  |  | 9
CONCEPTUAL PROPOSAL
[6 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . b | Ex pe r i e nc e
Firm Experience
` | Tidewater | Skanska, |  | Inc. | (Tidewater) |  | of | Norfolk, | Virginia, | is | a | wholly-owned | subsidiary | of
Skanska USA which is owned by Skanska AB. Skanska has over $5 billion in assets, employing in
excess of 60,000 people in over 50 countries. Total sales in 2004 were approximately $14 billion, of
which 85 percent was construction. Skanska USA was established in 1971 and recorded 2003 sales of
over $5.6 billion. |  | Skanska USA is the sixth largest U.S. construction contractor. Tidewater is a wholly-
owned subsidiary of Skanska USA and will act as the lead organization in executing the design-build
delivery approach for this project. |  |  |  |  | Skanska’s representative projects include:
 | Chesapeake Bay Bridge Tunnel, VA | [10 empty] | $200M
 | Hampton Roads Bridge Tunnel, VA | [10 empty] | $48M
 | Oresund Link: Sweden-Denmark Bridge Tunnels | [10 empty] | $758M
 | Bart Submerged Tunnel, San Francisco, CA | [10 empty] | $180M
 | Coleman Bridge, Yorktown, VA | [10 empty] | $73M
 | Berkley Bridge, Norfolk, VA | [10 empty] | $75M
 | BART Extension to San Francisco Airport, CA | [10 empty] | $526M
 | Light Rail (Air Train) at JFK Airport, NY | [9 empty] | $1300M
 | Richmond - San Rafael Bridge, CA | [10 empty] | $485M
 | Ft. McHenry Tunnel, Baltimore, MD | [10 empty] | $850M
 | Woodrow Wilson Bridge, Alexandria, VA | [10 empty] | $130M
 | Pinners Point Interchange, Portsmouth, VA | [10 empty] | $145M
 | Cooper River Bridge, Charleston, SC | [10 empty] | $550M
 | I-495/US 1 Interchange, Alexandria, VA | [10 empty] | $147M
` | Washington Group International (Washington) is headquartered in Boise, Idaho, and has a history
dating back to 1912 with the founding of its heritage company, Morrison Knudsen. Today, Washington is
an international engineering, construction, and construction management company offering public and
private | clients | a | full | range | of | services—engineering, |  |  | self-performed |  |  | construction, |  | construction
management, program management, operations and maintenance, and development programs—through
six | operating | units: | Infrastructure, |  |  | Power, | Energy | and | Environment, |  | Defense, | Industrial/Process, |  | and
Mining. With annual revenues exceeding $3 billion, Washington has approximately 27,000 employees at
work in 40 states and more than 30 countries. | [6 empty] | Washington’s representative transportation projects include:
 | Monitor Merrimac Memorial Bridge Tunnel, Hampton Roads, VA | [10 empty] | $138M
 | Ted Williams submerged tunnel, MA | [10 empty] | $251M
 | I-15 Corridor Reconstruction, UT | [9 empty] | $1380M
 | E-470 Toll Road Design-Build, CO | [10 empty] | $568M
 | Route 895 Pocahontas Parkway, VA | [10 empty] | $322M
 | Hudson-Bergen Light Rail System, NJ | [9 empty] | $1670M
` | Flatiron Construction Corp. (Flatiron) is a wholly owned subsidiary of Royal BAM Group nv
(BAM), which was founded in 1869 and currently employs over 30,000 people. | [12 empty] | BAM has over $8
billion in annual sales. Flatiron will be the operating company for BAM in executing this project. In
addition to having constructed over 50 submerged tunnels and highways in Europe, BAM’s recent U.S.
projects include:
THI1R0D HAMPTON ROADS CROSSING | [13 empty] | 10
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[16 empty] | 1 . b | Ex pe r i e nc e
 | Chesapeake Bay Bridge Tunnel Parallel Crossing | [12 empty] | $220M
 | Ted Williams submerged Tunnel, Boston, MA | [12 empty] | $251M
 | Eastern Transportation Corridor, Orange County, CA | [12 empty] | $772M
 | Carolina Bays Parkway, Myrtle Beach, SC | [12 empty] | $240M
 | Monitor Merrimac Memorial Bridge Tunnel, Hampton Roads, VA | [12 empty] | $138M
 | Cooper River Bridge, Charleston, SC | [12 empty] | $550M
` | Parsons | Brinckerhoff |  |  | Quade | & | Douglas, |  | Inc. | (PB) | and | Jacobs | Civil, |  | Inc. | (Jacobs) | have | been
selected | to | serve | as | the | engineer-of-record |  |  | based |  | on | the | firms’ | experience |  | gained | by | successfully
engineering |  | similar | projects |  | and | their | working |  | relationships |  |  | with | the | operating |  | companies. | PB | was
founded in 1885 and currently employs 9,000 people in 250 offices worldwide. Their portfolio includes
the completion of 40 submerged tunnel projects. For 86 years, Jacobs has participated in and has a proven
track record in the planning, design, and construction supervision of tunnels, shafts and major underground
transportation projects within the USA. Jacobs has 27,000 employees worldwide. This project will be built
on a develop-finance-design-build-operate and maintain basis, a delivery approach that is familiar to both
firms. | PB’s and Jacob’s representative projects include:
 | Fort McHenry Tunnel, Baltimore, MD | [12 empty] | $850M
 | Monitor Merrimac Memorial Bridge Tunnel, Hampton Roads, VA | [12 empty] | $138M
 | Ted Williams Submerged Tunnel, Boston, MA | [12 empty] | $251M
 | Chesapeake Bay Bridge Tunnel, VA | [12 empty] | $260M
 | Second Downtown Elizabeth River Tunnel, Norfolk, VA | [12 empty] | $300M
 | Coleman Bridge, Yorktown, VA | [12 empty] | $73M
 | Cooper River Bridge, Charleston, SC | [12 empty] | $550M
Key Project Personnel
 | David J. Eastwood, PE – Senior Vice President of Skanska USA; Chairman and CEO of Tidewater
| Skanska, Inc. |  | David Eastwood has 37 years of construction and 23 years in executive management
experience. He has been involved in all types of heavy construction in the United States, Britain, the
Middle-East and Hong Kong.
 | Edwin | W. | McLaughlin, |  | PE | – | President |  | of | Tidewater |  | Skanska, |  | Inc. | Ed | McLaughlin |  | has
responsibility for operations and performance on this project. He has 45 years of diversified design
and construction experience with focus on marine construction and bridges for the past 19 years.
 | Francis X. Watson, PE – Project Director for Tidewater Skanska, Inc. | [12 empty] | Francis (Buddy) Watson is
responsible for managing the project team for the SWB joint venture. He has 39 years of diversified
| hands-on | experience |  |  | managing |  | design, |  | construction, |  |  | contracting |  | operations |  | and | facilities
maintenance.
 | Frank Finlayson – Senior Vice President, Project Development, Washington Group International.
Frank Finlayson has 19 years of project financing experience, specializing in the management of
private-sector financing efforts for public/private partnerships in infrastructure-related markets. He is
responsible for directing all financing and business-related activities in negotiations with the public
| sector | and | private | debt | markets. |  | He | also | works |  | with | state | and | local | government |  | officials | to
implement public-sector requirements with that of the private sector.
THI1R1D HAMPTON ROADS CROSSING | [17 empty] | 11
CONCEPTUAL PROPOSAL
[5 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . b | Ex pe r i e nc e
 | Rich Linford – Senior Vice President, Design-Build Operations, Washington Group International.
Richard Linford has 29 years of experience in the construction industry with expertise in project
management and operations. He has extensive experience managing complex design-build highway
projects and interfacing with government agencies, the public, and other project stakeholders.
 | Dirk Langerbroek – Managing Director of Interbeton. | [6 empty] | Dirk Langerbroek has over 30 years of
engineering and construction experience.
 | Geoff D. Collins – Executive Vice President, Interbeton, Inc. | [7 empty] | Geoff Collins has over 33 years of
| engineering | and | construction |  | experience | including |  | serving | as | the | Chief | Engineer |  | for | the | Ted
Williams Tunnel in Boston.
 | William D. Smith, PE – President of Parsons Brinckerhoff Quade & Douglas, Inc. | [12 empty] | Bill Smith has
| 39 years of experience in engineering and design management. | [7 empty] | He joined PB in 1988 after serving
in various positions for global consulting firms.
 | William Allen, PE – Senior Vice President, Transportation Group, Jacobs Civil, Inc. | [12 empty] | Bill Allen has
over 30 years of engineering and design experience related to all types of facilities. He has extensive
experience in privatization and design-build approaches to complete transportation facilities.
The | projects | described | on | the | following | pages | are | representative |  | of | the | depth | of | experience |  | and
capability that the SWB Team members bring to the Third Hampton Roads Crossing. These projects
demonstrate a strong performance record and depth of our teaming experience. References are provided
for each project.
THI1R2D HAMPTON ROADS CROSSING | [15 empty] | 12
CONCEPTUAL PROPOSAL
[8 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . b | Ex pe r i e nc e
GEORGE P. COLEMAN BRIDGE REPLACEMENT
Yorktown, Virginia
This double-leaf swing span over the York River is the | [9 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
second longest in the world. Although procured by VDOT | [9 empty] | RESPONSIBLE:
under traditional design-bid-build procedures, Tidewater | [9 empty] | Tidewater scope of work included project management,
Skanska, | Inc. | (Tidewater) |  |  | managed |  | a | significant |  | quality assurance, redesign of truss and shoring systems,
engineering effort that allowed for construction of six 77- | [9 empty] | bridge construction, and electronic toll collection system.
foot-wide bridge spans, complete with barriers, lighting, | [9 empty] | Parsons Brinkerhoff was the project designer.
signs, and highway markings to be prefabricated 30 miles
downstream in the Hampton Roads. | [9 empty] | PROJECT COST:
$73 million
In May 1996 during a 12-day scheduled bridge closure, the
existing bridge spans were lifted and removed by barges | [9 empty] | COMPLETE DATE:
utilizing an elaborate pumping system and replaced with | [9 empty] | August 1996
the new wider bridge spans. Within nine days, the Coleman
Bridge | was | open | to | the | public, | three | days | ahead | of | REFERENCE:
schedule. | The | project |  | received | six | construction/design |  |  |  | Virginia Department of Transportation
awards for this major accomplishment and was featured on | [9 empty] | George Clendenin, State Structure and Bridge Engineer
the July 8, 1996 ENR cover. | [9 empty] | 1401 E. Broad Street
[10 empty] | Richmond, VA | 23219
(804) 786-2714
THI1R3D HAMPTON ROADS CROSSING | [11 empty] | 13
CONCEPTUAL PROPOSAL
[11 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[17 empty] | 1 . b | Ex pe r i e nc e
CAROLINA BAYS PARKWAY
Myrtle Beach, South Carolina
The Carolina Bays Parkway is a design-build project that | [12 empty] | Extensive use was made of contractors and suppliers in
connects SC Route 9 to US Route 501 in Horry County. | [12 empty] | the Myrtle Beach area.
The Parkway involves 22 miles of limited access divided
highway | with |  | 26 | bridges |  |  | including |  |  | one | over | the | ACTIVITIES FOR WHICH THE FIRM IS
Intracoastal Waterway. | [12 empty] | RESPONSIBLE:
Flatiron Structures Co., a wholly owned subsidiary of Royal
This unusual procurement required proposers to provide | [12 empty] | BAM | Group, | and | Tidewater | Skanska, | Inc. | formed | the
the | maximum |  | amount |  | of | scope | for |  | a | fixed | budget. |  | Palmetto Transportation Constructors, and were awarded this
Palmetto | Transportation Constructors not only provided | [11 empty] | design-build project.
all the scope on the SCDOT's’ list, but offered additional
scope | items | to | enhance |  | the |  | entire | area |  | transportation |  |  | PROJECT COST:
system. | [12 empty] | $254 million including exercised options
A significant amount of right-of-way is being procured by | [12 empty] | COMPLETION DATE:
the | design/build |  | contractor |  |  | as | well | as | by | SCDOT. |  | The | 2002
contractor is responsible for managing the entire process.
The | contractor |  | is | also | managing |  | relocation |  |  | of | existing |  | REFERENCE:
utilities. | [12 empty] | South Carolina DOT
ATTN: Berry Still, Project Manager
Protection | of | the |  | fragile | low |  | country |  | environment |  |  | was | P. O. Box 191
given a high priority. Design and construction were fast | [12 empty] | Columbia, SC |  | 29201
tracked | with | an | overall |  | schedule |  | of | 30 |  | months. | Some |  | (803) 737-9967
sections were completed early and turned over to SCDOT
and the motoring public.
THI1R4D HAMPTON ROADS CROSSING | [19 empty] | 14
CONCEPTUAL PROPOSAL
[9 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[19 empty] | 1 . b | Ex pe r i e nc e
PARALLEL CROSSING – CHESAPEAKE BAY BRIDGE TUNNEL
Cape Charles, Virginia
Interbeton |  | and | Jacobs | (Sverdrup) |  | were | both |  | involved |  | in | In | the | 1960s, | Jacobs |  | provided | planning, |  | design | and
this parallel crossing of the Chesapeake Bay consisting of | [11 empty] | construction |  |  | management |  | services | for | the | first | crossing.
12 | miles | of | low-level | trestle |  | over | the | mouth |  | of | the | Jacobs provided comprehensive construction management
Chesapeake Bay, a high-level bridge across the northern | [11 empty] | services |  | for | the | total | 17.5 | mile-long | crossing |  | which
navigation channel, as well as 3 miles of on-shore highway | [11 empty] | includes |  | the | 12 | miles | of | precast, | prestressed |  | concrete
work. | The | parallel | crossing |  | required |  | over | 2000 |  | precast, |  | trestle, along with four man-made islands in open water,
prestressed, |  | concrete | cylindrical |  |  | piles, | over |  | 600 | precast, |  | two | sunken |  | tube | tunnels, | two | high-level |  | bridges, | and | a
reinforced |  | concrete | pile |  | caps | and | over | 2000 |  | precast, |  | 8,319 foot causeway. In 1995, Sverdrup provided similar
prestressed |  | double | “T” | deck | units. |  | Most | of | this | precast |  | services for the parallel bridge crossing.
concrete | was |  | manufactured |  | at | a | purpose-built |  |  | on-site
facility. The contract included refurbishment of the original | [11 empty] | PROJECT COST:
crossing and all the work was completed in four years per | [11 empty] | $220 million
the original contract.
COMPLETION DATE:
ACTIVITIES FOR WHICH THE FIRMS WERE | [11 empty] | July 1999
RESPONSIBLE:
Interbeton was part of a construction joint venture to build | [11 empty] | REFERENCE:
the | parallel | crossing |  | of | the | Chesapeake |  | Bay |  | Bridge. |  | Chesapeake Bay Bridge Tunnel District
Interbeton set up and ran the precast yard, drove piles, and | [11 empty] | Attn: Paul Burnette, Jr.Chief Engineer
erected | precast |  | concrete |  | deck | units. | Interbeton |  |  | also |  | 32386 Lankford Highway
installed | electrical |  | and | electronic |  |  | services |  | as | well | as | Cape Charles, VA 23310
performed |  | partial | demolition |  |  | and | refurbishment |  |  | of | the | (757) 331-2960
existing bridge.
THI1R5D HAMPTON ROADS CROSSING | [21 empty] | 15
CONCEPTUAL PROPOSAL
[11 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[15 empty] | 1 . b | Ex pe r i e nc e
“TED WILLIAMS” BOSTON HARBOR TUNNEL
Boston, Massachusetts
A | Washington |  | Group-led |  |  | joint | venture |  | with | Interbeton |  |  |  | ACTIVITIES FOR WHICH THE FIRMS WERE
constructed |  | twin-tubes |  |  | highway |  | tunnels |  | beneath |  |  | Boston |  | RESPONSIBLE:
harbor | between |  | Logan |  | Airport |  | and | South |  | Boston. |  | This |  | Washington Group and Interbeton were responsible for all
$251 | million, |  | 3,850-foot-long |  |  |  | immersed |  |  | tube |  | tunnel |  | construction work. PB prepared concept designs and served
consisted | of | 12 | sections |  | of | double-tube |  |  | (binocular) |  |  | steel |  | as GEC to the Turnpike Authority
concrete | lined |  | segments |  |  | that | were | placed |  | in | a | harbor
bottom trench.
PROJECT COST:
$251 million
The | tube | segments |  | were |  | fabricated |  | at | Sparrows |  |  | Point,
Maryland, |  | where |  | they | were |  | lined | and | weighted |  |  | with
COMPLETE DATE:
concrete and sealed with bulkheads. The segments were
1994
then | loaded | on | a | submersible |  |  | barge | and |  | towed |  | to | the
Boston Inner harbor. After removal from the barge, each
REFERENCE:
segment was placed in a 90-foot-wide trench dredged to a
Massachusetts Turnpike Authority
minimum |  | depth |  | of | 95 | feet | at | mean |  | low |  | water.
Joseph J. Allegro
Approximately, |  |  | 1,057,000 |  |  | cubic | yards |  | of | material |  | was
10 Park Plaza
dredged from the harbor bottom. After tube placement, the
[14 empty] | Boston, MA | 02116
trench was backfilled with a minimum of 5 feet of cover.
(617) 342-1226
THI1R6D HAMPTON ROADS CROSSING | [15 empty] | 16
CONCEPTUAL PROPOSAL
[10 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
EASTERN TRANSPORTATION CORRIDOR
Orange County, California
The | Eastern | Transportation |  |  | Corridor |  | (ETC) |  | is | a | 40-km | ACTIVITIES FOR WHICH THE FIRM IS
four/six | lane | new |  | limited | access |  | toll | road | in |  | Orange | RESPONSIBLE:
County, | California. |  |  | The | owner | is | the | Foothill/Eastern |  |  |  | Flatiron led a joint venture to design and build the Eastern
Transportation Corridor Agency (TCA), a California Joint | [11 empty] | Transportation | Corridor. | Additionally, | the | joint | venture
Power | Agency. |  | The | ETC | facility |  | includes |  | four |  | fully | was responsible for all toll equipment. Quality assurance
directional |  | interchanges, |  |  | a | sophisticated |  |  |  |  | traffic | and quality control were provided by the contractor for
management system, and a state-of-the-art toll collection | [11 empty] | the entire project.
and | violation | enforcement |  |  | system, |  | including |  | full-speed
electronic toll collection. The project was approved under | [11 empty] | PROJECT COST:
the | Federal |  | Highway |  | Administration’s | [5 empty] | Special | $801 million
Experimental Project (SEP-14) as a design-build project.
COMPLETION DATE:
The project included four fully directional interchanges, | [11 empty] | February 1999 (14 months ahead of schedule)
69 bridges, placement of 1.3 million tons of asphalt and
moving 67 million cubic yards of earth and rock. | [11 empty] | REFERENCE:
Foothill Eastern Transportation Corridor Agency
The | project | was | financed |  | with | private |  | capital |  |  | raised | Gary H. Steinke
through $1.4 billion in tax-exempt bonds issued by the | [11 empty] | 201 E. Sandpointe, Suite 200
TCA. The bonds were placed in approximately one hour, | [11 empty] | Santa Ana, California | 92707
based | in | part | on | the | fixed | price |  | and | guaranteed |  |  | (949) 513-3437
completion date proved by the construction joint venture.
THI1R7D HAMPTON ROADS CROSSING | [16 empty] | 17
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
MONITOR MERRIMAC MEMORIAL BRIDGE-TUNNEL
Newport News, Virginia
ACTIVITIES FOR WHICH THE FIRMS WERE
The Washington Group-led joint venture with Interbeton
RESPONSIBLE:
Inc. | constructed | the | submerged |  | tube | tunnel | between
SWB Team members were responsible for all phases of
Newport News and Suffolk, Virginia. The $138 million
design and construction.
submerged tube tunnel is 4,500 feet long and consists of
15 sections of double-tube steel segments.
PROJECT COST:
The tube segments were fabricated, lined and weighted | [7 empty] | $138 million
with concrete, sealed with bulkheads at Sparrows Point,
Maryland, then towed to the Hampton Roads site. Each | [7 empty] | COMPLETE DATE:
segment was individually placed in a 90-foot-wide trench | [7 empty] | 1990
dredged to a maximum depth of 120 feet at mean low
water. | After | tube | placement, | the | trench | was | backfilled | REFERENCE:
with a minimum of 5 feet of cover. Sverdrup designed the | [7 empty] | Virginia Department of Transportation
tunnel | and | provided | construction |  | services. |  | Tidewater | Thornhill Snoddy
Skanska, Inc. built the northern approach to the tunnel. | [7 empty] | 1401 E. Broad St.
[8 empty] | Richmond, VA | 23219
(804) 786-2945
THI1R8D HAMPTON ROADS CROSSING | [9 empty] | 18
CONCEPTUAL PROPOSAL
[9 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
I-95 TOLL CONNECTOR AND VIETNAM VETERANS MEMORIAL BRIDGE
Henrico and Chesterfield Counties, Virginia
The Pocahontas Parkway was the first construction project | [10 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
awarded |  | under | the | Commonwealth |  | of | Virginia’s |  | Public- |  | RESPONSIBLE:
[11 empty] | Washington | Group | developed | financing | on | the | project,
Private Transportation Act of 1995. The 8.8-mile parkway
was a joint venture member, and served as the design-
involved the financing, design, and construction of a four-
[11 empty] | build | contractor. | Parsons | Brinckerhoff | was | responsible
lane | limited-access |  |  | highway | with | major | interchanges |  |  | at
for the design.
Interstate-295 in the east and Interstate-95 in the west. It
also includes a high-level crossing over the James River | [10 empty] | PROJECT COST:
south | of | Richmond, |  | Virginia, |  | providing |  | clearance |  | for | $362 million
ocean-going |  | vessels |  | bound | for | the | Port | of | Richmond.
Besides the nearly 9 miles of four-lane roadway and the | [10 empty] | COMPLETE DATE:
James River Bridge, the project also includes construction | [10 empty] | September 2002
of | three | interchanges, |  | ten | major | overpasses |  |  | and | grade
REFERENCE:
separation structures, and toll collection facilities. | [10 empty] | Virginia Department of Transportation
Jim Fariss, Project Manager
1401 E. Broad St.
[11 empty] | Richmond, VA | 23219
(804) 786-2998
THI1R9D HAMPTON ROADS CROSSING | [16 empty] | 19
CONCEPTUAL PROPOSAL
[8 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[16 empty] | 1 . b | Ex pe r i e nc e
INTERSTATE HIGHWAY 15 RECONSTRUCTION
Salt Lake City, Utah
This | project | involved |  | demolishing |  | and | reconstructing |  |  | ACTIVITIES FOR WHICH THE FIRM WAS
approximately 17 miles of Interstate 15 through the heart of | [9 empty] | RESPONSIBLE:
Salt Lake City, Utah. The $1.4 billion contract is Utah’s | [9 empty] | PB | was | the | program | manager | for | Utah | DOT. | PB | was
involved in all pre award activities and was responsible for
largest ever public works project, and at the time was the
[10 empty] | design | and |  | construction | oversight. |  | Washington |  | Group
largest design-build highway project underway anywhere
participated in this project as a design-build joint venture
in the U.S. Work included demolition and reconstruction of
partner responsible for overall project execution and as a
144 bridges, | half | of | which |  | are | steel | girder | and | the | major project designer as part of the design joint venture.
remainder | precast/prestressed |  |  |  | girder | structures |  | carrying
4.5 million square feet of new concrete pavement to build | [9 empty] | PROJECT COST:
four to six lanes of concrete highway in each direction. The | [9 empty] | $1.4 billion
work was conducted under a stringent time schedule for
completion | in | time | for | the | opening | of | the | 2002 | Winter | COMPLETE DATE:
Olympics. | [9 empty] | May 2001
REFERENCE:
Utah Department of Transportation
John Njord, Director
4501 S. 2700 W.
[10 empty] | Salt Lake City, UT |  |  | 84119-5998
[10 empty] | (801) | [6 empty] | 965-4113
THI2R0D HAMPTON ROADS CROSSING | [18 empty] | 20
CONCEPTUAL PROPOSAL
[10 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[18 empty] | 1 . b | Ex pe r i e nc e
POPLAR ISLAND RESTORATION PROJECT
Chesapeake Bay, Maryland
In | April | 2000, | Tidewater |  | Skanska, |  | Inc. was |  |  | awarded | a | The project includes spillway structures, stone roadways
$35.6 | million |  | contract | with |  | the | U.S. | Army |  | Corps | of | and subaqueous power and phone lines to the island. This
Engineers |  | for | the | construction |  |  | of | the | Poplar | Island |  | project required approximately 2,000,000 cubic yards of
Wildlife |  | Habitat | Restoration |  |  | project. |  | This |  | project | is | fill and 300,000 tons of stone. The project was awarded
located in the Chesapeake Bay, approximately 11⁄2 miles | [11 empty] | on | a | best | value | procurement | based | on | the | price | and | a
from the closest point of landfall, near Tilghman Island, | [11 empty] | technical proposal.
Maryland.
ACTIVITIES FOR WHICH THE FIRM WAS
Tidewater constructed a system of stone and earthen dikes | [11 empty] | RESPONSIBLE:
to reclaim Poplar Island from erosion and to create cells | [11 empty] | Tidewater was responsible for all construction and quality
that | will | be | filled | with | dredge |  | material |  | taken | from |  | control.
shipping channels in the area. The resulting island was
planted | to | establish |  | upland |  | and | lowland |  | environmental |  |  | PROJECT COST:
habitats for wildlife. | [11 empty] | $40 million
The work included building approximately 21,500 LF (4 | [11 empty] | COMPLETE DATE:
miles) of stone and earthen dikes. Stone berms were first | [11 empty] | December 2001
constructed along the toe of the proposed dikes. Material
was dredged from the bottom of the bay and pumped into | [11 empty] | REFERENCE:
a | specially | prepared |  | containment |  |  | area. |  | The | sand | was | Scott Johnson
loaded | to | trucks, | then | placed |  | and | shaped |  | to | form | the | U. S. Army Corps of Engineers
dikes. | External |  | faces | of | the | earthen |  | slopes | are | covered |  | Baltimore District Corps of Engineers
with | multiple |  | layers | of | graded |  | stone | to | prevent | future |  | P. O. Box 1715
erosion. | [11 empty] | Baltimore, MD |  |  | 21203-1715
(410) 962-6030
THI2R1D HAMPTON ROADS CROSSING | [21 empty] | 21
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
MASSACHUSETTS AVENUE INTERCHANGE
Boston, Massachusetts
A | joint | venture | including | Interbeton |  | and | Skanska | was | ACTIVITIES FOR WHICH THE FIRMS WERE
awarded the C 12A3 contract, which was located at the | [8 empty] | RESPONSIBLE:
southern most end of the Central Artery/Tunnel project. | [8 empty] | Interbeton, Skanska, and their joint venture partner were
The major challenge on this job was to work over, around, | [8 empty] | responsible for all construction work. PB provided GEC
and | through | the | major | highway | that | carries | traffic | into
services to the owner.
downtown |  | Boston | without | interrupting |  | traffic. | Work
preparation and traffic management played a critical role
PROJECT COST:
in the execution of the project. The project consisted of:
$200 million
 | Construction of 18 new bridges (totaling 2.3 miles)
| consisting of 220 steel tub girders, 216 precast | [7 empty] | COMPLETE DATE:
| I-beams and 42 precast post tension concrete box | [7 empty] | July 2001
beams.
 | In total, 102,000 CY of concrete was poured | [7 empty] | REFERENCE:
 | Construction of 4.6 miles of at-grade roads | [7 empty] | Massachusetts Highway Department
 | Construction of two storm water pump stations | [7 empty] | Paul Dye
C/O Bechtel Parsons Brinckerhoff
185 Kneeland Street
Boston, MA 02127
THI2R2D HAMPTON ROADS CROSSING | [9 empty] | 22
CONCEPTUAL PROPOSAL
[8 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
NEW CARQUINEZ BRIDGE
Crockett, California
As part of a joint venture, Interbeton Inc. constructed this | [8 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
new | suspension |  | bridge | across | the | Carquinez |  | Strait | RESPONSIBLE:
navigation |  | channel. | The | joint | venture | members |  | include | Interbeton, Flatiron and their joint venture partner were
two | sister | companies, |  | FCI | Constructors |  | North | and | responsible for all construction work.
Flatiron Structures Company.
PROJECT COST:
The new Carquinez structure is the third bridge at this site | [8 empty] | $231 million
and replaces the existing bridge, built in 1927, and carries
traffic westbound on I-80. The bridge built in 1958 was | [8 empty] | COMPLETE DATE:
seismically |  | retrofitted | and | carries | I-80 | traffic | eastbound. |  | 2003
The | three-span, | 3,465-foot-long |  |  | structure | is | the | nation’s
first new major suspension bridge built in 35 years. The | [8 empty] | REFERENCE:
bridge features two 400-foot concrete towers, supported by | [8 empty] | Caltrans
driven | piles. | The | new | 82-foot-wide | deck | accommodates |  |  | Kenneth Loncharich
four | vehicle | lanes |  | (including | one | HOV | lane), | a | C/O Caltrans Toll Bridge Program
bicycle/pedestrian lane, and wide shoulders. | [8 empty] | Hilltop Construction Field Office
3045 Research Drive
Richmond, CA
(510) 262-6808
THI2R3D HAMPTON ROADS CROSSING | [9 empty] | 23
CONCEPTUAL PROPOSAL
[8 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
SOUTH BOSTON INTERCHANGE
Boston, Massachusetts
The South Boston Interchange (Contract C01A6) is part | [10 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
of the Boston Central Artery / Tunnel Project executed by | [10 empty] | RESPONSIBLE:
the | Massachusetts |  | Highway | Department. |  |  | The | project |  | is | Interbeton Inc. and Flatiron were responsible for the cast-
located | in | South | Boston | and | is | part | of | the | I-90 |  | in-place tunnel sections, design and construction of earth
Massachusetts Turnpike extension to Logan Airport. | [10 empty] | retaining | structures, | temporary | bridges, | and | dewatering
systems. PB provided GEC services for the owner.
This contract borders two other Central Artery / Tunnel
contracts. | The | work | included | the |  | construction |  |  | of | a | PROJECT COST:
reinforced | cut-and-cover |  | tunnel | with |  | a | length | of | 1,250 |  | $225 million
feet, a width varying between 280 and 330 feet, and an
excavation depth of approximately 50 feet. | [10 empty] | COMPLETE DATE:
2002
REFERENCE:
Massachusetts Highway Department
Chester Choy-Hee
C/O Bechtel / Parsons Brinckerhoff
273 Summer Street
[11 empty] | Boston, MA | 02111
THI2R4D HAMPTON ROADS CROSSING | [15 empty] | 24
CONCEPTUAL PROPOSAL
[8 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[18 empty] | 1 . b | Ex pe r i e nc e
I-93 / I-90 INTERCHANGE
Boston, Massachusetts
Interbeton, | together |  | with |  | Slattery | Skanska, | a | Skanska |  | ACTIVITIES FOR WHICH THE FIRM WAS
subsidiary, | as | part | of | a | joint | venture, | constructed |  | this | RESPONSIBLE:
project located at the intersection of I-93 and the eastern | [9 empty] | Interbeton |  | and |  | Slattery | Skanska, |  | in | joint | venture, | were
terminus of the Massachusetts Turnpike (I-90). It is the | [9 empty] | responsible for fabrication and construction of 10,000 feet
largest | construction |  | contract |  |  | ever | awarded | by | the | of pre-cast, post-tensioned viaduct; construction of three
Massachusetts Turnpike Authority. The joint venture used | [9 empty] | jack-box tunnels with similar cross sections (80 feet wide
jacked-boxed tunnels under the active Amtrak rail lines at | [9 empty] | by | 40 | feet | high | by | 167, | 258 | and | 379 | linear | feet);
South Station; this method is the only means to construct | [9 empty] | construction |  |  | of | 3,000 | feet | of | cut-and-cover |  | tunnel, | and
tunnels under the tracks without interrupting rail service. | [9 empty] | 3,700 feet of cast-in-place boat section. PB provided GEC
The Project was completed in 2003. | [9 empty] | services for the owner
Interbeton was awarded the National Value Engineering | [9 empty] | PROJECT COST:
Award | for | best | technical |  | value | engineering |  | change |  | $420 M
proposal to Big Dig Contracts and was the Grand Award
Winner of ACEC's 2000 Engineering Excellence Award, | [9 empty] | COMPLETE DATE:
amongst various other national and international awards. | [9 empty] | 2003
REFERENCE:
Massachusetts Highway Department
Philip Rice
C/O Bechtel / Parsons Brinckerhoff
210 South Street
[10 empty] | Boston, MA |  |  | 02110
THI2R5D HAMPTON ROADS CROSSING | [19 empty] | 25
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
BAY AREA RAPID TRANSIT – TRANS-BAY TUBE
San Francisco, California
In 1966 Tidewater Skanska, Inc. and their joint venture | [8 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
Partners | were | awarded | the | $180 | M | contract | for | the | RESPONSIBLE:
construction | of | a | submerged | tunnel |  | between |  | San | The Tidewater Skanska Joint Venture was responsible for
Francisco | and | Oakland, | CA. | The |  | project | involved |  | all construction between the Oakland and San Francisco
fabrication, dredging, placement, and finishes for a 3.6- | [8 empty] | tunnel portals. Parsons Brinckerhoff was the lead project
mile-long | tunnel | having | a | 48-foot | by | 24-foot | cross |  | designer.
section. The tunnel was placed in depths up to 135 feet
below the water surface. The facility is in use to provide | [8 empty] | PROJECT COST:
commuter rail services. The project was built to stringent | [8 empty] | $180 million
seismic requirements. Parsons Brinckerhoff led the joint
venture for design and construction management for the | [8 empty] | COMPLETE DATE:
Trans-Bay Tube. | [8 empty] | 1970
REFERENCE:
Bay Area Rapid Transit Authority
THI2R6D HAMPTON ROADS CROSSING | [9 empty] | 26
CONCEPTUAL PROPOSAL
[11 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[20 empty] | 1 . b | Ex pe r i e nc e
E-470 TOLL ROAD DESIGN-BUILD PROJECT
Denver, Colorado
Washington Group’s involvement with the E-470 project
began | in | 1991. |  | The | E-470 |  | Public | Highway |  |  | Authority
contracted |  | with |  |  | Washington |  |  | Group | to | create |  | and
implement a comprehensive development plan to finance,
design, and build Segments II and III of the E-470 project.
Working |  | closely |  | with | the | Authority, |  |  | Washington |  |  | Group
designed a multi-tiered financing structure and conducted
environmental, |  |  |  | socioeconomic, |  |  | and | logistical |  |  | studies | to
support the plan. Washington Group acted as the owner’s
agent to assist in arranging the financing, which consisted
of long-term toll revenue bonds. The financing was secured
solely through toll revenues and vehicle registration fees.
The | financing |  |  | raised | for |  | the | facility |  | amounted |  | to
$658,829,600. | [12 empty] | In January 2000, after a competitive bid process, a second
[13 empty] | Washington |  |  | Group-led |  | joint | venture | began |  | work | on
Segment IV under a design-build contract. Segment IV is a
Washington, as sponsor of the Platte River Constructors, | [12 empty] | 12.5-mile, four-lane, controlled-access toll road that skirts
Ltd. | (PlRC) |  | joint |  | venture, |  | performed |  | the | design-build |  |  | the | northern |  | edge | of | the | Denver | metropolitan |  |  | area.
contract |  | for | Segments |  | II | & | III | including |  | transportation |  |  | Washington |  |  | Group-led |  |  | joint | venture |  | provided
planning, |  | preliminary |  |  | engineering, |  |  | financial |  |  | assistance, |  | transportation |  |  | planning, |  | engineering |  | and | design, |  | pre-
final |  | engineering, |  |  | construction, |  |  |  | and | construction |  |  | construction, |  |  | and | procurement |  | and | construction |  | services.
management |  |  | services. |  |  | Washington |  |  | Group |  | (dba | MK | Segment IV includes 7 interchanges, 43 bridges, 1 mainline
Centennial) |  |  | is | the | engineer-of-record |  |  |  |  | for | the | civil | and 8 ramp toll plazas. The roadway crosses various streets,
engineering and design of Segments II & III. Washington | [12 empty] | county roads, and the major transportation arteries of I-76,
Group was instrumental in the redesign of the roadway to | [12 empty] | US | 85, | and | the | BNSF | and | Union | Pacific |  | railroads.
decrease |  | project |  | costs | and enable |  |  | the project to become |  |  |  |  | Wetlands |  | replacement |  |  | was | also | included | in | the | project
financially |  | feasible. |  |  | We | managed |  | an | extensive |  |  | public | scope. Ongoing coordination was maintained with a wide
involvement program and also provided conceptual design, | [12 empty] | spectrum of agencies and local jurisdictions to obtain the
evaluated |  | alternative |  |  |  | alignments, |  |  | performed |  |  | value | necessary permits and approvals for construction. Similar
engineering |  |  | studies, |  | and | developed |  |  | the | toll | revenue |  | extensive |  | coordination |  |  | was | undertaken | with |  | all | utilities
preliminary engineering in support of toll revenue studies. | [12 empty] | companies.
As | the | managing |  | partner/Design-Builder |  |  |  |  | on | Segments |  | II | ACTIVITIES FOR WHICH THE FIRM WAS
and III, Washington Group constructed 12 interchanges and | [12 empty] | RESPONSIBLE:
33 bridges. |  | Washington |  |  |  | Group |  | also | constructed |  |  | three | Washington |  | Group |  | was | the | Joint | Venture | Sponsor |  | and
mainline toll plazas and 16 ramp toll structures. Other work | [12 empty] | provided |  | project |  | development |  |  | assistance, | design, |  | and
included |  | 135 | utility |  | relocations, |  |  | 2.9 | acres | of | wetlands
construction.
creation and mitigation, lighting, signing, and landscaping
as well as design and installation of 60 lanes of electronic
PROJECT COST:
toll | collection |  |  | equipment. |  |  | Washington |  |  | Group |  | self-
$567 million for the two design-build contracts
performed |  | grading, |  |  | drainage |  |  | work, | paving, |  |  | bridge
construction, signage, and emergency services coordination
COMPLETION DATE:
and | managed |  |  | the | subcontracted |  |  | portions |  | of | the | work.
2003
Washington Group also assisted in securing new right-of-
way was for essentially the entire length of the project and
REFERENCE:
managed |  | hazardous |  |  | materials |  |  | encountered |  |  |  | during
E-470 Public Highway Authority
construction. Segments II and III work was completed with
over two million work hours and no lost-time accidents. | [12 empty] | Matt McDole, Segments II & III
The | project |  | received |  | state |  | and | national |  | quality |  | award | (303) 537-3470
recognition for asphalt paving and state and | [12 empty] | Ed Delozier, Executive Director, Segment IV
local recognition for sensitivity to endangered species in | [12 empty] | (303) 537-3470
the corridor, and no litigation or claims.
THI2R7D HAMPTON ROADS CROSSING | [22 empty] | 27
CONCEPTUAL PROPOSAL
[11 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[23 empty] | 1 . b | Ex pe r i e nc e
HUDSON-BERGEN LIGHT RAIL TRANSIT PROJECT
Hudson and Bergen Counties, New Jersey
active Hoboken Terminal and Rail Yard to the north; the
[13 empty] | Hudson |  | River |  | to | the | east; |  | the | navigable |  |  | Long |  | Slip
Channel to the south and west. The area was so restrictive
[13 empty] | that | Washington |  |  |  | Group |  | provided |  | a | temporary |  |  | access
[13 empty] | bridge |  | across |  | the | Long |  | Slip |  | Channel |  |  | to | support
construction.
In October 2000 Washington Group was awarded Phase II
[13 empty] | (MOS-2), |  | which |  |  | adds | 6.1 | miles |  | and |  | involves |  | seven
passenger stations including three intermodal stations, four
park-and-ride facilities, a 1,000-foot viaduct, a 4,000-foot
[13 empty] | tunnel, |  | and | the |  | construction |  |  | and | rehabilitation |  |  |  | of | 12
[13 empty] | bridges. |  | Washington |  |  | Group |  |  | has | completed |  |  | the | design,
[13 empty] | plans, | and |  | specifications |  |  |  | for | these |  | two | extensions. |  |  | In
[13 empty] | addition |  | to | managing |  |  | subcontractors |  |  |  | performing |  |  | certain
Washington Group heads 21 st Century Rail Corporation, a | [12 empty] | civil, electrical and tunneling work, Washington Group is
consortium |  | contracted |  |  | to | design, |  | build, | operation |  |  | and | self-performing the civil and architectural work for the light
maintain (DBOM) the $1.8 billion Hudson-Bergen Light | [12 empty] | rail | stations, |  | as | well | as | some |  | of | the | rail | systems |  | work.
Rail | Transit | system. |  |  | The |  | Hudson-Bergen |  |  | Light |  | Rail | Construction |  |  | of | the | southern |  |  | extension |  | is | complete |  |  | and
Transit | System |  | is | unique |  | in | two | ways: | it | was | the | first | Revenue Service began in November 2003. The northern
DBOM | project |  | in | the | United |  |  | States | for | a | "transit" |  | extension |  | is | scheduled |  |  | to | be | complete |  | and |  | in | Revenue
application, and it was the first time such a contract was | [12 empty] | Service by late 2005.
awarded to a single consortium. The project team remains
on schedule since construction began in December 1996 | [12 empty] | ACTIVITIES FOR WHICH THE FIRM IS
and the latest extension, 22nd Street Station, opened two | [12 empty] | RESPONSIBLE:
years | ahead | of | schedule. |  |  | At | completion, |  |  | the | 20.5-mile |  | As | the | DBOM |  | Program |  | Manager |  |  | and | Prime |  | Contractor.
system | will | include |  | 32 | stations, |  |  | six | intermodal |  | transfer |  | Washington Group is responsible for fast-track engineering
sites, | and | six | park-and-right |  |  |  | lots | and | will | serve |  | over | and | design; |  | procurement; |  |  |  | construction |  |  | management; |  |  |  | and
100,000 riders daily. | [12 empty] | startup and commissioning. As the Program Manager and
[13 empty] | prime |  | contractor, |  |  | Washington |  |  |  | Group |  | is | performing
Since its opening in April 2000, Washington Group has | [12 empty] | engineering |  |  | design |  | for |  | bridges, |  | stations, |  |  | the | vehicle
operated | Hudson-Bergen |  |  |  | Light |  | Rail | Transit |  | System |  | and | maintenance |  |  | facility, |  | utilities, |  |  | and | track. |  | In | addition |  | to
maintained |  | the | infrastructure, |  |  |  | rail | system, |  | stations |  | and | managing subcontractors performing certain civil, electrical
facilities. The operation and maintenance of the Light Rail | [12 empty] | and tunneling work, Washington Group is self-performing
Transit System will continue through April 2015. | [12 empty] | the civil and architectural work for the light rail stations, as
[13 empty] | well | as | some |  | of | the | rail | systems |  | work. |  | PB |  | provided
Phase | I, | awarded |  | in | 1996 |  | and | completed |  |  | in | 2002, | engineering services for the owner.
involved fast-track design and construction of the initial
9.5-mile | segment. |  |  | The | first |  | 7.5 | miles | of | the | light | rail | PROJECT COST:
system went into revenue service in the spring of 2000. | [12 empty] | $1.8 billion
This | initial | Minimum |  |  | Operating |  |  |  | Segment |  | (MOS-1)
currently serves 17 stations (five of which are intermodal | [12 empty] | COMPLETION DATE:
transfer | locations), |  |  | rail | and |  | bus | transit, |  | ferries, |  | and | 2005
another | four | stations |  |  | with |  | park | and | ride | facilities. |  | A
maintenance complex was also constructed and includes a | [12 empty] | REFERENCE:
100,000 square foot maintenance shop, a 75,000 square | [12 empty] | Charles Dickerson
foot LRV storage building, and a storage yard. | [12 empty] | Director HBLRTS
New Jersey Transit
The | final | build-out |  | of | MOS-1 |  | involved |  | a | 4,000+ |  | foot | One Penn Plaza
extension of the light rail. Although less than a mile in | [12 empty] | Newark, NJ 07105-2246
length, | this | final |  | portion |  | of | the | route | presented |  |  | many | (973) 491-8480
challenges |  | due | to | the | close |  | proximity |  | of | NJ | Transit's
THI2R8D HAMPTON ROADS CROSSING | [26 empty] | 28
CONCEPTUAL PROPOSAL
[10 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
REPLACEMENT OF THE COOPER RIVER BRIDGES
Charleston, South Carolina
Skanska USA Civil and Flatiron are joint venture partners | [12 empty] | ACTIVITIES FOR WHICH THE FIRMS ARE
on | the | Replacement |  |  | of | the | Cooper |  | River | Bridges. |  |  | RESPONSIBLE:
Execution |  | for | the | joint | venture |  | is | being | carried |  | out | by | Skanska USA and Flatiron are the joint venture design-
operating |  | companies |  |  | Tidewater |  | Skanska |  | and |  | Flatiron |  | builders; PB is the designer for the project.
Structures. PB is the designer for the joint venture. The
contract is for a design-build project to replace two old | [12 empty] | PROJECT COST:
bridges on US 17 in Charleston County, South Carolina. | [12 empty] | $531 million
The bridge will provide for eight lanes of traffic plus a
pedestrian/bike lane. It will rise 186 feet above the water | [12 empty] | COMPLETION DATE:
and | have | the | longest |  | cable-stayed |  |  | main | span | in | North |  | 2005
America. There will be a major interchange at each end of
the | bridge, |  | resulting | in | a | total | bridge |  | length | of | over | 2 | REFERENCE:
miles. | The |  | main | span | towers |  | are | founded | on | 10 | foot- |  | South Carolina Department of Transportation
diameter drilled shafts surrounded by rock islands. The | [12 empty] | Bobby Clair, Project Director
towers will stand 570 feet above the water. Some of the | [12 empty] | 212 Huger St.
required |  | right-of-way |  |  | is | being | procured |  | by | the | design- |  | Charleston, SC | 29403
build | contractor. |  |  | The |  | contractor |  | is | also | managing |  |  | (843) 534-5004
relocation |  | of | existing |  | utilities. |  | Protection |  | of | the | fragile
low country environment is being given a high priority.
Design |  | and | construction |  |  | is being |  | fast | tracked, with |  |  | the
bridge opening for traffic in 44 months. Extensive use is
being | made |  | of | local | contractors |  |  | and | suppliers |  | in | the
Charleston area.
THI2R9D HAMPTON ROADS CROSSING | [14 empty] | 29
CONCEPTUAL PROPOSAL
[9 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . b | Ex pe r i e nc e
WOODROW WILSON BRIDGE FOUNDATIONS
Oxon Hill, Maryland
Tidewater Skanska, a subsidiary of Skanska USA Civil, is | [10 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
leading a joint venture to construct the foundations of the | [10 empty] | RESPONSIBLE:
new Woodrow Wilson Bridges. The award of the $125 | [10 empty] | Tidewater Skanska was the general contractor for
million Bridge Foundation contract on May 17, 2001 for | [10 empty] | foundation construction.
the | new | Woodrow | Wilson |  | Bridge |  | was | the | first | major
contract of the $2.2 billion, eight-year project. The project | [10 empty] | PROJECT COST:
will replace the existing single 6 lane bridge with two 6 | [10 empty] | $125 million
lane bridges to ease the congestion of the I95/I495 main
artery | that | crosses | the |  | Potomac | River. |  | This | fast-track |  | COMPLETION DATE:
contract with a completion date of July 2003 consisted of | [10 empty] | April 2003, three months early
the construction of 17 bridge piers, 11 of which are in the
Potomac River. The construction involved 35 cofferdam | [10 empty] | REFERENCE:
cells and 48-in., 66-in., and 72-in. steel pipe piles ranging | [10 empty] | Maryland State Highway Administration
from 160 to 210 feet long. | [10 empty] | Mr. Paul Gudelski, District Engineer
6009 Oxon Hill Road
The | construction |  | of | the | Bascule | Piers | was |  | particularly |  | Suite 404
demanding |  | based | on | the | requirement |  | of | homogeneous |  |  | Oxon Hill, Maryland 20745
concrete |  | placements |  | in | excess | of | 6,000 | cy | with | tight | (301) 749-8801 ext. 229
temperature control to minimize thermal cracking.
THI3R0D HAMPTON ROADS CROSSING | [11 empty] | 30
CONCEPTUAL PROPOSAL
[6 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . b | Ex pe r i e nc e
PINNERS POINT CONNECTOR
Portsmouth, Virginia
The Pinners Point Connector will provide a new four-lane | [7 empty] | ACTIVITIES FOR WHICH THE FIRM IS
road | and | interchange | from | the | Western | Freeway | (VA- | RESPONSIBLE:
164) | in | Portsmouth, | VA | to | the | Portsmouth | Marine | Tidewater | Skanska | is | the | General | Contractor | for | this
Terminal, Martin Luther King Expressway (VA-58) and | [7 empty] | project.
the Midtown Tunnel. The project will have six bridges
traversing |  | through | residential |  | and | industrial | areas | PROJECT COST:
covering both water and land. The bridges will consist of | [7 empty] | $136 million
concrete piles, drilled shaft foundations, reinforcing steel,
structural |  | steel | beams, | concrete | beams, | concrete | deck, | COMPLETION DATE:
parapets and dredging an access channel for construction | [7 empty] | 2005
of the water bridge.
REFERENCE:
Also included in the project is a new Midtown Tunnel | [7 empty] | Virginia Department of Transportation
Building |  | Complex | and | roadwork |  | consisting | of | Mr. P.D. Gribok, Resident Engineer
excavation, |  | clearing, | grading, |  | paving, | utilities, | wick | Mr. Michael Johnson, Engineering Manager
drains, fence/guardrails, sound walls, electrical, signs and | [7 empty] | 1992 South Military Highway
traffic management system. Construction is scheduled for | [7 empty] | Chesapeake, VA 23320
1,000 days. | [7 empty] | (757) 494-2451
THI3R1D HAMPTON ROADS CROSSING | [14 empty] | 31
CONCEPTUAL PROPOSAL
[8 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
ORLANDO-ORANGE COUNTY EXPRESSWAY TOLL O&M
Orlando, Florida
Florida | Toll | Services—a |  | Washington |  |  | Group-led | joint | ACTIVITIES FOR WHICH THE FIRM WAS
venture—under a $123.7 million contract, operates 100- | [8 empty] | RESPONSIBLE:
miles of limited-access toll roads serving customers in the | [8 empty] | Operations and maintenance.
Orlando-Orange |  |  | County | area. | The | road | system | serves
PROJECT COSTS:
featured attractions such as Disney World and the Florida
$123.7 million
Citrus | Bowl. | It | includes | the | East-West |  | Expressway,
Central Florida Greene-Way, the Bee Line Expressway, | [8 empty] | COMPLETE DATE:
and | the | Western | Expressway. |  |  | Washington |  | Group | 2004
established the performance benchmarks for maximizing
revenues, violation enforcement capture, and increasing | [8 empty] | REFERENCE:
customer |  | satisfaction | levels, | as | well | as | designed | and | Michael Snyder, PE, Exec. Dir.
Orlando-Orange County Expressway Authority (OOCEA)
maintained |  | the | measurement | system |  | to | collect | relevant
(407) 316-3800
data. As a result, as the volume of traffic has increased by
92% since the beginning of the contract in 1995, we have
saved the client $2.8 million over the life of the contract,
saved 190,000 man-hours, and customer satisfaction has
increased by 61%.
THI3R2D HAMPTON ROADS CROSSING | [9 empty] | 32
CONCEPTUAL PROPOSAL
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . b | Ex pe r i e nc e
Alameda Corridor Transportation Authority |  | ACTIVITIES FOR WHICH THE FIRM WAS
RESPONSIBLE:
Goldman Sachs & Co. was hired in 1992 by the Alameda |  | Senior Manager and Co-Senior Manager
Corridor Transportation Authority (ACTA) to help
develop a finance plan for a $2.2 billion rail corridor to |  | PROJECT COSTS:
link the Ports of Los Angeles and Long Beach to the |  | $2.2 billion
central rail yards in downtown Los Angeles.
Goldman Sachs was hired based on our experience in the |  | REFERENCE:
Port/Railroad community and our experience in helping |  | Alameda Corridor
develop plans of finance for major infrastructure projects |  | Transportation Authority
among other items, we specifically aided the transaction |  | Dean Martin, Chief Financial Officer
in the following ways: |  | One Civic Plaza, Suite 650
Carson, California 90745
1. | Identification of Funding Sources – Goldman Sachs | (310) 233-7480
worked with the Ports, the LACMTA, and the USDOT to |  | (212) 878-7278
identify potential funding sources for the project. In
addition, our modeling work, combined with several
studies from outside consultants also allowed us to create
a set of proposed use fees for each type of cargo traveling
through the corridor to be paid by the railroads.
2. | Developed an extensive cash flow model which
served as the central decision-making tool for the
financing team
3. | Development of Feasible Financing Plan – Key
funding sources include equity contributions from the
two Ports, use fees paid by the railroads and an
innovative federal loan.
4. | Negotiation of Use and Operating Agreement with
Railroads
5. | Assisted in negotiating a federal loan which is being
used as the model for future TIFIA loan financings.
6. | Design/Build Contract – Helped ACTA determine a
project plan that will finish project 22 months ahead
of schedule.
7. | Tax Analysis – Together with tax counsel, Goldman
Sachs helped develop a tax strategy that allowed ACTA
to use a special Private Letter Ruling from the Internal
Revenue Service to sell a substantial portion of the bonds
tax-exempt.
8. | Financing Structure – Achieved investment grade
ratings on both the senior and subordinate lien bonds
9. | Developed an effective marketing plan, resulting in a
very successful financing in which the tax-exempt
bonds were 4 times oversubscribed.
On the pricing date, the tax-exempt bonds were 4 times
oversubscribed.
THI3R3D | HAMPTON ROADS CROSSING |  | 33
CONCEPTUAL PROPOSAL
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . b | Ex pe r i e nc e
CITY OF RENO , NEVADA – RETRACT PROJECT |  | contribution package from the Union Pacific Railroad. In
July of 2000, Goldman Sachs took the ReTRAC team to
In October 1997, Goldman Sachs was appointed senior
the U. S. Secretary of Transportation and applied for
manager for the City of Reno on its ReTRAC project.
TIFIA assistance. In December of 2000, ReTRAC was
The City has been attempting for the past 45 years to
awarded a $73.5 million TIFIA loan package as part of
relocate the transcontinental mainline that was owned by
the project’s funding. The final environmental Record of
the Southern Pacific (and now owned by Union Pacific)
Decision (ROD) was issued on February 26, 2001 and the
that runs directly through the heart of the City and within
TIFIA loan package was successfully completed for the
one block of 1,500 hotel rooms. Goldman Sachs was
first funding package in June of 2002. This project is the
appointed to help craft a finance plan for the $250 million
first senior/subordinated use of the TIFIA program, an
public-private partnership to drop the rail line into a 35-
innovative funding initiative created by the USDOT to be
foot deep trench through a 9-intersection corridor. Three
used in senior/subordinated leveraging of private
blocks in the central business district will be capped and a
investment dollars for complicated transportation projects
parkway/esplanade will appear in what has been a
of national significance.
railroad right-of-way for over 135 years. An AMTRAK
passenger rail station will be built in the new corridor as |  | The project is being built under a design-build contract
part of the overall transit plan for Reno. |  | with Granite Constructors, and was awarded in June of
2002. The notice to proceed was given September 15,
The now-final funding plan includes:
2002 and the project is expected to take almost four years
a. | 0.125% sales tax throughout Washoe County; | to complete.
b. | 1% room tax on downtown hotel properties;
ACTIVITIES FOR WHICH THE FIRM WAS
c. | Benefit Assessment District on all downtown
RESPONSIBLE:
properties;
Senior Manager
d. | $60 million settlement with the Union Pacific
| Railroad, which includes a lease on a number of | PROJECT COSTS:
| property parcels transferred from Union Pacific to the | $250 million
City of Reno;
REFERENCE:
e. | TEA-21 pass-through funding from Nevada DOT;
City of Reno
f. | Tax-exempt Municipal Revenue Bonds; and | Andrew Lireen, Finance Director
490 South Center Street, Room 108
g. | A USDOT loan under the TIFIA program.
Reno, Nevada 89501
Three different financing packages will be used to |  | (775) 334-2410
complete the project’s funding plan. The first is a
senior/subordinate financing that includes a senior-lien
tax-exempt revenue bond secured by sales and hotel taxes
and a TIFIA loan from the USDOT secured by a
subordinate lien pledge on the same sales and hotel tax
base. The second financing is a TIFIA loan secured by
the downtown assessments. The third financing, which is
not expected to be offered until 2004, is another
senior/subordinated bond/TIFIA loan package paid from
the lease income on railroad property transfers. Cash and
pay-as-you-go financing make up the balance of the
funding.
Goldman Sachs has modeled cash flows, planned funding
steps, and supported the City staff in communicating
funding plan elements to citizens’ groups and policy
makers, including members of Congress, members of the
Nevada legislature and the staff of the USDOT.
Two separate legislative packages were passed in two
different biennium to allow the project to move forward.
Goldman Sachs was an integral member of the
negotiating team working to gain a $60 million
THI3R4D | HAMPTON ROADS CROSSING |  | 34
CONCEPTUAL PROPOSAL
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . b | Ex pe r i e nc e
Metropolitan Transportation Authority |  | ACTIVITIES FOR WHICH THE FIRM WAS
RESPONSIBLE:
Goldman Sachs was named financial advisor to the New |  | Financial Advisor
York Metropolitan Transportation Authority (MTA) in
August 2000. Under MTA's historic debt restructuring |  | REFERENCE:
program, MTA [and its Triborough Bridge and Tunnel |  | Stephen Kessler, Chief Financial Officer
Authority (TBTA) affiliate] has issued $15 billion of debt |  | 347 Madison Avenue
as of May 2003. In addition, MTA/TBTA expects to |  | New York, NY, 10017
issue over $2 billion of new money bonds under the |  | (212) 878-7278
program in 2003 and 2004. The 2002 issues are
comprised of 18 inter- related and coordinated, yet
separate series of bonds, including insured and uninsured
fixed rate bonds, senior and subordinate bonds, taxable
and tax-exempt bonds, variable rate demand notes,
auction rate securities and commercial paper. MTA also
entered into various interest rate swaps ( including BMA
and LIBOR-based swaps) to pre- hedge portions of its
issuance and hedge a portion of its longer-term variable
rate exposure. MTA also utilized special federal
legislation passed in the wake of September 11 to
advance refund several billion of bonds otherwise not
advance refundable.
Goldman Sachs is involved in the development of new
credits, drafting of resolutions, structuring of debt and the
assurance of a successful marketing program. The
restructuring simplified the MTA's credit structure by
consolidating sixteen old credits into four new primary
credits, modernizing old resolutions, releasing
unnecessary reserves, increasing bonding capacity and,
most importantly, providing approximately $4.5 billion of
funding capacity for the MTA's $17.2 billion 2000-2004
Capital Program without increasing maximum annual
debt service.
THI3R5D | HAMPTON ROADS CROSSING |  | 35
CONCEPTUAL PROPOSAL
TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
| 1 . c | Po i nt o f Co nt a c t
Provide the names, addresses and phone numbers of persons within the firm or consortium who
may be contacted for further information.
The following person may be contacted for further information regarding this conceptual proposal:
` Francis X. (Buddy) Watson, P. E.
Tidewater Skanska, Inc.
809 S. Military Highway
Virginia Beach, VA 23464
(757) 420-4140
Mr. Watson will serve as the SWB Project Director and member of the joint venture executive board.
Please contact Mr. Watson regarding any questions or requests for additional information regarding this
proposal.
THI3R6D HAMPTON ROADS CROSSING |  | 36
CONCEPTUAL PROPOSAL
[5 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . d | Re f e r enc e s
Include the address, telephone number, and the name of a specific contact person for an entity
for | which | the | firm/consortia | or | primary | member | of | the | consortia | have | completed | a | similar
project.
The SWB Team members are proud of the infrastructure that they have designed and constructed. Please
contact any of the references shown the project sheets included in Tab 1.B, Experience, for further
information regarding the outstanding capabilities of the SWB Team members.
THI3R7D HAMPTON ROADS CROSSING | [12 empty] | 37
CONCEPTUAL PROPOSAL
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . e | Fi na nc ia l St a t em e nt s
Provide a financial statement of the firm/consortia and each major partner. |  |  | Submit the most
recent Securities and Exchange Commission 10-K and 10-Q reports, if such reports have been
filed.
 | Appendix E contains the 2003 Annual Report of Skanska AB
 | Appendix F contains the audited financial statement of Skanska USA Civil, Inc.
 | Appendix G contains the audited financial statement of Tidewater Skanska, Inc.
 | Appendix H contains the Form 10-K Annual Report of Washington Group International, Inc.
 | Appendix I contains the Annual Report 2003 of Royal Bam Group nv.
THI3R8D HAMPTON ROADS CROSSING |  |  | 38
CONCEPTUAL PROPOSAL
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[6 empty] | 1. f | Sm a l l , W o m e n a nd M i no r i t y O wne d Bus i ne s s Pa r ti ci pa t i o n
Include | any | planned |  | participation |  | of | small, |  | woman | and | minority | owned |  | businesses |  | during
project development and implementation.
The SWB Team is committed, as a matter of policy, to the spirit and intent of socio-economic programs
that are intended to ensure adequate opportunities for small, women, and minority owned businesses.
SWB | will | provide | written | notification |  |  | to | all | known | small, | women | and | minority-owned |  | (S/W/M)
businesses that specialize in the areas that will be subcontracted and will conduct workshops for these
firms to broaden their level of participation. Drawings and specifications will be made available to all
firms | that | express | an | interest | in | bidding | opportunities. |  |  | SWB | will | negotiate | in | good | faith | with | all
potential subcontractors.
All SWB team members have a history of meeting S/W/M business goals. SWB will advertise in a
variety of media to ensure that S/W/M businesses are notified of business opportunities and plans will be
reviewed to ensure that opportunities exist for participation by a variety of suppliers and subcontractors.
SWB has already identified potential contracting opportunities for this project: demolition; excavation
and grading; steel fabrication and installation; electrical; fencing and guardrail; traffic control; trucking
services; asphalt concrete paving; survey services; and painting. SWB plans to implement the following
actions to encourage S/W/M business participation.
 | Organize pre-proposal conferences to make S/W/M businesses aware of contract opportunities.
 | Develop a S/W/M mailing list to advise S/W/M businesses of bid dates and the location of the
procurement documents.
 | Identify construction packages where subcontracting opportunities exist.
 | Contact firms with whom SWB has successfully worked together in the past to ensure that they are
included on the bidding lists.
 | Contact Commonwealth certified firms using published S/W/M listings.
 | Identify contract/procurement packages that can be used to target S/W/M firms during the design
process. In some cases, these packages can be reduced to a monetary level that will encourage
S/W/M participation.
 | Advertise | in | local | newspapers |  | and | trade |  | magazines | to | encourage |  | S/W/M | awareness |  | and
participation.
 | Provide flexible payment provisions in S/W/M business contracts. Early payment clauses may be
included in certain contracts to alleviate cash flow problems.
SWB’s S/W/M business outreach program will be managed by a small and disadvantaged business
specialist who has developed identical programs in the past. SWB members, in the normal course of
business, have successfully addressed these requirements and have established relationships with S/W/M
businesses.
THI3R9D HAMPTON ROADS CROSSING | [16 empty] | 39
CONCEPTUAL PROPOSAL
[9 empty] | TA B 2 : |  |  | P ROJ E CT CHA RA CT ERI S TI CS
[14 empty] | 2 . a | Pr o j e c t De s c r i pt i o n
Provide a description of the transportation facility or facilities, including the conceptual design
and all proposed interconnections with other transportation facilities. | [13 empty] | Identify communities that
may be affected and the assumptions used in developing the project.
Project Description
The Third Hampton Roads Crossing will connect the Hampton and Newport News areas with Suffolk,
Portsmouth, Chesapeake, Norfolk, and Virginia Beach. The project will reduce current congestion and
meet projected traffic demand, foster economic development, maintain the region’s quality of life, and
include the first Hampton Roads High Occupancy Vehicle (HOV)/Busway crossing which provides
space for the future addition of rail transit service. The Third Hampton Roads Crossing will also more
than double the capacity to evacuate low lying areas in the event of a hurricane.
Various alternatives to achieve this purpose have been evaluated by a Major Investment Study (MIS). A
Locally Preferred Alternative (LPA) has been selected as part of the MIS process and was approved by
the | Commonwealth |  |  | Transportation |  |  |  | Board | (CTB) | in | September |  | 1997. | The | Environmental | Impact
Statement (EIS) was approved in March 2001, and the Record of Decision was issued in June 2001. The
EIS supported the LPA that is defined by the five phases outlined below. SWB is proposing to develop,
design, construct, and finance all five phases.
 | Phase | I | – | Create | a | new | intermodal | connector |  | (I-564) |  | from | Terminal | Boulevard | past | Hampton
Boulevard in Norfolk to a new interchange with I-664 that is located south of Monitor-Merrimac
Memorial Bridge Tunnel. This section would consist of four general-purpose and two multi-modal
lanes constructed as a bridge-tunnel. This section will ultimately connect to a fourth cargo port at
| Craney | Island |  | (Phase |  | III) | and | provide | access | to | the | Norfolk | International |  | Terminals | and | I-564.
Direct access to the facility would also be provided from the Naval Operating Base.
 | Phase II - Widen the I-664, Monitor Merrimac Memorial Bridge Tunnel from Newport News to the
I-664/ I-564 Interchange with the addition of four general purpose and two multi-modal lanes. This
section will be a bridge tunnel that is constructed west of the existing facility.
 | Phase III - Construct a new four-lane road intersecting the extended I-564 and traversing Craney
| Island | to | an | interchange |  | with | the | Western | Freeway |  | (VA-164) |  | in | Portsmouth. | This | roadway | will
provide direct access to Craney Island, the Maersk Sealand terminal in Portsmouth, and also the
| Portsmouth Marine Terminal. Access to the Midtown Tunnel and the | [12 empty] | Downtown Tunnel will be
| provided |  | when | the |  | Pinners | Point | and | Martin | Luther |  | King | Expressway |  | extension | projects | are
completed.
 | Phase IV - Widen I-664 from its current interchange with I-64 in Hampton to the Newport News
end of the Monitor Merrimac Memorial Bridge Tunnel. This section will consist of eight general-
purpose and two multi-modal lanes, adding two lanes in each direction.
 | Phase V - Widen I-664 from its intersection with I-564 to the I-64/I-264 Interchange in Portsmouth.
The improvement would add one lane in each direction, resulting in six general-purpose lanes. This
THI4R0D HAMPTON ROADS CROSSING | [16 empty] | 40
CONCEPTUAL PROPOSAL
[9 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[14 empty] | 2 . a | Pr o j e c t De s c r i pt i o n
phase will complete an improved connection from I-64 to the growing US 58/US 460 corridor and
includes about 3 miles of roadway on a trestle over Hampton Roads.
Figure | 2.1, | EIS | Alignment, |  | shown |  | on | the | following |  | page, | describes | the | general | alignment | that | is
included in the Final Environmental Impact Statement (FEIS). This alignment satisfies all of the needs
that are defined by the MIS.
The | EIS | has | been | the | subject | of | intense |  | review | to | comply | with | all | federal | and | Commonwealth
requirements. Commonwealth, federal, and local government agency efforts are chronologically listed
below:
 | July 1997 – Hampton Roads Metropolitan Planning Organization (MPO) selects the LPA.
 | September 1997 – Commonwealth Transportation Board endorses the LPA.
 | October 1997 – the Final Major Investment Study is completed.
 | October 1999 – the Draft Environmental Impact Statement (DEIS) is completed.
 | Early 2000 – Public Hearings are held.
 | July 2000 – the Commonwealth Transportation Board approves the DEIS.
 | March 2001 – the Final Environmental Impact Statement (FEIS) is completed.
 | June 2001 - Record of Decision is issued.
 | 2001 and early 2002 – Proposals received by VDOT for design and construction under provisions of
PPTA
 | Third Hampton Roads Crossing Commission, established by House Joint Resolution 125/2000, has
reviewed the project on several occasions
 | August 2002 – VDOT returns proposals submitted under PPTA
 | November 2002 – Voter Referendum rejects extra taxes for highway construction
 | August 2003 – Hampton Roads Metropolitan Planning Organization (MPO) includes Phase I as a
toll road in the 2026 Regional Transportation Plan, which was subsequently approved by VDOT and
FHWA.
THI4R1D HAMPTON ROADS CROSSING | [16 empty] | 41
CONCEPTUAL PROPOSAL
TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
| 2 . a | Pr o j e c t De s c r i pt i o n
Figure 2.1 Environmental Impact Statement (EIS Alignment)
THI4R2D HAMPTON ROADS CROSSING |  | 42
CONCEPTUAL PROPOSAL
[7 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[12 empty] | 2 . b | VDO T Pa r t i ci pa t i on
Identify and fully describe any work to be performed by VDOT.
SWB expects that the following work will be performed by VDOT:
` | Development
As a public-private transportation venture participant, VDOT will act as the lead agency, or project
sponsor. This effort will extend to participating in the creation of an IRS 63-20 corporation. VDOT
will also be responsible for the management and administration of the Comprehensive Agreement.
VDOT’s participation will be required for coordination with the Federal Highway Administration
(FHWA) because the crossing involves interstate highways. The involvement will likely include new
connection agreements as the project includes I-564, I-664, I-64, and the I-64/I-264 Interchange.
Coordination with other federal agencies will also be required since permits will be obtained from the
U.S. Army Corps of Engineers, the U.S. Coast Guard, and other federal agencies. Additionally, a
number of other Commonwealth agencies will be involved.
` | Design
VDOT will also be involved in various reviews and approvals during engineering and design. This
includes conducting design reviews to ensure adherence to the adopted design criteria and standards.
VDOT will also approve the crossings geometric design as part of this effort.
It is anticipated that VDOT will provide dedicated engineers during the design phase in the Project
Office. The VDOT staff will be responsible for providing technical guidance and design reviews for
| the | various | construction |  | packages. | VDOT’s | presence |  | will | be | critical | to | maintaining | the | design
schedule since design-build projects are executed on a fast-track basis. The reviewers need to be
| familiar | with | each | construction | package’s |  | development |  | through |  | continuous |  | “over-the-shoulder”
reviews, and develop a comfort level with the incremental development and release of plans. This
coordination is needed on a day-to-day basis rather than the periodic reviews typical of the design-
bid-build approach.
` | Construction and Acceptance
| Finally, | VDOT | will | be | responsible | for | accepting | the | completed |  | transportation |  | facility. | Specific
responsibilities will be defined prior to the execution of the Comprehensive Agreement. The Quality
Assurance and Quality Control Inspection Program will define responsibilities for quality control
and quality assurance including acceptance testing and final acceptance. SWB will coordinate its
efforts with VDOT to define these responsibilities. It is assumed that acceptance testing and final
acceptance will be performed by VDOT.
THI4R3D HAMPTON ROADS CROSSING | [14 empty] | 43
CONCEPTUAL PROPOSAL
[7 empty] | TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
[12 empty] | 2 . c | Pe r m it s
Include a list of all federal, state and local permits and approvals required for the project and a
schedule for obtaining such permits and approvals.
Federal | and | Commonwealth |  | laws | and | regulations |  | require | that | various | environmental |  | permits | or
approvals be acquired prior to the start of construction activities:
 | Compliance with Executive Order 11990, Protection of Wetlands, and Section 404 Permits, Clean
Water Act, from the U.S. Army Corps of Engineers
 | Section 10 Permit, Rivers and Harbors Act, from the U.S. Army Corps of Engineers
 | Virginia | Water | Protection | Permit |  | from | the | Commonwealth |  | of | Virginia, | Department |  | of
Environmental Quality
 | Subaqueous Bed Permit, Virginia Water Law, from the Virginia Marine Resources Commission
 | U.S. Coast Guard Permit
 | Compliance with the Endangered Species Act (ESA)
 | Compliance with Section 106 of the Natural Historic Preservation Act
 | Compliance with Section 4(f) of the 1966 Department of Transportation Act
 | Compliance with Executive Order 12898 on Environmental Justice
 | Storm water management, erosion and sediment control permits from the Virginia Department of
Conservation and Recreation
Permits from local agencies will be identified during preliminary engineering. A local permit matrix will
be | prepared | as | public | agencies | are | contacted | to | determine |  | their | involvement | and | permitting
requirements. SWB will assign a permit specialist to the project during final engineering and design to
coordinate with PB/Jacobs and to manage the permit acquisition process. The permit specialists will be
the contact for all government agencies, ensuring that the proper permits are obtained prior to the start of
construction and that all permit requirements are met.
A permit acquisition schedule will be prepared during preliminary engineering once the required permits
have been identified and their requirements made known. Construction planning that will occur during
this timeframe will include the definition of construction packages and their scheduling requirements.
This scheduling effort will also consider permit requirements. Some permits are time sensitive and have
expiration dates. Their acquisition will be scheduled appropriately to avoid schedule delays.
THI4R4D HAMPTON ROADS CROSSING | [13 empty] | 44
CONCEPTUAL PROPOSAL
[7 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[11 empty] | 2 . d | Env i r o nm e nt a l Impa c t s
Without completing an Environmental Impact Statement, identify any anticipated adverse social,
economic and environmental impacts of the project. | [7 empty] | Specify the strategies or actions to mitigate
known impacts. |  | Identify the projected positive social, economic and environmental impacts of
the project.
A Final Environmental Impact Statement (FEIS) was approved by the Federal Highway Administration
on March 1, 2001 and a Record of Decision (ROD) for the project was issued in June 2001. These
documents have been used to prepare SWB’s conceptual proposal.
The Hampton Roads area is a growing metropolitan region with a diverse population involved in ship
building, shipping, heavy industrial, military, tourism and a broad range of commercial enterprises. The
continuing | sustenance, | quality |  | of | life | and | continued | growth | of | the | region’s |  | financial |  | base | will | be
severely hindered by limited access across major navigable waterways that dominate the area.
Hampton Roads is crossed by the Hampton Roads Bridge Tunnel and the Monitor Merrimac Memorial
Bridge Tunnel. Each of these facilities provides two mixed flow lanes in each direction and serves
different | activity | centers. | These | facilities |  |  | provide | limited | alternate |  | use | selection |  | during |  | the | ever-
increasing peak congestion periods and also provide extremely limited public transit. The MIS and the
EIS process provided startling data, portraying a region in perpetual gridlock with stifled economic and
population growth before 2015 without expanding the Hampton Roads crossings.
This lack of traffic handling capacity has been recognized and extensively documented. Various studies
have concluded that a Third Hampton Roads Crossing that provides added capacity for vehicles and
bus/rail transit access from Newport News across the Craney Island portion of Portsmouth to Norfolk is
the best solution. This crossing concept with the widening of I-664 and I-564, and a direct connection to
the Western Freeway, VA-164, has been adopted as the Locally Preferred Alternative (LPA) by the
Hampton | Roads | Metropolitan |  | Planning |  | Organization |  | (MPO). | The | LPA |  | has | been | approved |  | by | the
Commonwealth Transportation Board, and was endorsed by the Governor of Virginia in July 2000. The
EIS alignment has been selected as the LPA.
The EIS addresses environmental impacts and suggests appropriate mitigation measures and strategies.
To summarize, mitigation can be accomplished by refining the alignment during engineering and design,
including | provision | for | sound | attenuation |  |  | features | where | appropriate, |  | and | phasing |  | construction |  |  | to
minimize | wildlife | impacts. | Vehicle |  | emissions |  | will | actually | decrease |  | after | the | opening |  | of | the | Third
Hampton | Roads | Crossing | project |  | as | compared | with | the | no-build |  | option. |  | SWB | is | committed |  | to
environmental | quality, | as | evidenced |  |  | by | Skanska’s | ISO14001 | certification. |  |  |  | SWB | will | incorporate
appropriate features in the facility’s design that address the requirements that are defined by the EIS and
the environmental permits. SWB will also phase construction to avoid disturbing wildlife during critical
seasons.
The impact to residences and businesses is relatively minor. The project will involve the relocation of 38
residences and 11 businesses as the alignment is primarily over water or in existing right-of-way. This
alignment requires very minor noise mitigation measures, which will be incorporated during design and
construction.
THI4R5D HAMPTON ROADS CROSSING | [16 empty] | 45
CONCEPTUAL PROPOSAL
[8 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[13 empty] | 2 . d | Env i r o nm e nt a l Impa c t s
The project will significantly improve the quality of life for the region’s inhabitants with no adverse
environmental |  | impacts. |  | Quality | of | life | also | means | that | there | will | be | an | equitable | distribution |  | of
employment opportunities and contracts among the region’s diverse cultures. SWB will use locally hired
employees and regional subcontractors to the maximum extent possible and is committed to an equitable
distribution of contracting opportunities.
The | Third | Hampton |  | Roads | Crossing | provides |  | the | region | with | the | capability |  | to | grow | and | prosper
economically in the domestic and worldwide markets. The direct connection of Newport News, Norfolk,
and Portsmouth will substantially improve shipping links between the three major port complexes. The
connector link, between the extended I-564 and VA-164, Western Freeway, will provide the capability to
develop a significant fourth port at Craney Island with truck access to the other three Hampton Roads ports
and rail facilities.
The tourism industry will continue to thrive and be a major economic factor in the region with the
completion of a third crossing. Less congestion, alternate route selection and bus/rail transit capacity
will attract more visitors and tourists who will be better able to enjoy the regions’ many attractions.
The | EIS | considers | these | long-term |  | social | and | economic |  | enhancements. |  |  | On | a | short-term | basis | the
negative impacts that are normally associated with construction will be comparatively minor because
almost the entire footprint of the project is in previously purchased right-of-way and unencumbered
maritime |  | areas. | The | short-term |  | negative | impacts |  | will | be | offset | by | the | creation | of | employment
opportunities, |  | the | magnitude |  | of | business | growth/development |  |  |  | that |  | will | occur, | and | the | positive
environmental impacts such as cleaner air.
This project is definitely in the best interests of the region’s population. Citizens and businesses await
the completion of this critically needed transportation facility. An effective public information program,
including extensive outreach efforts, will be provided by SWB to continue fostering public support. The
public information program will respond to environmentally related public concerns. SWB will make
every effort to inform the public of protective measures that are being taken to protect the Hampton
Roads area.
THI4R6D HAMPTON ROADS CROSSING | [16 empty] | 46
CONCEPTUAL PROPOSAL
[10 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[15 empty] | 2 . e | Cr i t ic a l Suc c e s s Fa c t o r s
List the critical factors for the project’s success.
The | success |  | of | the | Hampton |  |  | Roads | Third | Crossing | is | contingent |  | upon |  | several | important |  | factors
including the composition of the Project Team, a viable financing plan, public support, and institutional
support. These factors are discussed as follows.
` | The SWB Team - SWB was formed specifically to undertake this project. The member companies
and | designated |  | designers |  |  | have |  | more | contemporary waterfront and highway design | [7 empty] | and | construction
experience in the Hampton Roads area than any other imaginable team. The SWB members know the
area well, and are acutely aware of the social and economic issues and benefits that are associated with a
third crossing. SWB has started the process of assembling an experienced and dedicated staff of long-
term employees to undertake the development of the Third Hampton Roads Crossing. SWB will execute
the project at the lowest possible cost and with minimal social, environmental, and economic impact.
The skills of the SWB Team, immense assets and capabilities of the parent firms and the commitment of
these firms to dedicate their best resources to the SWB Team will ensure success.
The Third Hampton Roads Crossing success requires that high quality be built in from the start. The
SWB | Team |  | has | a | proud | history |  | of | executing | well-controlled |  |  | and | complex |  | projects | that | have | been
constructed to exacting standards, while meeting cost and schedule goals. Minimizing time requirements
and constructing a high-quality project safely will encourage public support, reduce inconvenience to the
traveling public, while also reducing construction costs.
Local and regional workers and subcontractors will be employed to the maximum extent possible. They
will be fully integrated into the SWB Team and contribute to the project’s success.
The SWB Team will also establish and maintain mutually beneficial relations with VDOT, a proposed
IRS 63-20 organization or a public agency, the regional governing bodies, regional organizations, and a
myriad of civic, social, economic, professional, business and special interest groups. SWB is committed
to partnering with all stakeholders for mutual success.
` | Project | Financing |  |  | - | VDOT |  | has | estimated | the | Third | Hampton |  | Roads | Crossing |  | would | cost | $4.4
billion if it were designed and constructed between 2001 and 2014. The SWB estimated cost of the
Third Hampton Roads Crossing and the planned method of financing are discussed in Tab 3. Under
SWB’s plan, the cost of the crossing can be reduced substantially and the duration shortened. The
traveling public will be able to use the completed facility earlier than planned, and the taxpayer will not
have to bear the burden of a much more expensive facility.
` | Project | Financing |  |  | - | Testimony |  |  | provided | during | the | public | comment |  |  | and | community | outreach
programs |  | of | the | MIS |  | and | EIS | and | input | from | government |  | officials, |  | private |  | sector | groups, | and
individuals indicate overwhelming support for the project. Many people recognize that it is needed now,
and it is widely recognized that it is needed several years before VDOT’s estimated completion date if
the region is to experience a reasonable quality of life.
The | public | is | justified |  |  | in | its | concern | regarding | how | to | pay | for | this | urgently |  | needed, | but | fiscally
constrained project. A study published by the Hampton Roads Partnership in 2000 indicates that a
majority of residents are willing to finance transportation improvements through the imposition of tolls,
THI4R7D HAMPTON ROADS CROSSING | [18 empty] | 47
CONCEPTUAL PROPOSAL
[8 empty] | TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
[11 empty] | 2 . e | Cr i t ic a l Suc c e s s Fa c t o r s
a dedicated sales tax increment, a dedicated gas tax increment, or a combination of these financing
alternatives. The November 2002 referendum provided mixed results on similar questions but there
remains strong support for a viable Third Hampton Roads Crossing. Gaining additional public support
for financing the project during the next six years is critical, otherwise the project’s cost could nearly
double without any tangible benefit to the public. TAB 3 discusses SWB’s proposed financial plan.
` Forming | Coalitions |  | - | VDOT | and | the | SWB | Team | must | form | stakeholder | coalitions | during |  | the
development | process | to | develop |  | mutually |  | beneficial | solutions |  | and | foster | communication. | The | major
participants will include the FHWA, the U.S. Army Corps of Engineers, the U.S. Navy, the Hampton
Roads | Metropolitan | Planning | VDOT: Organization,; SWB: local; Team: jurisdictions,; form: and | other | local | agencies | and | port
authorities, as well as business interests and the public at large. Defining mutual interests and developing
plans to address those interests will be of paramount importance. SWB has dealt effectively with all of the
involved parties in the past. Relationships already exist that will allow SWB to quickly move forward.
THI4R8D HAMPTON ROADS CROSSING | [14 empty] | 48
CONCEPTUAL PROPOSAL
[7 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[14 empty] | 2 . f | Sc he dul e
Identify the proposed schedule for operator’s work on the project, including the estimated time
for completion.
VDOT’s fiscally constrained schedule in 2001 reflected a 14-year construction period, resulting in a
2014 completion date. This schedule is dependent upon the availability of direct funding from already
strained Commonwealth and federal sources. It is clear that limited funding is available at this time and
the | project’s | multi-phase |  |  | development | would | depend | on | incremental |  | funding | over | several |  | decades,
assuming that it was available.
SWB has developed financing and construction plans for the Third Hampton Roads Crossing that are
presented in TAB 3. Recognizing that time is of the essence, this proposal is based upon executing a
Comprehensive Agreement with VDOT and receiving a notice-to-proceed by 2007. The intervening
months will be used to further define the project sufficiently to allow the preparation of a fixed price
estimate. Given that a notice-to-proceed shortly after the Comprehensive Agreement is executed, final
engineering and design could proceed shortly thereafter. This accelerated schedule will allow the facility
to be completed in significantly less time than planned, resulting in several important benefits:
 | Greatly reduced construction costs
 | Improved quality of life
 | Greatly reduced interest costs
 | Added capacity years earlier
 | Economic benefits are realized years earlier
Once final engineering and design begins three levels of schedules will be used to plan, monitor and
control the design program: Level 1 (Master Schedule); Level 2 (Critical Path Method Schedule); and
Level | 3 | (Control | Level | Schedules). |  | This | schedule | system | will | be | fully | integrated | and |  | define | the
objectives of the plan of execution for each level of the organization.
The | Master | Schedule |  | will | define | major | milestones | for | each | construction |  | package. | A | project-level
schedule will further define the major activities that are associated with each milestone that is shown on
the | Master | Schedule. |  | This | Precedence |  | Diagram | Method | Schedule |  | will | be | used | to | define | the
interrelationship |  |  | of | planning, | design, | procurement, |  | and | construction |  | activities, |  | including |  | activities
performed |  | by | others | and | permitting | activities. | Control-level |  |  | schedules | will | be | developed |  | for | each
construction package to define all activities to use as the basis of status and progress reporting.
THI4R9D HAMPTON ROADS CROSSING | [15 empty] | 49
CONCEPTUAL PROPOSAL
|  |  | must: TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
[11 empty] | 2 . g | Ti m e l y Co m pl e t i o n o f t he Pr o je c t
Propose | allocation |  | of | risk | and | liability |  | for | past | agreement |  | work | and | assurances | for | timely
completion of the project.
Skanska/Washington/BAM (SWB), PB, and Jacobs will bear all design and construction liability in
accordance with existing professional standards and statutory requirements. The project will meet or
exceed all applicable laws and regulations.
The | SWB | Team has | VDOT: extensive; the: experience; Team: in executing the type of project envisioned as the Third
Hampton |  | Roads | Crossing |  | and | have | undertaken |  | numerous |  | projects |  | together. | Based | on | the | Team
experience |  | in | design | and | construction |  | in | the | Hampton |  | Roads | area | with | projects | that | bear | many
similarities to all phases of the Third Crossing Project, SWB is confident the project can be completed
by 2013. SWB expects to provide a firm price during finalization of a Comprehensive Agreement by
December 2006.
SWB recognizes that environmental considerations will limit timeframes for dredging operations and
that | weather |  | factors | are | always | more | pronounced |  |  | for | maritime | construction. |  | SWB’s |  | collective
experience in the Hampton Roads area demonstrates the Team’s proven capability to control schedules
and produce quality facilities in this environment. Based on a proven record, SWB is willing to accept
liquidated damages as part of the finalization of the Comprehensive Agreement.
THI5R0D HAMPTON ROADS CROSSING | [16 empty] | 50
CONCEPTUAL PROPOSAL
[8 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
|  | 2 . h | -: As s um pt i o ns Re l at e d t o O wne r s hi p, Li abi l i t y and Ope r a t i o na l Re s po ns i bi li t y
Clearly state the assumptions related to ownership, legal liability, law enforcement and operation
of the facility.
As | currently | envisioned |  | VDOT | will | have | ownership |  | and | police | responsibility |  | upon | completion |  | of
construction |  | except | for | certain | specialty |  | items. | Law | enforcement |  | and | legal | liability | will | be | the
responsibility of appropriate governmental agencies.
SWB will be responsible for operations and maintenance of the new facilities.
THI5R1D HAMPTON ROADS CROSSING | [15 empty] | 51
CONCEPTUAL PROPOSAL
[6 empty] | TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
|  |  | form: 2 . i | Pr o j e ct Pa r t i a l O peni ng s
Provide | information | relative | to | phased | or | partial | openings | of | the | proposed | project | prior | to
completion of the entire works.
Openings are scheduled to coincide with the completion of operable segments. | [10 empty] | Interfacing of operable
segments is addressed in Tab 3.
THI5R2D HAMPTON ROADS CROSSING | [12 empty] | 52
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  |  | form: TA B 3 : | P ROJ E CT FI NA NCI NG
[12 empty] | 3 . a | Pr o j e c t Co s t Es t i ma t e
INTRODUCTION
This section presents the schedule, estimates and financing plans for the alignment approved in the
Record of Decision (ROD). There are numerous alternatives based on selected phasing, selected scope,
toll levels and availability of funds in addition to toll revenue. Financially appealing alternatives to the
ROD-approved |  |  | alignment |  | are | available | to | explore | through | later | phases | of | the | PPTA | process. | The
following assumptions were used to prepare Skanska/Washington/BAM’s (SWB) proposal:
 | Primary funding will be provided through tax-exempt toll revenue bonds. Secondary funding will be
obtained by VDOT from other sources.
 | Tolls will be placed on the Hampton Roads Bridge Tunnel and the Monitor Merrimac Memorial
Bridge Tunnel in July 2008, 18 months after Notice to Proceed.
 | The | project | will | be | accomplished |  | on | a | develop-finance-design-build-operate |  |  |  |  | and | maintain | basis
rather than the traditional design-bid-build basis.
 | A Comprehensive Agreement, as described in the Public Private Transportation Act of 1995, will be
executed during December 2006, followed by a Notice to Proceed in January 2007.
 | VDOT estimated right-of-way costs of $70 million are reasonable and include right-of-way owned
by governmental agencies. VDOT will execute its right of eminent domain if necessary
 | All costs for toll collection are included in the SWB proposal. The primary means of toll collection
will be via electronic scanning such as EZ-Pass or Smart Tag.
 | SWB will be responsible for operations and maintenance of the new facilities.
 | Craney Island will be available as a dredge disposal site.
 | Bond interest rates and other financial terms are based on the April 30, 2004 market conditions for
35-year term, tax-exempt toll revenue bonds.
The | estimate | and | schedule |  | for | the | SWB | concept | proposal | compared | to | the | current |  | (2001) | VDOT
proposal is as follows:
[7 empty] | VDOT Plan (2001) |  |  | SWB Plan (2004)
|  | Estimated Cost ($M) | Team: $4,400M* | $3,671M
|  | Completion Date | Team: 2014* | 2013
*Note: Excludes Intermodal Connector from Hampton Boulevard to I-564 and is based on
|  |  | a project start in 2001. |  |  |  | If costs were escalated to 2004, the SWB proposal would
save greater than $1B
THI5R3D HAMPTON ROADS CROSSING | [15 empty] | 53
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  |  | form: TA B 3 : | P ROJ E CT FI NA NCI NG
[12 empty] | 3 . a | Pr o j e c t Co s t Es t i ma t e
Provide a preliminary estimate and estimating methodology of the cost of the work by phase
and/or segment (e.g. planning, design, construction).
This | section |  | addresses | the | cost | estimates | for | the | financing, | design | and | construction |  | of | the | Third
Hampton Roads Crossing. Estimated costs are also provided to finance, design and build the project by
phases. The breakdown of total project cost, by percentage is:
| Planning |  | and: 1.5%
| Design |  | and: 5.0%
| Construction |  | VDOT: 93.5% (Including Construction Engineering & Inspection)
The alignment of the Third Hampton Roads Crossing is illustrated in Figure 3-1. This alignment and the
five phases were approved in the June 2001 Record of Decision culmination of the Environmental
Impact Study. This alignment has also been approved by the Commonwealth Transportation Board and
the Metropolitan Planning Organization (MPO). In August 2003, the MPO added the four non-restricted
access lanes of the intermodal connector from Hampton Boulevard in Norfolk to the intersection of I-
564 to Phase I. This intermodal connector is included in the SWB proposal.
Based | on | a | January | 2007 | Notice | to | Proceed, | SWB | can | complete | the | entire | project | in | 2013 | at | an
estimated cost of $3,671M. The same scope and phasing, exclusive of the intermodal connector, was
presented to the Third Hampton Roads Crossing Commission by VDOT on January 15, 2001 with an
estimated cost of $4,400M and a projected completion date of 2014, assuming a project start in early
2001.
The project can be built in phases to provide operational segments as needed to meet the growing traffic
demand. If VDOT elects to construct the project in phases, SWB recommends that Phase II be built
concurrently with the redefined (August 2003) Phase I to minimize costs, to meet the growing traffic
demands on the Monitor Merrimac Memorial Bridge Tunnel, and to avoid significant extra costs for
temporary facilities that are needed to make Phase I feasible as a stand-alone facility. The costs by
phases are illustrated in Table 3.1.
Table 3.1 |  | Estimated Cost by Phase
| PHASES |  | the: SWB Plan
Phases I and II |  |  | SWB: $2,499M
Phase III |  |  | SWB: $551M
Phase IV |  |  | SWB: $305M
Phase V |  |  | SWB: $316M
Total |  |  | SWB: $3,671M
Completion Date |  |  | SWB: July 2013
THI5R4D HAMPTON ROADS CROSSING | [16 empty] | 54
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  |  | form: TA B 3 : |  | P ROJ E CT FI NA NCI NG
[12 empty] | 3 . a | Pr o j e c t Co s t Es t i ma t e
Phases I and II represent the backbone of the Third Hampton Roads Crossing and provide the basic
functionality of the project. Phases III, IV, and V are independent of each other but depend on Phases I
and II to achieve the required capacity. The start of these three phases could be scheduled as shown in
Figure | 3.2 | to | achieve | completion | of | all | five | phases | by | 2013. | Phases | III, | IV, | and | V | could | also | be
scheduled independently to meet ridership demands or the availability of funds.
THI5R5D HAMPTON ROADS CROSSING | [17 empty] | 55
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | TA B 3 : | -: P ROJ E CT FI NA NCI NG
|  |  | 3 . a | Pr o j e c t Co s t Es t i ma t e
Figure 3.1 | Project Alignment
THI5R6D HAMPTON ROADS CROSSING |  |  | VDOT: 56
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  |  | Team: TA B 3 :; form: P ROJ E CT FI NA NCI NG
[11 empty] | 3 . b | Fi na nc i ng Pl a n
Submit | a | plan | for | the | development, | financing | and | operation | of | the | project, | showing: | the
anticipated schedule on which funds will be required; and proposed sources and uses for such
funds.
Figure 3.2, Project Schedule, illustrates the timeframe for major activities associated with the
development, design and construction of the Third Hampton Roads Crossing. A further breakdown of
key elements germane to project financing is outlined below:
Period |  | Activity
7/04–11/04 |  |  | -: VDOT issues public notice that an unsolicited proposal has been received.
12/04–01/05 |  |  | -: Initial Review Committee review and recommendation
2/05 |  |  | -: Commonwealth Transportation Board decision.
2/05-3/05 |  |  | -: Resolve requirements for the detailed Technical Proposal phase and execute an initial
agreement.
3/05-3/06 |  |  | -: SWB develops concept engineering and studies.
4/06 |  |  | -: Detailed Technical Proposal and preliminary engineering submitted for Advisory Panel
review.
|  |  | -: Detailed Technical Proposal submitted to local governments for their 60 day review period.
|  |  | -: VDOT, with SWB assistance, submits analysis to FHWA for tolling existing interstate
highways.
8/06 |  |  | -: Negotiations complete and approved. Initiate efforts for bond offering.
12/06 |  |  | -: Comprehensive Agreement executed.
1/07 |  |  | -: Notice-to-proceed issued.
2/07 |  |  | -: Funding in place.
6/07 |  |  | -: Complete toll facility design and begin construction.
|  |  | -: Design for islands complete and permits for Island construction issued.
1/08 |  |  | -: Island construction starts.
7/08 |  |  | -: Begin toll collection.
12/09 |  |  | -: Initiate second bond offering.
12/10 |  |  | -: Complete project design.
7/13 |  |  | -: Complete facility open to public.
While Phases I and II must start at the earliest possible date, the remaining phases can be scheduled with
Phases I and II to maximize construction efficiency. Table 3.2, Schedule of Funds Required for Each
Alternative, illustrates the funding required for each year for the complete scope of the project if all
phases are to be completed by 2013. Table 3.2 also provides the funding required for each year if VDOT
elects to authorize completion of only Phases I and II.
THI5R7D HAMPTON ROADS CROSSING | [12 empty] | 57
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  |  | the: TA B 3 :; SWB: P ROJ E CT FI NA NCI NG
[7 empty] | 3 . c | Fi na nc ia l As s um pt io ns
Figure 3.2 | Project Schedule
Description |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013
Third Crossing
Preliminary Engineering
Notice to Proceed
Phase I + II
Engineering
Mobilization
Graving Dock
Tunnel Islands
Elizabeth River Tunnel
MM Tunnel
Roadwork and Bridges
Trestles
Phase III
Engineering
Roadwork and Bridges
Phase IV
Engineering
Roadwork and Bridges
Phase V
Engineering
Roadwork and Bridges
Project Completion
THI5R8D HAMPTON ROADS CROSSING |  | 2013: 58
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | 2005: TA B 3 :; 2006: P ROJ E CT FI NA NCI NG
|  |  | 3 . c | Fi na nc ia l As s um pt io ns
Table 3.2 | Schedule of Funds Required for Each Alternative
|  | COMPLETE PROJECT | PHASES I AND II ONLY
YEAR
|  | $ in Millions | $ in Millions
| 2007 | 2005: 179; 2006: 179
| 2008 | 2005: 465; 2006: 457
| 2009 | 2005: 550; 2006: 501
| 2010 | 2005: 733; 2006: 546
| 2011 | 2005: 763; 2006: 400
| 2012 | 2005: 645; 2006: 300
| 2013 | 2005: 336; 2006: 116
| Total | 2005: $3,671; 2006: $2,499
The proposed funding source for this project is through a combination of toll collection and VDOT
obtaining external funding. The financial model utilizes non-recourse toll revenue bonds issued by a
non-profit organization (IRS 63-20 or public agency). Bond offerings will be in 2006 and 2010.
Toll Revenue will be provided from toll collection facilities at the Hampton Roads Bridge Tunnel and
the Monitor Merrimac Memorial Bridge Tunnel starting in July 2008.
Sources and uses of funds for the SWB alternatives outlined above are included in TAB 3f.
THI5R9D HAMPTON ROADS CROSSING |  | 2007: 59
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | 2013: TA B 3 : |  | P ROJ E CT FI NA NCI NG
[13 empty] | 3 . c | Fi na nc ia l As s um pt io ns
Include a list and discussion of assumptions (user fees or toll rates, and usage of the facility)
underlying all major elements of the plan.
The EIS provides traffic projections for the Hampton Roads Bridge Tunnel and the Monitor Merrimac
Memorial |  | Bridge | Tunnel. |  | These |  | figures | suggest | that the | aggregate |  | traffic | for these facilities would
increase at 2.9 percent per year after the 1994 base year. VDOT’s traffic volume measurements through
2003 confirm that the growth is in line with these projections. For the purposes of the financial analysis
SWB has assumed:
| 1. | 2005: A conservative traffic growth rate of approximately 2 percent per year after 2002.
| 2. | 2005: Execution of the Comprehensive agreement during December 2006.
| 3. | 2005: Instituting tolls on Hampton Roads Bridge-Tunnel and the Monitor Merrimac Memorial Bridge
Tunnel in July 2008.
| 4. | 2005: An average toll for each vehicle, regardless of the type of vehicle or hour of the day. A more
diversified toll structure will be developed during preparation of the detailed technical proposal.
| 5. | 2005: All costs associated with the toll collection function will be paid out of the toll revenues. Toll
collection would be done primarily by electronic means such as EZ-Pass or Smart Tag.
| 6. | 2005: All right-of-way can be obtained within the VDOT estimate of $70 million.
| 7. | 2005: An escalation rate for construction costs of 3.5 percent per year.
| 8. | 2005: VDOT will be able to obtain the required authority to place tolls on the Monitor Merrimac
Memorial Bridge Tunnel and the Hampton Roads Bridge Tunnel.
| 9. | 2005: A conservative financing package based on April 30, 2004 market conditions.
| 10. | 2005: Imposing tolls reduces projected traffic by 3 percent per $0.50 toll increment.
| 11. | 2005: VDOT will obtain funds from other sources in accordance with the timeframe of the selected
alternative.
| 12. | 2005: The average toll increases $0.50 every five years after completion in 2013 to compensate for
inflation.
| 13. | The | above | toll | rates | are | averages | between | cars | and | trucks | and | the | selected | method | of | toll
payment (cash or electronic).
Based on the assumptions above, SWB has determined that:
| Case 1. | 2006: Phases I and II can be financed without funds from other sources if the starting toll in
2008 is set at $2.00/trip and the toll is increased to $5.75/trip upon project completion in
2013.
| Case 2. | 2006: The complete project (Phases I through IV) will require $900 million in funds from other
sources, even with a starting toll of $2.00/trip in 2008 and an increased toll of $8.50/trip
in 2013.
The toll rate may be reduced or the debt retired earlier if:
 | External funding is increased.
 | Interest rate is lower.
 | Actual traffic is greater than expected.
 | Certain loan guarantees are obtained.
THI6R0D HAMPTON ROADS CROSSING | [16 empty] | 60
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | 2005: TA B 3 :; 2006: P ROJ E CT FI NA NCI NG
|  |  | 3 . c | Fi na nc ia l As s um pt io ns
Some of these funding options could be explored further during the preparation of the detailed technical
proposal. For illustration purposes, the following examples show two of a virtually infinite number of
potential alternatives with external funds, the impact of varying the initial tolls (July 2008), and the
amount of external funds:
Alternate A. | If Phases I through V were built:
|  | 2005: Initial (2008) toll is $2.00/Trip
|  | 2005: Toll upon completion in 2013 is $3.00/Trip
|  | 2005: External funds required are $1,850M
Alternate B. | If Phases I and II were built:
|  | 2005: Initial (2008) toll is $2.00/Trip
|  | 2005: Toll upon completion in 2013 is $3.00/Trip
|  | 2005: External funds required are $600M
Note: | Funding generated by required debt/service ratio could be used as a fund source for remaining
phases.
THI6R1D HAMPTON ROADS CROSSING |  | 2007: 61
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | 2013: TA B 3 : |  | P ROJ E CT FI NA NCI NG
[14 empty] | 3 . d | Ri s k Fac t o r s
Identify the proposed risk factors and methods for dealing with these factors.
SWB | is | confident |  | that | the | Third | Hampton | Roads | Crossing | can | be | built | by | 2013 | based | on |  | the
assumptions |  | in | this | submittal. |  | This | conceptual | proposal |  | demonstrates |  | that | the | project | is | financially
feasible and satisfies a demonstrated need. SWB is prepared to begin negotiations with VDOT to arrive
at a mutually acceptable price and schedule that will result in the SWB assuming risk commensurate
with anticipated returns. Four major areas of risk have been identified as outlined below.
` Availability of Funds – The presentation of financial alternatives depends on the acceptability of
tolls to a certain level and the availability of other funding to finance the remainder of the costs. The
MPO and various public opinion polls indicate that tolls will be acceptable to a certain extent, but the
Third Crossing will require a significant amount of funds from other sources even if the maximum
public acceptability of tolls is $3.00 per crossing in 2013. VDOT’s ability to obtain the required funds
from other sources is essential to the success of the proposed project.
VDOT | and | the | Hampton |  | Roads |  | Planning | District | Commission |  | are | currently | contracting |  |  | for | a | Toll
Feasibility Study. The results of this study will be incorporated in the detailed Technical Proposal.
The | proposal | also |  | assumes |  | that | The | Hampton | Roads | Bridge | Tunnel | and | the | Monitor |  | Merrimac
Memorial Bridge Tunnel will be tolled. VDOT needs to obtain the required approvals to institute toll
collection on these existing Interstate Highways for the purpose of reducing congestion at these facilities
by using an improved traffic management system and constructing the Third Crossing. The capability of
VDOT to obtain the requisite authority in the time frames indicated is critical to the success of the
undertaking.
` | Rising Construction Costs - Starting the project as quickly as possible is integral to the success of
the financial plan. Inflation will increase project costs by over $100 million per year. Time is of the
essence. SWB is ready to move quickly. The SWB proposal includes escalation commensurate with the
proposed schedule and assumes a Comprehensive Agreement is in place by December 2006.
` Actual Traffic - A major concern for any project using private financing is that the projected traffic
will not materialize. For the Third Crossing the risk is minimized because traffic history is known and
the tolling plan minimizes diversion alternatives. SWB has made a conservative traffic projection based
upon long-term historic data for all the existing crossings and industry accepted traffic suppression rates.
All Hampton Roads crossings are to be tolled. SWB is confident that the projected toll revenues will
support the assumption of debt through sale of non-recourse toll revenue bonds.
` Obtaining Permits - The Third Hampton Roads Crossing Project requires numerous permits from
various agencies, which can be a long process. SWB anticipates that permits will be approved in a
timely manner by working with appropriate agencies during the detailed technical proposal and design
phases. The EIS addresses this risk factor in detail and concludes that environmental factors can be
mitigated by appropriate design and construction considerations.
SWB anticipates the risk of not obtaining permits in a timely manner is low based upon the Approved
Environmental Impact Statement.
THI6R2D HAMPTON ROADS CROSSING | [17 empty] | 62
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | 2010: TA B 3 :; 2011: P ROJ E CT FI NA NCI NG
[9 empty] | 3 . e | Addi t i ona l Re s o ur c e s
Identify any local, state and federal resources that the proposer contemplates requesting for the
project. | Describe the total commitment (financial, services, property, etc.), if any, expected from
governmental sources; and the timing of any anticipated financial commitment.
In order to finance the Third Hampton Roads Crossing project with non-recourse toll revenue bond, the
Hampton Roads Bridge Tunnel and the Monitor Merrimac Memorial Bridge Tunnel will have to be
tolled and clearly recognized as part of the same vital transportation system as the Third Hampton Roads
Crossing. | VDOT | 2005: must; 2006: obtain; 2007: approval to toll these facilities. Various combinations of tolls on the
Hampton | Roads | Bridge | Tunnel | and | Monitor | Merrimac | Memorial | Bridge | Tunnel | and | other | funding
would establish a base for construction of the Third Hampton Roads Crossing.
Certain right of way will be required for the project. It is assumed that all costs associated with this land
are included in the $70M VDOT right-of-way costs. This $70M VDOT estimate has been incorporated
into the SWB project budget. SWB may need assistance from VDOT in obtaining this land through the
eminent domain process.
The SWB analysis is based on using non-recourse toll revenue bonds as the primary use of funds. This
analysis indicates that the necessary toll levels to support construction would probably not be acceptable to
the general public. A combination of an acceptable level of tolls and other funding is required. VDOT will
have to obtain any funds necessary to supplement the toll revenue financing from other sources.
THI6R3D HAMPTON ROADS CROSSING | [11 empty] | 63
CONCEPTUAL PROPOSAL
CONFIDENTIAL |  | 2008: TA B 3 :; 2009: P ROJ E CT FI NA NCI NG
[6 empty] | 3 . f | So ur c e s a nd Us e s o f Funds
Case 1 | Phase I & II Only | 2007: Case 2; 2008: Phase I Through V
| Toll Rate: | 2006: $2.00 (2008); 2008: Toll Rate:; 2010: $2.00 (2008)
|  |  | $5.75 (2013) |  |  |  | $8.50 (2013)
Sources: |  | 2007: Sources:
Bond Proceeds |  | 2007: Bond Proceeds
Par Amount |  | 2006: 2,918,793,864; 2007: Par Amount; 2010: 3,205,828,744
Uses: |  | 2007: Uses:
Project Fund Deposits |  | 2007: Project Fund Deposits
Phases I & II Construction Draws (Net) |  | 2010: 2,326,231,129; 2006: 2,326,231,129; 2007: Phases I & II Construction Draws (Net)
|  |  |  | Phases III - V Construction Draws (Net) |  |  | 1,146,192,490
Other Fund Deposits |  | 2007: Other Fund Deposits
Debt Service Reserve Fund |  | 2006: 291,879,386; 2007: Debt Service Reserve Fund; 2010: 320,582,874
Capitalized Interest |  | 2006: 64,708,680; 2007: Capitalized Interest; 2010: 65,413,042
Delivery Date Expenses |  | 2007: Delivery Date Expenses
Cost of Issuance |  | 2006: 43,781,908; 2007: Cost of Issuance; 2010: 48,087,431
Bond Insurance |  | 2006: 174,937,456; 2007: Bond Insurance; 2010: 190,311,121
Other Uses of Funds |  | 2007: Other Uses of Funds
Additional Funding for Phases I & II |  | 2010: -890,989,343; 2006: 17,255,305; 2007: Funding Shortfall for Phases III - V
Total |  | 2006: 2,918,793,864; 2007: Total; 2010: 3,205,828,744
Total Additional/(Shortfall of Funds) |  | 2010: -890,989,343; 2006: 17,255,305; 2007: Total Additional/(Shortfall) of Funds
Alternate A | Phase I Through V | 2007: Alternate B; 2008: Phase I & II Only
| Toll Rate: | 2006: $2.00 (2008); 2008: Toll Rate:; 2010: $2.00 (2008)
|  |  | $3.00 (2013) |  |  |  | $3.00 (2013)
Sources: |  | 2007: Sources:
Bond Proceeds |  | 2007: Bond Proceeds
Par Amount |  | 2006: 2,169,957,459; 2007: Par Amount; 2010: 2,169,957,459
Uses: |  | 2007: Uses:
Project Fund Deposits |  | 2007: Project Fund Deposits
Phases I & II Construction Draws |  | 2010: 2,326,231,129; 2005: (Net); 2006: 2,326,231,129; 2007: Phases 1 & II Construction Draws (Net)
Phases III - V Construction Draws (Gross) |  | 2006: 1,242,450,000
Other Fund Deposits |  | 2007: Other Fund Deposits
Debt Service Reserve Fund |  | 2006: 216,995,746; 2007: Debt Service Reserve Fund; 2010: 216,995,746
Capitalized Interest |  | 2006: 62,871,148; 2007: Capitalized Interest; 2010: 62,871,148
Delivery Date Expenses |  | 2007: Delivery Date Expenses
Cost of Issuance |  | 2006: 32,549,362; 2007: Cost of Issuance; 2010: 32,549,362
Bond Insurance |  | 2006: 131,219,941; 2007: Bond Insurance; 2010: 131,219,941
Other Uses of Funds |  | 2007: Other Uses of Funds
Funding Shortfall for Phases I & II |  | 2010: -599,909,867; 2006: -599,909,867; 2007: Funding Shortfall for Phases I & II
Funding Shortfall for Phases III - V |  | 2006: -1,242,450,000
Total |  | 2006: 2,169,957,459; 2007: Total; 2010: 2,169,957,459
Total Additional/(Shortfall of Funds) |  | 2010: -599,909,867; 2006: -1,842,359,867; 2007: Total Additional/(Shortfall) of Funds
THI6R4D HAMPTON ROADS CROSSING |  | 2010: 64
CONCEPTUAL PROPOSAL
[12 empty] | TA B 4 : | P UB LI C S UP PO RT
[13 empty] | 4 . a | Co m m uni t y Be ne fi t s
Identify who will benefit from the project, how they will benefit and how the project will benefit
the overall transportation system.
The Hampton Roads region of Virginia has 1.7 million residents and encompasses the area from James
City County, Surry County and Southampton County east to the Atlantic Ocean. The region is divided
by numerous waterways, foremost of which are the Chesapeake Bay, Hampton Roads, the York River,
the | James | River, | and | the | Elizabeth | River. | The |  | region | has | a | highly | diverse | social | structure |  | and
demographics. With the construction of the Hampton Roads Bridge Tunnel, James River Bridge and the
most recent Monitor Merrimac Memorial Bridge Tunnel, the mobility provided to the population has
improved significantly. People routinely traverse Hampton Roads for business, shopping, and recreation
purposes. The regions economy also employs individuals who reside outside the area, and the economy
of the area is greatly dependent upon continued and improved access across Hampton Roads.
The Hampton Roads Bridge Tunnel is the major link across Hampton Roads. Its four lanes are currently
operating at capacity with significant delays a routine occurrence. The only other interstate access across
Hampton | Roads |  | is | the | Monitor | Merrimac | Memorial |  |  | Bridge | Tunnel, | which | has | capacity |  | to | accept
additional |  | traffic | but | does | not | directly | serve | the | major | residential, |  | business, |  | and | military | areas | of
Virginia Beach or Norfolk. The James River Bridge is about five miles west of the Monitor Merrimac
Memorial Bridge Tunnel and has capacity for increased traffic but it also does not directly serve major
population centers. This traffic situation is limiting the growth of the region and impacts the required
mobility of U.S. Military in the area.
The | Major | Investment |  |  | Study | (MIS) | identified |  | the | need | to | increase | capacity | and | to | provide | a
transportation |  | facility |  | that | would | reduce | Hampton |  |  | Roads | Bridge | Tunnel | traffic |  | while | providing
improved access with greatly increased capacity from the peninsula to the southern Hampton Roads
area. The MIS also identified the need to provide linkage to major ports, existing highways and to serve
as a major freight corridor. The EIS (Locally Preferred Alternative) now proposed by SWB as the Third
Hampton Roads Crossing will satisfy these community needs by:
 | Reducing the traffic on the Hampton Roads Bridge Tunnel traffic by nearly 20 percent from the no
build alternative bringing the level of service on this route to acceptable levels.
 | Providing highways that are in tune with current and projected origin and destination patterns.
 | Providing access to all current and planned port areas.
 | Providing highways that will serve as a major freight corridor.
 | Providing direct connections with existing major highways in the area.
 | Providing a facility at significantly lower cost than planned.
 | Providing a facility significantly earlier than planned.
 | Providing the first facility that will have HOV access across Hampton Roads.
 | Providing a facility that can accommodate rail transit.
 | Making all of these improvements at a significantly lower cost and significantly earlier than planned.
THI6R5D HAMPTON ROADS CROSSING | [16 empty] | 65
CONCEPTUAL PROPOSAL
[11 empty] | TA B 4 : |  |  | P UB LI C S UP PO RT
[14 empty] | 4 . a | Co m m uni t y Be ne fi t s
The proposed facility will also act as an emergency access/egress route in case of an emergency like a
hurricane. The Third Hampton Roads Crossing will more than double the capacity to evacuate people
from and to the peninsula or the US58/US460 corridor.
Construction of the Third Hampton Roads Crossing will benefit social and economic aspects of the
region and improve the quality of life of its inhabitants. The improved access will foster the continuing
growth of the region’s increasingly diverse economy by making it easier to ship goods into and out of
the | region | through | its | port | facilities | and | reduce |  | existing | industrial |  | traffic |  | in | residential | areas. |  | The
improved access will also aid the continuing growth of tourism, which is a key aspect of the area
economy. |  | The | crossing | will | improve |  | the | readiness | posture | of | the | U.S. | military |  | through |  | alternate
overland route capacity in case of emergency and the potential for transshipping through a fourth port
area. The project will foster the growth of a new Commonwealth port facility and the Maersk/Sealand
terminal which is currently moving into its construction phase. These new port facilities aid mobility and
permit | the | continuing | favorable |  |  | growth | of | the | maritime | industry | that | is | a | very | significant |  | business
interest in the region and the Commonwealth.
Maintaining economic growth and attracting new business to the area demands that employees have an
acceptable quality of life. Improved access across the waterways in the area is critical for the individual
mobility and choices for alternative routes for recreation, employment and shopping. The region will be
in | virtual | gridlock | surrounded |  | by | air | pollution |  | without | construction |  | of | the | Third | Hampton |  |  | Roads
Crossing. Without construction of the Third Hampton Roads Crossing the situation will degrade the
quality of life to a point that is unacceptable to both employees and employers and the increasing
numbers of retired residents. The alternative is for some of the businesses to leave the area. This is not
acceptable |  | from | local, | state | or | national | viewpoints. |  | All | depend | on | Hampton |  |  | Roads | as | a | major
international port, quality vacation area and home to the U.S. Navy’s largest operational base.
On a short-term basis, the construction of the Third Hampton Roads Crossing will provide employment
to numerous individuals and provide opportunities for a large variety of local and regional businesses.
SWB is committed to utilizing local resources to the maximum extent possible. The construction effort
will create some short-term growth in the local economy followed by the long-term growth in other
business areas created by improved access and quality of life.
THI6R6D HAMPTON ROADS CROSSING | [17 empty] | 66
CONCEPTUAL PROPOSAL
[12 empty] | TA B 4 : |  |  | P UB LI C S UP PO RT
|  | 2013: 4 . b | G o v e r nm e nt a nd Co m m uni t y Suppo r t
Identify | any | 2005: anticipated; 2006: government; 2009: support; 2012: or; 2013: opposition, |  |  | or | general | public |  | support |  | or
opposition for the project.
The Major Investment Study (MIS) and the National Environmental Policy Act (NEPA) process have
investigated the problem of providing a suitable Third Hampton Roads Crossing for over a decade.
During this process there have been numerous opportunities for the public to comment on a variety of
routing alternatives that would foster economic growth while maintaining a suitable quality of life. The
resultant locally preferred alternative provides for the interests of virtually everyone in a manner which
has very minor impact on the environment.
The NEPA process and associated public hearings show the routing is acceptable to residents, business
interests | and | local | governments. | It | is | expected |  | that | there |  | may | be | occasional |  | concerns |  | about | some,
currently | unidentified, | 2006: issues; 2007: during; 2008: further; 2010: development | and | construction. |  |  | SWB | will | establish |  | and
maintain | a | community | relations | office |  | to | be | sensitive |  | to | these | types |  | of | issues | and | to | provide | all
stakeholders with continuous information as the project is developed and constructed.
Almost everyone concurs with the need for the project and the planned alignment. SWB recognizes that
concerns | have | been | voiced | regarding |  | methods |  | to | finance |  | the | facility. |  | Differing |  | opinions |  | regarding
financing alternatives are expected to continue, but due to the tremendous support for the project it is
expected that an acceptable method of financing can be found through dialogue with the relevant parties.
THI6R7D HAMPTON ROADS CROSSING | [18 empty] | 67
CONCEPTUAL PROPOSAL
[11 empty] | TA B 4 : |  | P UB LI C S UP PO RT
[12 empty] | 4 . c | Publ i c Inv o l v e m e nt Pl a n
Explain the strategy and plans that will be carried out to involve and inform the agencies and the
public in areas affected by the project.
The success of the Third Hampton Roads Crossing project is contingent upon consensus among the
Virginia Department of Transportation, local businesses and interest groups, state and local officials, and
the general public.
SWB | will | cooperate |  | with | these | groups | to | ensure | cohesiveness |  | of | efforts | towards |  | the | successful
completion of the undertaking desired by all stakeholders. SWB will develop and maintain a high level
of positive communication and support by informing and educating the many segments of the public
prior to and during construction. SWB will also be involved in open dialogue with all affected civic
groups to keep them abreast of project status and to listen to any concerns. SWB’s goal, simply stated, is
to | ensure | that | all | citizens | and | political | groups, | as | important |  | stakeholders, |  | have | an | opportunity |  | to
comment and become involved with the success of the project.
A large portion of the SWB public involvement program will involve meeting with various groups,
coordinating with the media, issuing press releases and maintaining an updated internet web site. We
expect | the | Third |  | Hampton | Roads | Crossing |  | project | will | be | very | successful | and | SWB |  | wants | all
stakeholders to be satisfied with the status and to take pride in the fact that their support has lead to a
project that satisfies their needs for the foreseeable future.
This project is locally developed and strongly supported by the citizens of the Hampton Roads area.
SWB is headquartered in Hampton Roads and is well aware of the importance of continuing the positive
involvement of the citizens. SWB will do everything within its capability to ensure that the general
public remains informed and that they share in the success of the project.
THI6R8D HAMPTON ROADS CROSSING | [16 empty] | 68
CONCEPTUAL PROPOSAL
[5 empty] | TA B 5 : |  | P ROJ E CT BE NE FI TS / C O M PA TI B I LI TY
[13 empty] | 5 . a |  | Publ i c Be ne f i t s
Describe the significant benefits to the community, region or state. | [11 empty] | Identify any state benefits
resulting from the project including the achievement of state transportation policies or other
state goals.
In the fall of 2000 the Virginia Department of Transportation (VDOT) estimated that the Third Hampton
Roads Crossing project would require a construction period of 14 years resulting in a completion date of
2014. | By that time it is expected that air pollution will have reached an unacceptable level, the region
will be in nearly constant gridlock, and that businesses would be leaving the area due to deterioration of
quality of life, which makes recruiting and retention of quality employees extremely difficult. One of the
areas major employers, the U.S. Navy, will continue to have less mobility than desired, as relocation is
not | an | option. | Clearly | delaying | completion |  | beyond |  | 2014 | is | not | acceptable. | The |  | Environmental
Assessment “no build” option is not acceptable to the inhabitants of the Hampton Roads area.
In the intervening years there has not been any progress on the project while the area has seen moderate
growth, increased congestion and growing concerns with environmental issues. SWB can still design
and | build | the | Third | Hampton | Roads | Crossing | and | have | it | complete |  | by | 2013, | or | earlier, | using | a
financing-design-build approach.
Even with a 2013 completion date congestion and environmental considerations will become far worse
than currently exist. The continued delay in executing the Third Hampton Roads Crossing project is
impacting business development and creating a reduced quality of life for residents and other workers in
the area. Recent incidents associated with Hurricane Isabel and a maritime incident serves to point out
just | how | fragile | the | transportation | system | is | in | the | 2003/2004 |  | timeframe. |  | Normal |  | growth | of | the
commercial, tourist and residential traffic will make transportation throughout the region intolerable by
the earliest time the facility can be available.
Current and future inhabitants of the area will clearly be the major benefactors of the project. The
transportation improvements will foster the development of existing businesses and create opportunity
for new industry while promoting those aspects of the area desirable for tourists. The continued growth
of the very successful commercial port will make Virginia a more favored port of call for international
commerce and create growth that is beneficial to the entire Commonwealth. The state would also benefit
in numerous other ways associated with the healthy development of the second largest economic region
in the Commonwealth.
The Third Hampton Roads Crossing will also provide the capability for improved transit operations.
High occupancy vehicle lanes and bus rapid transit capability will be available upon project completion.
THI6R9D HAMPTON ROADS CROSSING | [16 empty] | 69
CONCEPTUAL PROPOSAL
[5 empty] | TA B 5 : |  | P ROJ E CT BE NE FI TS / C O M PA TI B I LI TY
[13 empty] | 5 . b | Ec o no m i c Be ne fi t
Describe the significant benefits to the state’s economic condition. | [10 empty] | Discuss whether this project is
critical to attracting or maintaining competitive industries and businesses to the state or region.
The proposed project will benefit the entire economy of the Commonwealth, including significant direct
benefits to the tourism, port, and military aspects of the local economy. Underutilized land will become
available/accessible |  | for | business, | residential |  | or | tourism |  | purposes. |  | The | project |  | will | also | affect | the
economic development of areas adjacent to Hampton Roads. The project’s capability for future transit
operations | between | jurisdictions |  | in | the | Hampton | Roads |  | area | will | provide |  | an | alternative |  | means | of
transportation throughout the region.
The project will provide direct access to Craney Island, which is to be developed into a port facility.
This | development | is | highly | advantageous |  | to | the | Commonwealth |  |  | and | the | nation’s |  | economy. | The
connecting roadways will provide direct access to other port facilities in the area and the entire highway
system of the United States through the I-64 link on the peninsula and the US 58 and Route 460 links
along the southern part of Virginia. This project will also provide vital alternate routes for trucking using
the Norfolk International Terminals (NIT) and Lamberts Point Ports, thus reducing heavy traffic on
residential streets.
The project will provide an additional crossing of the Elizabeth River to directly access Norfolk and
Virginia | Beach. | The | Hampton | Roads | Bridge |  | Tunnel | is | currently |  | operating |  | at | its | design | capacity.
Continual congestion impacts residents’ quality of life, while detracting visitors and businesses, with the
resultant limitation on further economic development. This project will provide direct access with HOV
and multi-modal capability, which will benefit the tourism industry and foster all aspects of the region’s
economic growth. This crossing will also benefit the military by enhancing their mobility by providing
an additional, more direct access to and from naval installations.
By improving the quality of life, the Third Hampton Roads Crossing project will ensure the growth of
businesses that depend on a highly skilled workforce. These types of businesses provide significant
benefits to the region and the state.
SWB’s proposal to build the project in less time and at a lower cost than planned will mitigate all
problems associated with a later completion and will stimulate positive economic growth for the region.
THI7R0D HAMPTON ROADS CROSSING | [16 empty] | 70
CONCEPTUAL PROPOSAL

## Page 2
Name: “Table 1 of 1 on page 2 of 80”
Table: 1
June 30, 2004
Mr. Malcolm T. Kerley, P.E.
Chief Engineer for Program Development
Virginia Department of Transportation
1401 E. Broad Street
Richmond, Virginia 23219
Re: | Conceptual proposal pursuant to the Public-Private Transportation Act of
1995 for design, construction and financing of the Third Hampton Roads
Crossing
Dear Mr. Kerley:
Enclosed are twenty (20) copies of the Skanska/Washington/BAM (SWB) conceptual
proposal for the Third Hampton Roads Crossing submitted in accordance with both the
Public-Private |  | Transportation |  |  |  | Act |  | of | 1995 | (PPTA) | and | the | Department |  | of
Transportation's Implementation Guidelines. | [8 empty] | A copy of the proposal is being delivered to
all appropriate jurisdictions as indicated in the attached.
TAB 3 of the proposal, the Project Financing, is considered proprietary and confidential
in its entirety. |  | The attached letter granted exemption from all Freedom of Information
Act requests for this portion of the proposal.
A | cashier's | check | in | the | amount |  | of | $10,000 | is | being | forwarded | separately | to | cover
VDOT's review costs.
SWB | is | looking | forward |  | to | VDOT's |  | favorable consideration |  |  | of | this | proposal | for | the
critical Third Hampton Roads Crossing Project.
I am the designated SWB point of contact for this project.
Sincerely,
F. X. Watson
Project Director
Attachments: |  | 1) Local Jurisdiction Distribution
2) Letter regarding Confidential and Proprietary Information
SKANSKA  WASHINGTON  BAM
| P.O. Box 57, Norfolk, VA |  |  |  |  | 23501 | 809 S. Military Highway, Virginia Beach, VA | [5 empty] | 23464
|  |  |  | Tel: | 757-420-4140 |  |  |  | Fax: | 757-420-3551

## Page 3
Name: “Table 1 of 1 on page 3 of 80”
Table: 2
Attachment 1. AFFECTED LOCAL JURISDICTIONS
Distribution List
TAB 3 not provided with these copies
Mr. George E. Wallace, City Manager
City of Hampton
22 Lincoln Street |  | Mr. Clarence V. Cuffee, City Manager
Hampton, Virginia 23669 |  | City of Chesapeake
(Mr. Charles A. Wornom, Mayor) |  | 306 Cedar Road
Chesapeake, Virginia 23328
Mr. Ed Maroney, City Manager |  | (Mr. Dalton Edge, Mayor)
City of Newport News
2400 Washington Street |  | Mr. James K. Spore, City Manager
10 th Floor City hall |  | City of Virginia Beach
Newport News, Virginia 23607 |  | 2401 Courthouse Road
(Mr. Joe S. Frank, Mayor) |  | Municipal Center, Bldg. #1
Virginia Beach, Virginia 23456
Mr. Jackson C. Tuttle, City Manager |  | (Mrs. Meyera E. Oberndorf, Mayor)
City of Williamsburg
401 Lafayette Street |  | Mr. Rowland L. Taylor, City Manager
Williamsburg, Virginia 23185 |  | City of Franklin
(Ms. Jeanne Zeidler, Mayor) |  | 207 West Second Street
Franklin, Virginia 23851
Mr. Charles W. Burgess, Jr., City Manager |  | (Mr. James P. Councill, III, Mayor)
City of Poquoson
500 City Hall Avenue |  | Mr. Peter M. Stephenson, Town Manager
Poquoson, Virginia 23662 |  | Town of Smithfield
(Mr. Gordon C. Helsel, Jr., Mayor) |  | 315 Main Street
Smithfield, Virginia 23431
Mr. Robert “Steve” Herbert, City Manager |  | (Mr. Stan D. Clark, Chairman)
City of Suffolk |  | Isle of Wight Board of Supervisors
441 Market Street
Suffolk, Virginia23434 |  | Mr. Sanford B. Wanner, County Administrator
(Mr. Dana W. Dickins, III, Mayor) |  | James City County
101 Mounts Bay Road
Mr. C. W. McCoy, City Manager |  | Williamsburg, Virginia 23187
City of Portsmouth |  | (Mr. Bruce Goodson, Chairman)
801 Crawford Street |  | James City County Board of Supervisors
Portsmouth, Virginia 23704
(Dr. James W. Holley, III, Mayor) |  | Mr. W. Douglas Caskey, County Administrator
Isle of Wight County
Mrs. Regina V. Williams, City Manager |  | 17130 Monument Circle-Suite A
City of Norfolk |  | Isle of Wight, Virginia 23397
810 Union Street |  | (Mr. Stan D. Clark, Chairman)
Norfolk, Virginia 23510 |  | Isle of Wight County Board of Supervisors
(Mr. Paul D. Fraim, Mayor)
SKANSKA  WASHINGTON  BAM
P.O. Box 57, Norfolk, VA | 23501 | 809 S. Military Highway, Virginia Beach, VA |  | 23464
Tel: | 757-420-4140 | Fax: | 757-420-3551

## Page 4
Name: “Table 1 of 1 on page 4 of 80”
Table: 3
Attachment 1. AFFECTED LOCAL JURISDICTIONS
Distribution List
TAB 3 not provided with these copies
Mr. James O. McReynolds, County Administrator
York County
224 Ballard Street
Yorktown, Virginia 23690
(Mr. James S. Burgett, Chairman)
York County Board of Supervisors
Mr. Michael Johnson, County Administrator
Southampton County
26022 Administration Center Drive
Courtland, Virginia 23837
(Mr. Dallas O. Jones, Chairman)
Southampton County Board of Supervisors
Mr. William H. Whitley, County Administrator
Gloucester County
6467 Main Street
Gloucester, Virginia 23061
(Mr. Charles R. “Rick” Allen, Jr., Chairman)
Gloucester County Board of Supervisors
Mr. Terry D. Lewis, County Administrator
Surry County
45 School Street
Surry, Virginia 23883
(Mr. Reginald O. Harrison, Chairman)
Surry County Board of Supervisors
Mr. Arthur L. Collins, Executive Director
Hampton Roads Planning district Commission
723 Woodlake Drive
Chesapeake, Virginia 23320
SKANSKA  WASHINGTON  BAM
P.O. Box 57, Norfolk, VA | 23501 | 809 S. Military Highway, Virginia Beach, VA |  | 23464
Tel: | 757-420-4140 | Fax: | 757-420-3551

## Page 6
Name: “Table 1 of 1 on page 6 of 80”
Table: 4
TA BL E OF CO N TE NTS
| TAB | TITLE |  | PAGE
Transmittal Letter
Freedom of Information Act Letter
|  | Table of Contents |  | i
|  | List of Exhibits |  | ii
|  | Executive Summary |  | E-1
| 1 | Qualifications and Experience
|  | 1.a | Organizational Approach | 1
|  | 1.b | Experience | 8
|  | 1.c | Point of Contact | 36
|  | 1.d | References | 37
|  | 1.e | Financial Statements | 38
|  | 1.f | Small, Woman and Minority Owned Business Participation | 39
| 2 | Project Characteristics
|  | 2.a | Project Description | 40
|  | 2.b | VDOT Participation | 43
|  | 2.c | Permits | 44
|  | 2.d | Environmental Issues | 45
|  | 2.e | Critical Success Factors | 47
|  | 2.f | Schedule | 49
|  | 2.g | Timely Completion of the Project | 50
|  | 2.h | Assumptions Related to Ownership, Liability and Operational
|  |  | Responsibility | 51
|  | 2.i | Project Partial Openings | 52
| 3 | Project Financing (Restricted Distribution)
|  | 3.a | Project Cost Estimate | 53
|  | 3.b | Financing Plan | 57
|  | 3.c | Financial Assumptions | 58
|  | 3.d | Risk Factors | 62
|  | 3.e | Additional Resources | 63
|  | 3.f | Sources and Uses of Funds | 64
| 4 | Public Support
|  | 4.a | Community Benefits | 65
|  | 4.b | Government and Community Support | 67
|  | 4.c | Public Involvement Plan | 68
| 5 | Project Benefits/Compatibility
|  | 5.a | Public Benefits | 69
|  | 5.b | Economic Benefits | 70
THiIRD | HAMPTON ROADS CROSSING |  |  | i
CONCEPTUAL PROPOSAL

## Page 7
Name: “Table 1 of 1 on page 7 of 80”
Table: 5
TA BL E OF CO N TE NTS
| FIGURE | TAB | TITLE | PAGE
| 1.1 | 1.a | Organization Chart | 3
| 2.1 | 2.a | EIS Alignment | 41
| 3.1 | 3.a | Project Alignment | 56
| 3.2 | 3.c | Project Schedule | 58
APPENDICIES |  |  | TITLE
| A | Skanska USA Civil, Inc. Brochure
| B | Washington Group International, Inc. Brochure
| C | Parsons Brinckerhoff Quade & Douglas, Inc. Brochure
| D | Jacobs Civil Inc. Brochure
| E | Annual Report 2003 Skanska AB
| F | Audited Financial Statement of Skanska USA Civil, Inc.
| G | Audited Financial Statement of Tidewater Skanska, Inc.
| H | 10-K Annual Report of Washington Group International, Inc.
| I | Annual Report 2003 Royal BAM Group nv
| J | Flatiron Brochure
THiIiRD | HAMPTON ROADS CROSSING |  |  | ii
CONCEPTUAL PROPOSAL

## Page 8
Name: “Table 1 of 1 on page 8 of 80”
Table: 6
EX EC UT I VE S UM M AR Y
` | Introduction – Skanska/Washington/BAM (SWB), a joint venture of Skanska USA, Inc. (Skanska),
Washington |  | Group | International |  |  | (Washington) |  |  | and | Royal |  | BAM | Group |  | nv | (BAM) | is | submitting |  | an
unsolicited proposal for the development, design, construction, financing, operation and maintenance of
the Third Hampton Roads Crossing. | [6 empty] | This conceptual proposal is submitted in accordance with the
Virginia | Department |  |  | of | Transportation’s |  |  | (VDOT) |  | implementing |  |  | guidelines |  |  | for | the | Virginia |  | Public
Private Transportation Act of 1995. | [6 empty] | This conceptual proposal is based upon the Major Investment Study
(MIS), the Environmental Impact Statement (EIS) and the 2001 Record of Decision. | [16 empty] | The design team of
Parsons Brinckerhoff Quade & Douglas, Inc. and Jacobs Civil, Inc. (Jacobs) (formerly JE Sverdrup) will
serve as the engineer-of-record. | [5 empty] | The SWB Team members have been involved with the design and/or
construction of all of the tunnels and bridge-tunnels in the Hampton Roads area.
` | Project Configuration - The Third Hampton Roads Crossing involves the construction of 13 miles
of limited access expressway in addition to widening 15 miles of interstate highway. The project will
cross | Hampton | Roads |  | and | the | Elizabeth |  | River | via trestles |  |  | and | two | new | tunnels |  | to | provide |  | greatly
enhanced mobility in the Hampton Roads area.
` | Project Need - The Hampton Roads region is a major residential, commercial and tourist area in
Virginia and home to many military installations. | [8 empty] | Increasing traffic volumes have outstripped capacity.
The MIS and EIS predict traffic levels will become so critical that by the time any solution is in place
the | regions | economy |  | will | be | stifled | and | noxious |  | emissions |  |  | will | impair | the | health |  | of | individuals.
Without | near-term |  | relief, |  | the | quality | of | life | and | the | region’s |  | economy |  | will | decline. |  | Several |  | recent
occurrences of major gridlock are just another indication that the Third Hampton Roads Crossing is
needed earlier rather than later.
` | Consistency | with |  | Concept |  | - | The | EIS | provides |  | an | estimate |  | of | $4.4 | billion | to | construct |  | the
Metropolitan Planning Organization’s (MPO) Locally Preferred Alternative that was approved by the
Commonwealth Transportation Board. In 2000 VDOT anticipated that the project could be completed in
2014. This conceptual proposal contains alternatives that dramatically reduce the project’s cost and
accelerates the completion date of the Third Hampton Roads Crossing. | [13 empty] | The concepts that are offered by
this conceptual proposal are consistent with the Third Hampton Roads Crossing MIS and EIS. | [18 empty] | Specific
recommendations for the project’s financing and development are included.
` | Environmental |  | - | All | known | environmental |  |  | issues |  | can | be | prudently |  | and | economically |  |  | mitigated
based | upon | SWB’s |  | proposed |  | develop-finance-design-build-operate-maintain | [9 empty] | approach |  |  | and | SWB’s
experience with addressing the same issues on previous projects. The entire Conceptual Proposal is
based upon the Record of Decision (ROD) issued on June 4, 2001.
` | Utility Plan – The SWB Team will assume responsibility for utility coordination and relocations.
Proactive communication will be maintained with impacted utility owners to quickly resolve all utility
issues.
` | Property Acquisition – According to the EIS, 38 residences and 11 businesses will need to be
relocated. The SWB Team will be responsible for obtaining real estate and will prepare the necessary
documentation for VDOT in cases where taking by eminent domain is required.
THI1RD | HAMPTON ROADS CROSSING | [18 empty] | E-1
CONCEPTUAL PROPOSAL

## Page 9
Name: “Table 1 of 1 on page 9 of 80”
Table: 7
EX EC UT I VE S UM M AR Y
` | Design | and | Construction |  |  | Guarantees |  | – | SWB | will | sign | a | Comprehensive |  |  | Agreement |  | and | will
guarantee a fixed price and completion date.
` Institutional and Public Support - Testimony provided during the preparation of the MIS and the
EIS, | discussions |  | with | governmental, |  |  | private |  | sector | groups |  | and | individuals |  |  | indicate |  | overwhelming
support for the project at all levels. | [5 empty] | Most see it as needed now. | [5 empty] | The project is supported by:
 | Metropolitan Planning Organization
 | Hampton Roads Third Crossing Commission
 | Commonwealth Transportation Board
 | Hampton Roads Partnership
 | Hampton Roads Chamber of Commerce
 | U.S. Military
 | Virginia Port Authority
 | Hampton Roads Maritime Association
SWB will initiate a public information program in coordination with VDOT to assure that all interested
parties | are | provided |  | information |  | and | given |  | opportunities |  | to | ask |  | questions |  | and | provide | meaningful
comments. |  | All | available | communication |  |  |  | techniques |  | will | also |  | be | used | to | keep | the | general | public
informed.
` | Construction Process – The SWB Team will manage the construction process to ensure that it is
consistent with established VDOT standards and practices. The maintenance of traffic plans will assure
that an adequate number of lanes will be maintained throughout the construction period. Construction
will be primarily over water on a new alignment and is expected to have minimal traffic impacts. | [18 empty] | The
proposed accelerated design-build schedule will further reduce traffic impacts while providing a greatly
enhanced |  | facility | in | significantly |  | less | time | than | the | design-bid-build |  |  |  | process |  | originally |  | planned | by
VDOT.
` | QC/QA Process – SWB Team members are thoroughly familiar with VDOT’s quality control and
quality assurance requirements. | [5 empty] | SWB will develop a project specific Design Quality Management Plan
and a Quality Assurance/Quality Control Inspection Program. The new crossing will reflect the attention
to | detail | and | quality | that | is | inherent | in | the | transportation |  | projects |  |  | that | the | team | has | designed | and
constructed in the past.
` | Small, Women and Minority-Owned Business (S/W/M) Participation – SWB has developed the
following approach for involving S/W/M owned businesses:
 | Actively solicit the involvement of S/W/M owned firms via announcements and notices published in
local and regional construction journals and other periodicals.
 | Set aside scopes of work for S/W/M owned firms and encourage them to participate in the pre-
qualification process and bidding opportunities.
 | Utilize S/W/M owned businesses who have a long standing relationship with SWB team members.
 | Include provisions regarding S/W/M compliance in all subcontracts.
 | Review the SWB Team's progress, attaining the S/W/M goals, on a regular basis.
THI2RD | HAMPTON ROADS CROSSING | [17 empty] | E-2
CONCEPTUAL PROPOSAL

## Page 10
Name: “Table 1 of 1 on page 10 of 80”
Table: 8
EX EC UT I VE S UM M AR Y
` | Business Plan – SWB has developed a financial plan that is included in TAB 3. | [11 empty] | This preliminary
plan presents a realistic approach based on conservative assumptions to financing the Third Hampton
Roads Crossing. The plan is based on financing the project by means of tax-exempt toll revenue bonds,
augmented by funds from public sources. | [7 empty] | The total cost of the facility will be between $2.5 billion and
$ 4.0 billion and will require up to $1.8 billion in public funds. | [11 empty] | Toll levels and the amount of public
funds required vary with the alternative selected. | [8 empty] | If the project is built in phases, public funds in the
amount of approximately $0.5 billion plus a reasonable toll will provide the critical first two phases of
the project.
` | Benefits of the SWB Plan - The benefits that are described by this conceptual proposal are a result of
the evolution of the SWB Team’s planning. | [8 empty] | A considerable effort has been made to develop a plan that
is simple and straightforward while offering the most benefit to the public.
 | The Third Hampton Roads Crossing is a multi-modal facility that incorporates an exclusive High
Occupancy Vehicle/Bus Rapid Transit lane reserving space for the future addition of Light Rail
| Transit. |  | This multi-modal solution provides a more flexible facility and extends the life and use of
this transportation corridor.
 | SWB will complete the crossing within 7 years after the Notice to Proceed, while the most recent
| VDOT |  | plan | was | based | on | a | 14-year | period | using | the | traditional | design-bid-build | contracting
| approach. |  | This accelerated schedule will provide the vital traffic handling capacity that is needed
| now | as | well | as | the | capacity | to | accommodate |  | the regions continued demographic and economic
growth.
 | SWB’s proposed public-private partnership approach significantly reduces the time and cost of the
| Third Hampton Roads Crossing. | [6 empty] | Simply put, the use of private sector funding now saves over
$1,000,000,000 compared to the current plan.
 | The SWB plan provides the quickest solution to alternative hurricane evacuation routes and frequent
road system incapacitations due to accidental occurrences.
 | Adequate transportation infrastructure is provided to support the continued growth of the cities that
surround the corridor and new maritime facilities such as the Craney Island port and the new Maersk
Terminal.
 | As an environmentally friendly solution, SWB’s concept will reduce air pollution.
 | An electronic toll collection system such as EZ-Pass or Smart Tag will be used to minimize the
impact of toll collection on riders and permit implementation of variable pricing strategies.
 | Design and construction contracts will emphasize use of local and regional firms.
 | The SWB plan utilizes the most highly experienced team of world class contractors imaginable for
the development, design and construction of the Third Hampton Roads Crossing.
THI3RD | HAMPTON ROADS CROSSING | [12 empty] | E-3
CONCEPTUAL PROPOSAL

## Page 11
Name: “Table 1 of 1 on page 11 of 80”
Table: 9
|  |  |  | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[8 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
Identify the legal structure of the firm, or consortium of firms making the proposal. | [9 empty] | Identify the
organizational structure for the project, the management approach and how each partner and
major subcontractor in the structure fits into the overall team.
Legal Structure
Skanska USA, Inc. (Skanska), Washington Group International, Inc. (Washington), and Royal BAM
Group nv (BAM) have formed the joint venture Skanska/Washington/BAM (SWB). SWB has been
formed to develop, finance, design, build, operate and maintain the Third Hampton Roads Crossing.
Skanska is the joint venture's managing partner. The project will be executed through the three firms’
respective operating companies: Tidewater Skanska, Inc. (Tidewater), Washington Group International
(Washington), and Flatiron Construction Corp. (Flatiron). | [6 empty] | Tidewater is the joint venture’s operating
manager. | Joining SWB is the design team of Parsons Brinckerhoff Quade & Douglas, Inc. (PB) and
Jacobs Civil, Inc. (Jacobs) (formerly Sverdrup), Goldman Sachs, who will be the financial advisor, and
Kaufman & Canoles, P.C., the legal advisors. |  |  |  |  | Collectively, this group of joint venture partners and
designers is known as the SWB Team. The SWB Team members have experience working together to
successfully | execute | large | and | complex | projects. | As | the | development | proceeds, | SWB | may | add
additional partners and subcontractors to the team. A brief description of each SWB Team member is
presented below.
Organizational Structure
` Tidewater Skanska, Inc. (Tidewater) of Norfolk, Virginia is a long-term VDOT contractor with a
reputation for delivering outstanding marine and transportation facilities under budget and ahead of
schedule. The firm’s more notable projects include the construction of the award-winning Coleman
Bridge, the original Chesapeake Bay Bridge Tunnel, the Hampton Roads Bridge Tunnel, the Cooper
River Bridge in Charleston, SC, the new Woodrow Wilson Bridge Foundations, and the Pinners Point
Interchange. Tidewater is a wholly owned subsidiary of Skanska. | [7 empty] | Skanska’s financial strength and the
broad capabilities of its subsidiary firms, together with those of the other team members, will make the
dream of a Third Hampton Roads Crossing a reality.
` | Washington Group International (Washington) of Boise, Idaho, is a leading transportation design-
build firm with significant project development experience. The firm’s construction history dates to
1912 with the founding of its heritage company, Morrison Knudsen. In joint venture with Interbeton,
Washington Group built the Monitor Merrimac Memorial Bridge Tunnel (the second Hampton Roads
crossing) and the Ted Williams Tunnel in Boston. Project development transportation projects include
the E-470 Toll Road in Denver and the Pocahontas Parkway (Route 895) in Virginia. Washington’s
experience will be used in conjunction with that of the other Partners to provide the depth of capability
needed for this project.
` | Flatiron Construction Corp. (Flatiron) of Longmont, Colorado, is a subsidiary of Royal BAM
Group nv of the Netherlands. Interbeton, Inc. (Interbeton), a Flatiron subsidiary, in joint venture with
Washington, built the Monitor Merrimac Memorial Bridge Tunnel and the Ted Williams Tunnel in
Boston. Interbeton also recently completed the widening of the Chesapeake Bay Bridge Tunnel trestles.
Additionally, BAM has completed many submerged tunnels in Europe. | [7 empty] | BAM’s financial strength and
THI1RD | HAMPTON ROADS CROSSING | [10 empty] | 1
CONCEPTUAL PROPOSAL

## Page 12
Name: “Table 1 of 1 on page 12 of 80”
Table: 10
[7 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
experience will be used in conjunction with that of the other team members to provide the resources that
will be required to undertake this project.
` | Parsons Brinckerhoff Quade & Douglas, Inc. (PB) and Jacobs Civil, Inc. (Jacobs) are the premier
marine tunnel and transportation designers in the United States. They have designed all of the tunnel and
bridge-tunnel facilities in the Hampton Roads area and thousands of highways and bridges around the
world. | PB | will | draw | upon | its | extensive |  | environmental | and | permitting | experience |  | to | perform | any
required permit applications or supplements to the environmental document. Additionally, the long and
successful relationship that PB and Jacobs have with the other SWB Team members makes them the
ideal firms to engineer and design the Third Hampton Roads Crossing.
` | Goldman, Sachs & Co. (Goldman Sachs) is one of the nation’s largest, most diversified and most
highly regarded investment banks. | [5 empty] | The firm was founded in 1869 as a dealer of commercial paper, a
product Goldman Sachs created. | [5 empty] | Since the firm’s founding, it has expanded to over 22,000 employees
located in 67 regional offices in 24 countries. It’s Municipal Bond Department, established in 1951, is
part of the firm’s Fixed Income, Currency and Commodities Division and is a leader in transportation
finance. | The Department consists of 130 dedicated municipal bond professionals who coordinate their
activities to underwrite and distribute municipal securities and maintain a liquid secondary market for
issues the firm manages.
` | Kaufman & Canoles, P. C. (K&C) is a full-service commercial law firm with offices in Virginia
Beach, Chesapeake, Hampton, Newport News, Norfolk, Richmond and Williamsburg with over 125
attorneys. |  | K&C has been a nationally recognized firm in the area of tax-exempt and public finance
since 1974 and has served as either bond counsel, underwriters counsel, issuer counsel or borrowers
counsel in hundreds of financing. | [5 empty] | The firm has participated in unsolicited proposals under the Public-
Private | Transportation |  |  | Act | and | financings |  | which | resulted | therefrom, | either | directly | or | indirectly,
including | the | Commonwealth’s |  |  |  | Route | 28 | improvements | in | Loudoun | and | Fairfax | Counties | and | the
Chesapeake Toll Road. |  |  |  | The firm has experience in arranging, structuring and coordinating all aspects of
public-private projects and economic development initiatives.
Figure 1.1, Organization Chart, shows the proposed organizational relationships between the Virginia
Department of Transportation (VDOT), the three SWB joint venture partners, and the designers, PB and
Jacobs and the financial advisors, Goldman Sachs.
THI2RD | HAMPTON ROADS CROSSING | [13 empty] | 2
CONCEPTUAL PROPOSAL

## Page 13
Name: “Table 1 of 1 on page 13 of 80”
Table: 11
|  |  | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  |  |  | 1 . a | O r g a niza t i o na l Appr o a c h
Figure 1.1 | Organizational Chart
|  | Skanska/Washington/BAM (SWB) |  |  | 63-20
Organization
|  |  | Skanska USA |  | Or
|  | Washington Group International |  |  | Public Agency
Royal BAM Group nv
| Designers | Financial Advisors |  | Legal Advisors
| PB / Jacobs | Goldman Sachs |  | Kaufman & Canoles
The SWB Team members are all recognized leaders in the engineering and construction industry, as
demonstrated by current rankings by Engineering News-Record (ENR) shown on Table 1.1. These firms
are also among the world’s oldest and largest companies in the industry. Their experience in the region
is unparalleled; having been involved with all of the tunnels and bridge-tunnels in the Hampton Roads
area. | Fortune magazine has selected Skanska AB, the parent company of Skanska, USA, as the most
admired company in the world in the category of Engineering and Construction. The ratings were based
on quality of management; quality of products and services; innovativeness; long-term investment value;
financial soundness; ability to attract, develop and retain talent; community responsibility; and use of
corporate assets.
Table 1.1 Engineering News-Record Rankings
SWB Team Member/Ranking
ENR
| Category | Skanska | Washington | BAM | PB | Jacobs
Domestic |  | 6 | 9 | 95
Construction
International |  | 1 | 35 | 36
Construction
Transportation |  | 4 | 10 | 15 | 3 | 5
Bridges |  | 2 |  | 4 | 4 | 3
Highways |  | 4 | 7 | 15 | 2 | 5
Design |  |  | 20 |  | 11 | 4
THI3RD | HAMPTON ROADS CROSSING |  |  |  |  | 3
CONCEPTUAL PROPOSAL

## Page 14
Name: “Table 1 of 1 on page 14 of 80”
Table: 12
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
Management Approach
SWB’s management approach is a clear, comprehensive plan to develop the Third Hampton Roads
Crossing. The plan addresses the managerial, financial, technical, legal, environmental, and construction
requirements for the project.
` Program Manager - The SWB executive committee will appoint a program manager to manage the
project with the guidance of the managing partner, Skanska. | [10 empty] | To support the program manager, SWB
will have a full-time and integrated staff consisting of experienced, qualified personnel from the joint
venture team members. This staff will award contracts for planning, design and construction services to
augment | the | services |  | that | will | be | provided | by | the | operating |  | companies. |  | SWB |  | will | function | as | an
integrated staff without any company affiliation under the direction of the program manager.
` | Project | Office | - | The | cornerstone |  | of | SWB’s | approach |  | is | partnering | with |  | a | strong | emphasis |  | on
communication. SWB will facilitate communication by establishing a Project Office that co-locates the
design, | public | information |  |  | and | construction |  | management |  |  | staffs | of | SWB | and | VDOT. |  | All | decision-
makers will be co-located in one office to promote their interaction, which has been crucial to our
successful completion of many other large projects.
Design Management Approach
` | Design Team - PB will lead the design team. PB will make extensive use of the broad experience and
depth of its engineering and design organization, the largest transportation engineering staff in the U.S.
Jacobs will also provide engineering and design personnel to augment the design team. The combined
resources of PB and Jacobs represent an enormous technical capability with extensive experience in
bridge and tunnel design.
` | Preliminary | Engineering |  |  | – | Preliminary |  | engineering |  | activities |  | will | be | performed |  |  | by | PB/Jacobs.
SWB will provide constructibility reviews (including safety) throughout the preliminary engineering
effort to identify practical and expedient construction approaches that will shorten schedules and lower
construction costs. SWB will develop realistic construction cost estimates based on its team members’
local | marine | and | heavy |  | civil | construction |  | experience. |  | This |  | interactive |  | design |  | team | will | prepare
construction |  | cost | estimates |  | and | schedules |  | that | will | be | used | for | the | Plan | of | Finance |  | and | the
Comprehensive Agreement.
` | Design Management Plan – SWB will develop a Design Management Plan (DMP) within three
weeks of receipt of the notice-to-proceed. The DMP will include procedures and processes that take
advantage of the SWB Team's design-build experience. The DMP will promote the efficient execution
of the design effort. Lessons learned in implementing DMPs for previous design-build projects will
contribute to an efficient, effective management plan for the Third Hampton Roads Crossing. The DMP
will prescribe a number of measures to control the design including:
 | Clearly defining the scope of services for each subconsultant. Each subconsultant will be managed
by an assigned manager.
 | Developing of detailed design schedules, consistent with the project's master schedule, for use in
managing the development and production of all construction packages.
THI4RD | HAMPTON ROADS CROSSING | [17 empty] | 4
CONCEPTUAL PROPOSAL

## Page 15
Name: “Table 1 of 1 on page 15 of 80”
Table: 13
[6 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
 | Ensuring that design quality control will be an integral part of the design management process by
reflecting the procedures outlined in the Design Quality Management Plan.
 | Enhancing coordination and communication with a local area network (LAN) that provides e-mail
and access to standard software, as well as design documents as they are developed.
 | Providing guidance for advance planning requirements to define each construction package.
 | Outlining communication procedures with VDOT and other public agencies.
` | Work Plans - Work plans will be prepared for each design element. A project-specific work plan,
including detailed tasks for each construction package, will be prepared concurrently with the DMP. The
work plans will define managerial and technical approaches that will be used for the engineering and
design of each package. The plans will define the scope of services, staffing requirements, tasks and
their objectives, deliverables, coordination requirements, permitting requirements, lead times, budgets,
schedules, and reporting procedures relative to each package.
Construction Management Approach
SWB’s construction management concept takes full advantage of the team’s strong local presence and
experienced | construction |  |  | supervisors. |  | Over | the | years, | the | SWB | members | have | developed | excellent
relationships with local suppliers and subcontractors.
` | Safety - SWB’s construction concept enhances safety performance by placing safety technicians in
the field to monitor the construction activities of our crews and subcontractors. Safety is a top priority.
The SWB Team’s construction safety manager will report to the program manager.
` | Task Forces - The Project Office will house all members of the task force groups that are responsible
for constructing the crossing. The construction supervisors will be active participants in the task force
groups to facilitate the development of effective and efficient designs. The design team project engineers
and design discipline leads will assume a leadership role. Task force meetings will be convened on a
regular basis to coordinate construction requirements and collaborate on design decisions. The task forces
will also facilitate constructibility by reviewing the construction packages prior to each formal design
review.
` | Task-specific Work Plans - The development of task-specific work plans by the superintendent that is
supervising each construction operation is another cornerstone of SWB’s construction approach. These
detailed | work | plans | will | include | a | work | plan | narrative, | schedule, |  | budget, | staff-hour | factors, | quality
specifications, safety procedures, and testing methods for each operation. SWB’s construction approach
requires the safety, quality, and the production staffs to review these plans before construction begins. The
goal is to increase quality, lower cost, and raise productivity.
` | Constructability - Constructability is built into our construction concept through constructability
reviews and regular construction planning meetings. All field representatives attend these meetings,
including | production |  | supervisors, |  | subcontractors, |  |  | quality | and | safety | personnel, | and | the | construction
management | staff. | Three-week |  | look-ahead |  |  | schedules | are | coordinated |  | during | these | meetings. | These
schedules focus on the current week and following two-week period.
THI5RD | HAMPTON ROADS CROSSING | [12 empty] | 5
CONCEPTUAL PROPOSAL

## Page 16
Name: “Table 1 of 1 on page 16 of 80”
Table: 14
[7 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[12 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
` | Permitting | - | The | SWB | Team | will | establish | a | permit | task | force | to | address | all | Commonwealth,
federal, and local requirements. This task force will interface with public agencies to obtain permits in a
timely manner and will serve as the focal point to resolve any permit compliance issues.
Public Information Program
SWB’s approach to public outreach is to use education and information to maintain a high level of
communication. SWB’s two primary public information goals will be to (1) gain and maintain public
support for the Third Hampton Roads Crossing and (2) to provide the support needed for the public to
deal with construction concerns on a daily basis.
It is SWB’s experience that when the traveling public is aware of potential impacts, knows what is
happening, and why, how, and when it will happen, they are more apt to maintain positive opinions
regarding construction. SWB’s public information team will apply this approach to it’s interaction with
residents, businesses, |  |  |  | commuters, |  | local | governments, the Department of Defense, and Virginia Port
Authority. SWB will also use this approach to assist VDOT counterparts to inform the traveling public.
Public information goals will be accomplished by: establishing and maintaining clear and open lines of
communication with internal teams and external audiences; meeting public information needs through
the media, public meetings and a project web site; and providing accurate information through other
audience-appropriate distribution methods. Interaction with neighborhoods and businesses impacted by
SWB’s construction activities will occur via communication between the public information specialists
and the production crews. |  |  |  | As issues/concerns are brought up through a project website or hotline, the
public information specialist will interact with the production crews to develop appropriate resolutions.
Plan of Finance
The SWB Team’s financial consultant will prepare a Plan of Finance that includes sources and uses of
funds. A preliminary Plan of Finance is provided in TAB 3. This plan will be refined as more information
becomes available during the Detailed Technical Proposal Phase.
Non-Recourse Toll Revenue Bond Sale
SWB’s approach to funding includes the sale of non-recourse toll revenue bonds. This is a common
approach that is used for funding transportation improvement throughout the U.S. SWB is prepared to
create, in conjunction with VDOT, an IRS 63-20 not-for-profit private corporation or a public agency,
for such a sale. SWB services would include supporting the 63-20 or public agency in the bond rating
process as well as the bond underwriting and sale.
Comprehensive Agreement
SWB will execute a Comprehensive Agreement with VDOT for the development rights associated with
the Third Hampton Roads Crossing, subject to the mutual satisfaction of both parties regarding the terms
and conditions. SWB will agree to the contract amount and assume liability for the project’s design and
construction. As a public-private venture, VDOT will be responsible for providing services including
design reviews, right-of-way acquisition coordination, assistance with permitting, coordination with the
Federal Highway Administration, and quality assurance acceptance activities.
THI6RD | HAMPTON ROADS CROSSING | [13 empty] | 6
CONCEPTUAL PROPOSAL

## Page 17
Name: “Table 1 of 1 on page 17 of 80”
Table: 15
[6 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . a | O r g a niza t i o na l Appr o a c h
Contracting Opportunities
Each of the world-renowned companies that constitute the SWB Team relies upon subcontractors to
provide specialty services for selected portions of the work. Based on the team members’ experience and
extensive current operations in the Hampton Roads area, the SWB Team anticipates awarding subcontracts
for the following construction specialties:
 | Tunnel segment fabrication |  |  |  |  | Concrete |  |  |  | Earthwork and paving
 | Pre-cast concrete members |  |  |  |  | QA/QC |  |  |  | Public relations
 | Right-of-way services |  |  |  |  | Diving |  |  |  | Specialty design
 | Electrical |  |  |  |  | Reinforcing steel |  |  |  | Utility relocation
 | Mechanical |  |  |  |  | Slurry walls |  |  |  | Metal finishes
 | Dredging |  |  |  |  | Rip-rap and gravel |  |  |  | Traffic management system
 | Tug boat support |  |  |  |  | Equipment rental
Early indications are that there will be a sufficient number of subcontractors available within the region
to meet the majority of subcontracting needs. It is expected that subcontracts will be competitively
awarded based on price and capabilities.
The | SWB | Team | is | particularly | sensitive | to | contracting | with | minority | and | women-owned | firms. | To
broaden the level of participation of these firms, SWB will conduct workshops and provide written
notice to all known minority and women-owned firms that specialize in the work that SWB will be
subcontracting. Drawings and specifications will be available to all minority and women-owned firms
that express an interest in bidding opportunities. SWB will negotiate in good faith with all potential
subcontractors.
THI7RD | HAMPTON ROADS CROSSING | [11 empty] | 7
CONCEPTUAL PROPOSAL

## Page 18
Name: “Table 1 of 1 on page 18 of 80”
Table: 16
[5 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . b | Ex pe r i e nc e
Describe the experience of each firm and the key principals involved in the proposed project.
Describe the length of time in business, business experience, public sector experience and other
engagements of the firm(s). |  |  | The lead organization must be identified.
Team Experience
Skanska USA, Inc. (Skanska), Washington Group International (Washington), and Royal BAM Group
nv (BAM) have formed the joint venture Skanska/Washington/BAM (SWB). SWB has been formed to
undertake the development, financing, design, construction, operation and maintenance of the Third
Hampton | Roads | Crossing. | The | SWB | lead | organization | and | the | managing | joint | venture | partner | is
Skanska. | Skanska’s wholly owned subsidiary, Tidewater Skanska, Inc. will be the operating manager.
` | Skanska AB (Sweden) founded 1887
Skanska USA founded 1971
Tidewater Skanska, Inc. founded in 1932 as heritage company Tidewater Construction Corporation
` | Washington Group International founded 1912 as heritage company Morrison Knudsen
` Royal BAM Group nv (Netherlands) founded in 1869
Flatiron Construction Corp. established in the United States in 1970
Interbeton established in the United States in 1986
The SWB Team firms are international leaders of the construction industry, and have successfully built
thousands of projects for both the public and private sectors. Their reputations and experience have
earned them financial stability and unsurpassed capabilities that are crucial to the development of the
Third Hampton Roads Crossing.
SWB was formed to bring together the country’s premier companies with experience in the design and
construction | of | complex | bridges | and | tunnels. | SWB | selected | the | most | experienced | engineering | and
design team in the world, Parsons Brinckerhoff Quade & Douglas, Inc. (PB) and Jacobs Civil, Inc.
(Jacobs), for this type of facility. |  |  |  | These companies, which together with Goldman Sachs as financial
advisor, collectively compose the SWB Team, have long-standing working relationships. The team’s
capabilities are ideally suited to solve the pressing need for a Third Hampton Roads Crossing.
The operating companies of the three joint venture members will self perform a substantial amount of the
construction. Tidewater, Washington, and Flatiron have the demonstrated experience and capability to
develop the Third Hampton Roads Crossing. These firms have consistently proven their capability to
accomplish difficult projects within time and budget constraints.
Table 1.2, Representative Submerged Tunnel Projects, provides a list of similar facilities that have been
designed and/or constructed by SWB Team members. This table illustrates the depth of the teaming
experience on similar projects, and also clearly indicates that one or more of the SWB Team member
firms have designed or built all of the bridge-tunnels in the Hampton Roads area.
THI8RD | HAMPTON ROADS CROSSING | [11 empty] | 8
CONCEPTUAL PROPOSAL

## Page 19
Name: “Table 1 of 1 on page 19 of 80”
Table: 17
|  | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[5 empty] | 1 . b | Ex pe r i e nc e
Table 1.2 Representative Submerged Tunnel Projects
Year
Tunnel |  | Skanska | Washington | BAM | PB | Jacobs
Completed
Hampton Roads Area
Hampton Roads Bridge | 1957 |  |  |  | 
Tunnel #1
Hampton Roads Bridge | 1976 |  |  |  | 
Tunnel #2
Monitor Merrimac | 1992 |  |  |  |  | 
Memorial Bridge Tunnel
Downtown | 1952 |  |  |  | 
Tunnel #1
Downtown | 1988 |  |  |  | 
Tunnel #2
Midtown Tunnel #1 | 1962 |  |  |  | 
Chesapeake Bay Bridge | 1964 |  |  |  |  | 
Tunnel #1
Other Locations
Ft. McHenry Tunnel | 1986 |  |  |  |  | 
Ted Williams Tunnel | 1995 |  |  |  |  | 
BART Tunnel | 1966 |  |  |  | 
Tunnel de Noord, | 1992 |  |  | 
Netherlands
Willemspoor Tunnel | 1994 |  |  | 
Netherlands
Alphen aan den Rijn, | 1997 |  |  | 
Netherlands
Conway Tunnel, Wales | 1991 |  |  | 
Medway Tunnel, UK | 1995 |  |  | 
THI9RD | HAMPTON ROADS CROSSING |  |  |  |  | 9
CONCEPTUAL PROPOSAL

## Page 20
Name: “Table 1 of 1 on page 20 of 80”
Table: 18
[6 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . b | Ex pe r i e nc e
Firm Experience
` | Tidewater | Skanska, |  | Inc. | (Tidewater) |  | of | Norfolk, | Virginia, | is | a | wholly-owned | subsidiary | of
Skanska USA which is owned by Skanska AB. Skanska has over $5 billion in assets, employing in
excess of 60,000 people in over 50 countries. Total sales in 2004 were approximately $14 billion, of
which 85 percent was construction. Skanska USA was established in 1971 and recorded 2003 sales of
over $5.6 billion. |  | Skanska USA is the sixth largest U.S. construction contractor. Tidewater is a wholly-
owned subsidiary of Skanska USA and will act as the lead organization in executing the design-build
delivery approach for this project. |  |  |  |  | Skanska’s representative projects include:
 | Chesapeake Bay Bridge Tunnel, VA | [10 empty] | $200M
 | Hampton Roads Bridge Tunnel, VA | [10 empty] | $48M
 | Oresund Link: Sweden-Denmark Bridge Tunnels | [10 empty] | $758M
 | Bart Submerged Tunnel, San Francisco, CA | [10 empty] | $180M
 | Coleman Bridge, Yorktown, VA | [10 empty] | $73M
 | Berkley Bridge, Norfolk, VA | [10 empty] | $75M
 | BART Extension to San Francisco Airport, CA | [10 empty] | $526M
 | Light Rail (Air Train) at JFK Airport, NY | [9 empty] | $1300M
 | Richmond - San Rafael Bridge, CA | [10 empty] | $485M
 | Ft. McHenry Tunnel, Baltimore, MD | [10 empty] | $850M
 | Woodrow Wilson Bridge, Alexandria, VA | [10 empty] | $130M
 | Pinners Point Interchange, Portsmouth, VA | [10 empty] | $145M
 | Cooper River Bridge, Charleston, SC | [10 empty] | $550M
 | I-495/US 1 Interchange, Alexandria, VA | [10 empty] | $147M
` | Washington Group International (Washington) is headquartered in Boise, Idaho, and has a history
dating back to 1912 with the founding of its heritage company, Morrison Knudsen. Today, Washington is
an international engineering, construction, and construction management company offering public and
private | clients | a | full | range | of | services—engineering, |  |  | self-performed |  |  | construction, |  | construction
management, program management, operations and maintenance, and development programs—through
six | operating | units: | Infrastructure, |  |  | Power, | Energy | and | Environment, |  | Defense, | Industrial/Process, |  | and
Mining. With annual revenues exceeding $3 billion, Washington has approximately 27,000 employees at
work in 40 states and more than 30 countries. | [6 empty] | Washington’s representative transportation projects include:
 | Monitor Merrimac Memorial Bridge Tunnel, Hampton Roads, VA | [10 empty] | $138M
 | Ted Williams submerged tunnel, MA | [10 empty] | $251M
 | I-15 Corridor Reconstruction, UT | [9 empty] | $1380M
 | E-470 Toll Road Design-Build, CO | [10 empty] | $568M
 | Route 895 Pocahontas Parkway, VA | [10 empty] | $322M
 | Hudson-Bergen Light Rail System, NJ | [9 empty] | $1670M
` | Flatiron Construction Corp. (Flatiron) is a wholly owned subsidiary of Royal BAM Group nv
(BAM), which was founded in 1869 and currently employs over 30,000 people. | [12 empty] | BAM has over $8
billion in annual sales. Flatiron will be the operating company for BAM in executing this project. In
addition to having constructed over 50 submerged tunnels and highways in Europe, BAM’s recent U.S.
projects include:
THI1R0D HAMPTON ROADS CROSSING | [13 empty] | 10
CONCEPTUAL PROPOSAL

## Page 21
Name: “Table 1 of 1 on page 21 of 80”
Table: 19
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[16 empty] | 1 . b | Ex pe r i e nc e
 | Chesapeake Bay Bridge Tunnel Parallel Crossing | [12 empty] | $220M
 | Ted Williams submerged Tunnel, Boston, MA | [12 empty] | $251M
 | Eastern Transportation Corridor, Orange County, CA | [12 empty] | $772M
 | Carolina Bays Parkway, Myrtle Beach, SC | [12 empty] | $240M
 | Monitor Merrimac Memorial Bridge Tunnel, Hampton Roads, VA | [12 empty] | $138M
 | Cooper River Bridge, Charleston, SC | [12 empty] | $550M
` | Parsons | Brinckerhoff |  |  | Quade | & | Douglas, |  | Inc. | (PB) | and | Jacobs | Civil, |  | Inc. | (Jacobs) | have | been
selected | to | serve | as | the | engineer-of-record |  |  | based |  | on | the | firms’ | experience |  | gained | by | successfully
engineering |  | similar | projects |  | and | their | working |  | relationships |  |  | with | the | operating |  | companies. | PB | was
founded in 1885 and currently employs 9,000 people in 250 offices worldwide. Their portfolio includes
the completion of 40 submerged tunnel projects. For 86 years, Jacobs has participated in and has a proven
track record in the planning, design, and construction supervision of tunnels, shafts and major underground
transportation projects within the USA. Jacobs has 27,000 employees worldwide. This project will be built
on a develop-finance-design-build-operate and maintain basis, a delivery approach that is familiar to both
firms. | PB’s and Jacob’s representative projects include:
 | Fort McHenry Tunnel, Baltimore, MD | [12 empty] | $850M
 | Monitor Merrimac Memorial Bridge Tunnel, Hampton Roads, VA | [12 empty] | $138M
 | Ted Williams Submerged Tunnel, Boston, MA | [12 empty] | $251M
 | Chesapeake Bay Bridge Tunnel, VA | [12 empty] | $260M
 | Second Downtown Elizabeth River Tunnel, Norfolk, VA | [12 empty] | $300M
 | Coleman Bridge, Yorktown, VA | [12 empty] | $73M
 | Cooper River Bridge, Charleston, SC | [12 empty] | $550M
Key Project Personnel
 | David J. Eastwood, PE – Senior Vice President of Skanska USA; Chairman and CEO of Tidewater
| Skanska, Inc. |  | David Eastwood has 37 years of construction and 23 years in executive management
experience. He has been involved in all types of heavy construction in the United States, Britain, the
Middle-East and Hong Kong.
 | Edwin | W. | McLaughlin, |  | PE | – | President |  | of | Tidewater |  | Skanska, |  | Inc. | Ed | McLaughlin |  | has
responsibility for operations and performance on this project. He has 45 years of diversified design
and construction experience with focus on marine construction and bridges for the past 19 years.
 | Francis X. Watson, PE – Project Director for Tidewater Skanska, Inc. | [12 empty] | Francis (Buddy) Watson is
responsible for managing the project team for the SWB joint venture. He has 39 years of diversified
| hands-on | experience |  |  | managing |  | design, |  | construction, |  |  | contracting |  | operations |  | and | facilities
maintenance.
 | Frank Finlayson – Senior Vice President, Project Development, Washington Group International.
Frank Finlayson has 19 years of project financing experience, specializing in the management of
private-sector financing efforts for public/private partnerships in infrastructure-related markets. He is
responsible for directing all financing and business-related activities in negotiations with the public
| sector | and | private | debt | markets. |  | He | also | works |  | with | state | and | local | government |  | officials | to
implement public-sector requirements with that of the private sector.
THI1R1D HAMPTON ROADS CROSSING | [17 empty] | 11
CONCEPTUAL PROPOSAL

## Page 22
Name: “Table 1 of 1 on page 22 of 80”
Table: 20
[5 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . b | Ex pe r i e nc e
 | Rich Linford – Senior Vice President, Design-Build Operations, Washington Group International.
Richard Linford has 29 years of experience in the construction industry with expertise in project
management and operations. He has extensive experience managing complex design-build highway
projects and interfacing with government agencies, the public, and other project stakeholders.
 | Dirk Langerbroek – Managing Director of Interbeton. | [6 empty] | Dirk Langerbroek has over 30 years of
engineering and construction experience.
 | Geoff D. Collins – Executive Vice President, Interbeton, Inc. | [7 empty] | Geoff Collins has over 33 years of
| engineering | and | construction |  | experience | including |  | serving | as | the | Chief | Engineer |  | for | the | Ted
Williams Tunnel in Boston.
 | William D. Smith, PE – President of Parsons Brinckerhoff Quade & Douglas, Inc. | [12 empty] | Bill Smith has
| 39 years of experience in engineering and design management. | [7 empty] | He joined PB in 1988 after serving
in various positions for global consulting firms.
 | William Allen, PE – Senior Vice President, Transportation Group, Jacobs Civil, Inc. | [12 empty] | Bill Allen has
over 30 years of engineering and design experience related to all types of facilities. He has extensive
experience in privatization and design-build approaches to complete transportation facilities.
The | projects | described | on | the | following | pages | are | representative |  | of | the | depth | of | experience |  | and
capability that the SWB Team members bring to the Third Hampton Roads Crossing. These projects
demonstrate a strong performance record and depth of our teaming experience. References are provided
for each project.
THI1R2D HAMPTON ROADS CROSSING | [15 empty] | 12
CONCEPTUAL PROPOSAL

## Page 23
Name: “Table 1 of 1 on page 23 of 80”
Table: 21
[8 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . b | Ex pe r i e nc e
GEORGE P. COLEMAN BRIDGE REPLACEMENT
Yorktown, Virginia
This double-leaf swing span over the York River is the | [9 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
second longest in the world. Although procured by VDOT | [9 empty] | RESPONSIBLE:
under traditional design-bid-build procedures, Tidewater | [9 empty] | Tidewater scope of work included project management,
Skanska, | Inc. | (Tidewater) |  |  | managed |  | a | significant |  | quality assurance, redesign of truss and shoring systems,
engineering effort that allowed for construction of six 77- | [9 empty] | bridge construction, and electronic toll collection system.
foot-wide bridge spans, complete with barriers, lighting, | [9 empty] | Parsons Brinkerhoff was the project designer.
signs, and highway markings to be prefabricated 30 miles
downstream in the Hampton Roads. | [9 empty] | PROJECT COST:
$73 million
In May 1996 during a 12-day scheduled bridge closure, the
existing bridge spans were lifted and removed by barges | [9 empty] | COMPLETE DATE:
utilizing an elaborate pumping system and replaced with | [9 empty] | August 1996
the new wider bridge spans. Within nine days, the Coleman
Bridge | was | open | to | the | public, | three | days | ahead | of | REFERENCE:
schedule. | The | project |  | received | six | construction/design |  |  |  | Virginia Department of Transportation
awards for this major accomplishment and was featured on | [9 empty] | George Clendenin, State Structure and Bridge Engineer
the July 8, 1996 ENR cover. | [9 empty] | 1401 E. Broad Street
[10 empty] | Richmond, VA | 23219
(804) 786-2714
THI1R3D HAMPTON ROADS CROSSING | [11 empty] | 13
CONCEPTUAL PROPOSAL

## Page 24
Name: “Table 1 of 1 on page 24 of 80”
Table: 22
[11 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[17 empty] | 1 . b | Ex pe r i e nc e
CAROLINA BAYS PARKWAY
Myrtle Beach, South Carolina
The Carolina Bays Parkway is a design-build project that | [12 empty] | Extensive use was made of contractors and suppliers in
connects SC Route 9 to US Route 501 in Horry County. | [12 empty] | the Myrtle Beach area.
The Parkway involves 22 miles of limited access divided
highway | with |  | 26 | bridges |  |  | including |  |  | one | over | the | ACTIVITIES FOR WHICH THE FIRM IS
Intracoastal Waterway. | [12 empty] | RESPONSIBLE:
Flatiron Structures Co., a wholly owned subsidiary of Royal
This unusual procurement required proposers to provide | [12 empty] | BAM | Group, | and | Tidewater | Skanska, | Inc. | formed | the
the | maximum |  | amount |  | of | scope | for |  | a | fixed | budget. |  | Palmetto Transportation Constructors, and were awarded this
Palmetto | Transportation Constructors not only provided | [11 empty] | design-build project.
all the scope on the SCDOT's’ list, but offered additional
scope | items | to | enhance |  | the |  | entire | area |  | transportation |  |  | PROJECT COST:
system. | [12 empty] | $254 million including exercised options
A significant amount of right-of-way is being procured by | [12 empty] | COMPLETION DATE:
the | design/build |  | contractor |  |  | as | well | as | by | SCDOT. |  | The | 2002
contractor is responsible for managing the entire process.
The | contractor |  | is | also | managing |  | relocation |  |  | of | existing |  | REFERENCE:
utilities. | [12 empty] | South Carolina DOT
ATTN: Berry Still, Project Manager
Protection | of | the |  | fragile | low |  | country |  | environment |  |  | was | P. O. Box 191
given a high priority. Design and construction were fast | [12 empty] | Columbia, SC |  | 29201
tracked | with | an | overall |  | schedule |  | of | 30 |  | months. | Some |  | (803) 737-9967
sections were completed early and turned over to SCDOT
and the motoring public.
THI1R4D HAMPTON ROADS CROSSING | [19 empty] | 14
CONCEPTUAL PROPOSAL

## Page 25
Name: “Table 1 of 1 on page 25 of 80”
Table: 23
[9 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[19 empty] | 1 . b | Ex pe r i e nc e
PARALLEL CROSSING – CHESAPEAKE BAY BRIDGE TUNNEL
Cape Charles, Virginia
Interbeton |  | and | Jacobs | (Sverdrup) |  | were | both |  | involved |  | in | In | the | 1960s, | Jacobs |  | provided | planning, |  | design | and
this parallel crossing of the Chesapeake Bay consisting of | [11 empty] | construction |  |  | management |  | services | for | the | first | crossing.
12 | miles | of | low-level | trestle |  | over | the | mouth |  | of | the | Jacobs provided comprehensive construction management
Chesapeake Bay, a high-level bridge across the northern | [11 empty] | services |  | for | the | total | 17.5 | mile-long | crossing |  | which
navigation channel, as well as 3 miles of on-shore highway | [11 empty] | includes |  | the | 12 | miles | of | precast, | prestressed |  | concrete
work. | The | parallel | crossing |  | required |  | over | 2000 |  | precast, |  | trestle, along with four man-made islands in open water,
prestressed, |  | concrete | cylindrical |  |  | piles, | over |  | 600 | precast, |  | two | sunken |  | tube | tunnels, | two | high-level |  | bridges, | and | a
reinforced |  | concrete | pile |  | caps | and | over | 2000 |  | precast, |  | 8,319 foot causeway. In 1995, Sverdrup provided similar
prestressed |  | double | “T” | deck | units. |  | Most | of | this | precast |  | services for the parallel bridge crossing.
concrete | was |  | manufactured |  | at | a | purpose-built |  |  | on-site
facility. The contract included refurbishment of the original | [11 empty] | PROJECT COST:
crossing and all the work was completed in four years per | [11 empty] | $220 million
the original contract.
COMPLETION DATE:
ACTIVITIES FOR WHICH THE FIRMS WERE | [11 empty] | July 1999
RESPONSIBLE:
Interbeton was part of a construction joint venture to build | [11 empty] | REFERENCE:
the | parallel | crossing |  | of | the | Chesapeake |  | Bay |  | Bridge. |  | Chesapeake Bay Bridge Tunnel District
Interbeton set up and ran the precast yard, drove piles, and | [11 empty] | Attn: Paul Burnette, Jr.Chief Engineer
erected | precast |  | concrete |  | deck | units. | Interbeton |  |  | also |  | 32386 Lankford Highway
installed | electrical |  | and | electronic |  |  | services |  | as | well | as | Cape Charles, VA 23310
performed |  | partial | demolition |  |  | and | refurbishment |  |  | of | the | (757) 331-2960
existing bridge.
THI1R5D HAMPTON ROADS CROSSING | [21 empty] | 15
CONCEPTUAL PROPOSAL

## Page 26
Name: “Table 1 of 1 on page 26 of 80”
Table: 24
[11 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[15 empty] | 1 . b | Ex pe r i e nc e
“TED WILLIAMS” BOSTON HARBOR TUNNEL
Boston, Massachusetts
A | Washington |  | Group-led |  |  | joint | venture |  | with | Interbeton |  |  |  | ACTIVITIES FOR WHICH THE FIRMS WERE
constructed |  | twin-tubes |  |  | highway |  | tunnels |  | beneath |  |  | Boston |  | RESPONSIBLE:
harbor | between |  | Logan |  | Airport |  | and | South |  | Boston. |  | This |  | Washington Group and Interbeton were responsible for all
$251 | million, |  | 3,850-foot-long |  |  |  | immersed |  |  | tube |  | tunnel |  | construction work. PB prepared concept designs and served
consisted | of | 12 | sections |  | of | double-tube |  |  | (binocular) |  |  | steel |  | as GEC to the Turnpike Authority
concrete | lined |  | segments |  |  | that | were | placed |  | in | a | harbor
bottom trench.
PROJECT COST:
$251 million
The | tube | segments |  | were |  | fabricated |  | at | Sparrows |  |  | Point,
Maryland, |  | where |  | they | were |  | lined | and | weighted |  |  | with
COMPLETE DATE:
concrete and sealed with bulkheads. The segments were
1994
then | loaded | on | a | submersible |  |  | barge | and |  | towed |  | to | the
Boston Inner harbor. After removal from the barge, each
REFERENCE:
segment was placed in a 90-foot-wide trench dredged to a
Massachusetts Turnpike Authority
minimum |  | depth |  | of | 95 | feet | at | mean |  | low |  | water.
Joseph J. Allegro
Approximately, |  |  | 1,057,000 |  |  | cubic | yards |  | of | material |  | was
10 Park Plaza
dredged from the harbor bottom. After tube placement, the
[14 empty] | Boston, MA | 02116
trench was backfilled with a minimum of 5 feet of cover.
(617) 342-1226
THI1R6D HAMPTON ROADS CROSSING | [15 empty] | 16
CONCEPTUAL PROPOSAL

## Page 27
Name: “Table 1 of 1 on page 27 of 80”
Table: 25
[10 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
EASTERN TRANSPORTATION CORRIDOR
Orange County, California
The | Eastern | Transportation |  |  | Corridor |  | (ETC) |  | is | a | 40-km | ACTIVITIES FOR WHICH THE FIRM IS
four/six | lane | new |  | limited | access |  | toll | road | in |  | Orange | RESPONSIBLE:
County, | California. |  |  | The | owner | is | the | Foothill/Eastern |  |  |  | Flatiron led a joint venture to design and build the Eastern
Transportation Corridor Agency (TCA), a California Joint | [11 empty] | Transportation | Corridor. | Additionally, | the | joint | venture
Power | Agency. |  | The | ETC | facility |  | includes |  | four |  | fully | was responsible for all toll equipment. Quality assurance
directional |  | interchanges, |  |  | a | sophisticated |  |  |  |  | traffic | and quality control were provided by the contractor for
management system, and a state-of-the-art toll collection | [11 empty] | the entire project.
and | violation | enforcement |  |  | system, |  | including |  | full-speed
electronic toll collection. The project was approved under | [11 empty] | PROJECT COST:
the | Federal |  | Highway |  | Administration’s | [5 empty] | Special | $801 million
Experimental Project (SEP-14) as a design-build project.
COMPLETION DATE:
The project included four fully directional interchanges, | [11 empty] | February 1999 (14 months ahead of schedule)
69 bridges, placement of 1.3 million tons of asphalt and
moving 67 million cubic yards of earth and rock. | [11 empty] | REFERENCE:
Foothill Eastern Transportation Corridor Agency
The | project | was | financed |  | with | private |  | capital |  |  | raised | Gary H. Steinke
through $1.4 billion in tax-exempt bonds issued by the | [11 empty] | 201 E. Sandpointe, Suite 200
TCA. The bonds were placed in approximately one hour, | [11 empty] | Santa Ana, California | 92707
based | in | part | on | the | fixed | price |  | and | guaranteed |  |  | (949) 513-3437
completion date proved by the construction joint venture.
THI1R7D HAMPTON ROADS CROSSING | [16 empty] | 17
CONCEPTUAL PROPOSAL

## Page 28
Name: “Table 1 of 1 on page 28 of 80”
Table: 26
[7 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
MONITOR MERRIMAC MEMORIAL BRIDGE-TUNNEL
Newport News, Virginia
ACTIVITIES FOR WHICH THE FIRMS WERE
The Washington Group-led joint venture with Interbeton
RESPONSIBLE:
Inc. | constructed | the | submerged |  | tube | tunnel | between
SWB Team members were responsible for all phases of
Newport News and Suffolk, Virginia. The $138 million
design and construction.
submerged tube tunnel is 4,500 feet long and consists of
15 sections of double-tube steel segments.
PROJECT COST:
The tube segments were fabricated, lined and weighted | [7 empty] | $138 million
with concrete, sealed with bulkheads at Sparrows Point,
Maryland, then towed to the Hampton Roads site. Each | [7 empty] | COMPLETE DATE:
segment was individually placed in a 90-foot-wide trench | [7 empty] | 1990
dredged to a maximum depth of 120 feet at mean low
water. | After | tube | placement, | the | trench | was | backfilled | REFERENCE:
with a minimum of 5 feet of cover. Sverdrup designed the | [7 empty] | Virginia Department of Transportation
tunnel | and | provided | construction |  | services. |  | Tidewater | Thornhill Snoddy
Skanska, Inc. built the northern approach to the tunnel. | [7 empty] | 1401 E. Broad St.
[8 empty] | Richmond, VA | 23219
(804) 786-2945
THI1R8D HAMPTON ROADS CROSSING | [9 empty] | 18
CONCEPTUAL PROPOSAL

## Page 29
Name: “Table 1 of 1 on page 29 of 80”
Table: 27
[9 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
I-95 TOLL CONNECTOR AND VIETNAM VETERANS MEMORIAL BRIDGE
Henrico and Chesterfield Counties, Virginia
The Pocahontas Parkway was the first construction project | [10 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
awarded |  | under | the | Commonwealth |  | of | Virginia’s |  | Public- |  | RESPONSIBLE:
[11 empty] | Washington | Group | developed | financing | on | the | project,
Private Transportation Act of 1995. The 8.8-mile parkway
was a joint venture member, and served as the design-
involved the financing, design, and construction of a four-
[11 empty] | build | contractor. | Parsons | Brinckerhoff | was | responsible
lane | limited-access |  |  | highway | with | major | interchanges |  |  | at
for the design.
Interstate-295 in the east and Interstate-95 in the west. It
also includes a high-level crossing over the James River | [10 empty] | PROJECT COST:
south | of | Richmond, |  | Virginia, |  | providing |  | clearance |  | for | $362 million
ocean-going |  | vessels |  | bound | for | the | Port | of | Richmond.
Besides the nearly 9 miles of four-lane roadway and the | [10 empty] | COMPLETE DATE:
James River Bridge, the project also includes construction | [10 empty] | September 2002
of | three | interchanges, |  | ten | major | overpasses |  |  | and | grade
REFERENCE:
separation structures, and toll collection facilities. | [10 empty] | Virginia Department of Transportation
Jim Fariss, Project Manager
1401 E. Broad St.
[11 empty] | Richmond, VA | 23219
(804) 786-2998
THI1R9D HAMPTON ROADS CROSSING | [16 empty] | 19
CONCEPTUAL PROPOSAL

## Page 30
Name: “Table 1 of 1 on page 30 of 80”
Table: 28
[8 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[16 empty] | 1 . b | Ex pe r i e nc e
INTERSTATE HIGHWAY 15 RECONSTRUCTION
Salt Lake City, Utah
This | project | involved |  | demolishing |  | and | reconstructing |  |  | ACTIVITIES FOR WHICH THE FIRM WAS
approximately 17 miles of Interstate 15 through the heart of | [9 empty] | RESPONSIBLE:
Salt Lake City, Utah. The $1.4 billion contract is Utah’s | [9 empty] | PB | was | the | program | manager | for | Utah | DOT. | PB | was
involved in all pre award activities and was responsible for
largest ever public works project, and at the time was the
[10 empty] | design | and |  | construction | oversight. |  | Washington |  | Group
largest design-build highway project underway anywhere
participated in this project as a design-build joint venture
in the U.S. Work included demolition and reconstruction of
partner responsible for overall project execution and as a
144 bridges, | half | of | which |  | are | steel | girder | and | the | major project designer as part of the design joint venture.
remainder | precast/prestressed |  |  |  | girder | structures |  | carrying
4.5 million square feet of new concrete pavement to build | [9 empty] | PROJECT COST:
four to six lanes of concrete highway in each direction. The | [9 empty] | $1.4 billion
work was conducted under a stringent time schedule for
completion | in | time | for | the | opening | of | the | 2002 | Winter | COMPLETE DATE:
Olympics. | [9 empty] | May 2001
REFERENCE:
Utah Department of Transportation
John Njord, Director
4501 S. 2700 W.
[10 empty] | Salt Lake City, UT |  |  | 84119-5998
[10 empty] | (801) | [6 empty] | 965-4113
THI2R0D HAMPTON ROADS CROSSING | [18 empty] | 20
CONCEPTUAL PROPOSAL

## Page 31
Name: “Table 1 of 1 on page 31 of 80”
Table: 29
[10 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[18 empty] | 1 . b | Ex pe r i e nc e
POPLAR ISLAND RESTORATION PROJECT
Chesapeake Bay, Maryland
In | April | 2000, | Tidewater |  | Skanska, |  | Inc. was |  |  | awarded | a | The project includes spillway structures, stone roadways
$35.6 | million |  | contract | with |  | the | U.S. | Army |  | Corps | of | and subaqueous power and phone lines to the island. This
Engineers |  | for | the | construction |  |  | of | the | Poplar | Island |  | project required approximately 2,000,000 cubic yards of
Wildlife |  | Habitat | Restoration |  |  | project. |  | This |  | project | is | fill and 300,000 tons of stone. The project was awarded
located in the Chesapeake Bay, approximately 11⁄2 miles | [11 empty] | on | a | best | value | procurement | based | on | the | price | and | a
from the closest point of landfall, near Tilghman Island, | [11 empty] | technical proposal.
Maryland.
ACTIVITIES FOR WHICH THE FIRM WAS
Tidewater constructed a system of stone and earthen dikes | [11 empty] | RESPONSIBLE:
to reclaim Poplar Island from erosion and to create cells | [11 empty] | Tidewater was responsible for all construction and quality
that | will | be | filled | with | dredge |  | material |  | taken | from |  | control.
shipping channels in the area. The resulting island was
planted | to | establish |  | upland |  | and | lowland |  | environmental |  |  | PROJECT COST:
habitats for wildlife. | [11 empty] | $40 million
The work included building approximately 21,500 LF (4 | [11 empty] | COMPLETE DATE:
miles) of stone and earthen dikes. Stone berms were first | [11 empty] | December 2001
constructed along the toe of the proposed dikes. Material
was dredged from the bottom of the bay and pumped into | [11 empty] | REFERENCE:
a | specially | prepared |  | containment |  |  | area. |  | The | sand | was | Scott Johnson
loaded | to | trucks, | then | placed |  | and | shaped |  | to | form | the | U. S. Army Corps of Engineers
dikes. | External |  | faces | of | the | earthen |  | slopes | are | covered |  | Baltimore District Corps of Engineers
with | multiple |  | layers | of | graded |  | stone | to | prevent | future |  | P. O. Box 1715
erosion. | [11 empty] | Baltimore, MD |  |  | 21203-1715
(410) 962-6030
THI2R1D HAMPTON ROADS CROSSING | [21 empty] | 21
CONCEPTUAL PROPOSAL

## Page 32
Name: “Table 1 of 1 on page 32 of 80”
Table: 30
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
MASSACHUSETTS AVENUE INTERCHANGE
Boston, Massachusetts
A | joint | venture | including | Interbeton |  | and | Skanska | was | ACTIVITIES FOR WHICH THE FIRMS WERE
awarded the C 12A3 contract, which was located at the | [8 empty] | RESPONSIBLE:
southern most end of the Central Artery/Tunnel project. | [8 empty] | Interbeton, Skanska, and their joint venture partner were
The major challenge on this job was to work over, around, | [8 empty] | responsible for all construction work. PB provided GEC
and | through | the | major | highway | that | carries | traffic | into
services to the owner.
downtown |  | Boston | without | interrupting |  | traffic. | Work
preparation and traffic management played a critical role
PROJECT COST:
in the execution of the project. The project consisted of:
$200 million
 | Construction of 18 new bridges (totaling 2.3 miles)
| consisting of 220 steel tub girders, 216 precast | [7 empty] | COMPLETE DATE:
| I-beams and 42 precast post tension concrete box | [7 empty] | July 2001
beams.
 | In total, 102,000 CY of concrete was poured | [7 empty] | REFERENCE:
 | Construction of 4.6 miles of at-grade roads | [7 empty] | Massachusetts Highway Department
 | Construction of two storm water pump stations | [7 empty] | Paul Dye
C/O Bechtel Parsons Brinckerhoff
185 Kneeland Street
Boston, MA 02127
THI2R2D HAMPTON ROADS CROSSING | [9 empty] | 22
CONCEPTUAL PROPOSAL

## Page 33
Name: “Table 1 of 1 on page 33 of 80”
Table: 31
[8 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
NEW CARQUINEZ BRIDGE
Crockett, California
As part of a joint venture, Interbeton Inc. constructed this | [8 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
new | suspension |  | bridge | across | the | Carquinez |  | Strait | RESPONSIBLE:
navigation |  | channel. | The | joint | venture | members |  | include | Interbeton, Flatiron and their joint venture partner were
two | sister | companies, |  | FCI | Constructors |  | North | and | responsible for all construction work.
Flatiron Structures Company.
PROJECT COST:
The new Carquinez structure is the third bridge at this site | [8 empty] | $231 million
and replaces the existing bridge, built in 1927, and carries
traffic westbound on I-80. The bridge built in 1958 was | [8 empty] | COMPLETE DATE:
seismically |  | retrofitted | and | carries | I-80 | traffic | eastbound. |  | 2003
The | three-span, | 3,465-foot-long |  |  | structure | is | the | nation’s
first new major suspension bridge built in 35 years. The | [8 empty] | REFERENCE:
bridge features two 400-foot concrete towers, supported by | [8 empty] | Caltrans
driven | piles. | The | new | 82-foot-wide | deck | accommodates |  |  | Kenneth Loncharich
four | vehicle | lanes |  | (including | one | HOV | lane), | a | C/O Caltrans Toll Bridge Program
bicycle/pedestrian lane, and wide shoulders. | [8 empty] | Hilltop Construction Field Office
3045 Research Drive
Richmond, CA
(510) 262-6808
THI2R3D HAMPTON ROADS CROSSING | [9 empty] | 23
CONCEPTUAL PROPOSAL

## Page 34
Name: “Table 1 of 1 on page 34 of 80”
Table: 32
[8 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
SOUTH BOSTON INTERCHANGE
Boston, Massachusetts
The South Boston Interchange (Contract C01A6) is part | [10 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
of the Boston Central Artery / Tunnel Project executed by | [10 empty] | RESPONSIBLE:
the | Massachusetts |  | Highway | Department. |  |  | The | project |  | is | Interbeton Inc. and Flatiron were responsible for the cast-
located | in | South | Boston | and | is | part | of | the | I-90 |  | in-place tunnel sections, design and construction of earth
Massachusetts Turnpike extension to Logan Airport. | [10 empty] | retaining | structures, | temporary | bridges, | and | dewatering
systems. PB provided GEC services for the owner.
This contract borders two other Central Artery / Tunnel
contracts. | The | work | included | the |  | construction |  |  | of | a | PROJECT COST:
reinforced | cut-and-cover |  | tunnel | with |  | a | length | of | 1,250 |  | $225 million
feet, a width varying between 280 and 330 feet, and an
excavation depth of approximately 50 feet. | [10 empty] | COMPLETE DATE:
2002
REFERENCE:
Massachusetts Highway Department
Chester Choy-Hee
C/O Bechtel / Parsons Brinckerhoff
273 Summer Street
[11 empty] | Boston, MA | 02111
THI2R4D HAMPTON ROADS CROSSING | [15 empty] | 24
CONCEPTUAL PROPOSAL

## Page 35
Name: “Table 1 of 1 on page 35 of 80”
Table: 33
[8 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[18 empty] | 1 . b | Ex pe r i e nc e
I-93 / I-90 INTERCHANGE
Boston, Massachusetts
Interbeton, | together |  | with |  | Slattery | Skanska, | a | Skanska |  | ACTIVITIES FOR WHICH THE FIRM WAS
subsidiary, | as | part | of | a | joint | venture, | constructed |  | this | RESPONSIBLE:
project located at the intersection of I-93 and the eastern | [9 empty] | Interbeton |  | and |  | Slattery | Skanska, |  | in | joint | venture, | were
terminus of the Massachusetts Turnpike (I-90). It is the | [9 empty] | responsible for fabrication and construction of 10,000 feet
largest | construction |  | contract |  |  | ever | awarded | by | the | of pre-cast, post-tensioned viaduct; construction of three
Massachusetts Turnpike Authority. The joint venture used | [9 empty] | jack-box tunnels with similar cross sections (80 feet wide
jacked-boxed tunnels under the active Amtrak rail lines at | [9 empty] | by | 40 | feet | high | by | 167, | 258 | and | 379 | linear | feet);
South Station; this method is the only means to construct | [9 empty] | construction |  |  | of | 3,000 | feet | of | cut-and-cover |  | tunnel, | and
tunnels under the tracks without interrupting rail service. | [9 empty] | 3,700 feet of cast-in-place boat section. PB provided GEC
The Project was completed in 2003. | [9 empty] | services for the owner
Interbeton was awarded the National Value Engineering | [9 empty] | PROJECT COST:
Award | for | best | technical |  | value | engineering |  | change |  | $420 M
proposal to Big Dig Contracts and was the Grand Award
Winner of ACEC's 2000 Engineering Excellence Award, | [9 empty] | COMPLETE DATE:
amongst various other national and international awards. | [9 empty] | 2003
REFERENCE:
Massachusetts Highway Department
Philip Rice
C/O Bechtel / Parsons Brinckerhoff
210 South Street
[10 empty] | Boston, MA |  |  | 02110
THI2R5D HAMPTON ROADS CROSSING | [19 empty] | 25
CONCEPTUAL PROPOSAL

## Page 36
Name: “Table 1 of 1 on page 36 of 80”
Table: 34
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
BAY AREA RAPID TRANSIT – TRANS-BAY TUBE
San Francisco, California
In 1966 Tidewater Skanska, Inc. and their joint venture | [8 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
Partners | were | awarded | the | $180 | M | contract | for | the | RESPONSIBLE:
construction | of | a | submerged | tunnel |  | between |  | San | The Tidewater Skanska Joint Venture was responsible for
Francisco | and | Oakland, | CA. | The |  | project | involved |  | all construction between the Oakland and San Francisco
fabrication, dredging, placement, and finishes for a 3.6- | [8 empty] | tunnel portals. Parsons Brinckerhoff was the lead project
mile-long | tunnel | having | a | 48-foot | by | 24-foot | cross |  | designer.
section. The tunnel was placed in depths up to 135 feet
below the water surface. The facility is in use to provide | [8 empty] | PROJECT COST:
commuter rail services. The project was built to stringent | [8 empty] | $180 million
seismic requirements. Parsons Brinckerhoff led the joint
venture for design and construction management for the | [8 empty] | COMPLETE DATE:
Trans-Bay Tube. | [8 empty] | 1970
REFERENCE:
Bay Area Rapid Transit Authority
THI2R6D HAMPTON ROADS CROSSING | [9 empty] | 26
CONCEPTUAL PROPOSAL

## Page 37
Name: “Table 1 of 1 on page 37 of 80”
Table: 35
[11 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[20 empty] | 1 . b | Ex pe r i e nc e
E-470 TOLL ROAD DESIGN-BUILD PROJECT
Denver, Colorado
Washington Group’s involvement with the E-470 project
began | in | 1991. |  | The | E-470 |  | Public | Highway |  |  | Authority
contracted |  | with |  |  | Washington |  |  | Group | to | create |  | and
implement a comprehensive development plan to finance,
design, and build Segments II and III of the E-470 project.
Working |  | closely |  | with | the | Authority, |  |  | Washington |  |  | Group
designed a multi-tiered financing structure and conducted
environmental, |  |  |  | socioeconomic, |  |  | and | logistical |  |  | studies | to
support the plan. Washington Group acted as the owner’s
agent to assist in arranging the financing, which consisted
of long-term toll revenue bonds. The financing was secured
solely through toll revenues and vehicle registration fees.
The | financing |  |  | raised | for |  | the | facility |  | amounted |  | to
$658,829,600. | [12 empty] | In January 2000, after a competitive bid process, a second
[13 empty] | Washington |  |  | Group-led |  | joint | venture | began |  | work | on
Segment IV under a design-build contract. Segment IV is a
Washington, as sponsor of the Platte River Constructors, | [12 empty] | 12.5-mile, four-lane, controlled-access toll road that skirts
Ltd. | (PlRC) |  | joint |  | venture, |  | performed |  | the | design-build |  |  | the | northern |  | edge | of | the | Denver | metropolitan |  |  | area.
contract |  | for | Segments |  | II | & | III | including |  | transportation |  |  | Washington |  |  | Group-led |  |  | joint | venture |  | provided
planning, |  | preliminary |  |  | engineering, |  |  | financial |  |  | assistance, |  | transportation |  |  | planning, |  | engineering |  | and | design, |  | pre-
final |  | engineering, |  |  | construction, |  |  |  | and | construction |  |  | construction, |  |  | and | procurement |  | and | construction |  | services.
management |  |  | services. |  |  | Washington |  |  | Group |  | (dba | MK | Segment IV includes 7 interchanges, 43 bridges, 1 mainline
Centennial) |  |  | is | the | engineer-of-record |  |  |  |  | for | the | civil | and 8 ramp toll plazas. The roadway crosses various streets,
engineering and design of Segments II & III. Washington | [12 empty] | county roads, and the major transportation arteries of I-76,
Group was instrumental in the redesign of the roadway to | [12 empty] | US | 85, | and | the | BNSF | and | Union | Pacific |  | railroads.
decrease |  | project |  | costs | and enable |  |  | the project to become |  |  |  |  | Wetlands |  | replacement |  |  | was | also | included | in | the | project
financially |  | feasible. |  |  | We | managed |  | an | extensive |  |  | public | scope. Ongoing coordination was maintained with a wide
involvement program and also provided conceptual design, | [12 empty] | spectrum of agencies and local jurisdictions to obtain the
evaluated |  | alternative |  |  |  | alignments, |  |  | performed |  |  | value | necessary permits and approvals for construction. Similar
engineering |  |  | studies, |  | and | developed |  |  | the | toll | revenue |  | extensive |  | coordination |  |  | was | undertaken | with |  | all | utilities
preliminary engineering in support of toll revenue studies. | [12 empty] | companies.
As | the | managing |  | partner/Design-Builder |  |  |  |  | on | Segments |  | II | ACTIVITIES FOR WHICH THE FIRM WAS
and III, Washington Group constructed 12 interchanges and | [12 empty] | RESPONSIBLE:
33 bridges. |  | Washington |  |  |  | Group |  | also | constructed |  |  | three | Washington |  | Group |  | was | the | Joint | Venture | Sponsor |  | and
mainline toll plazas and 16 ramp toll structures. Other work | [12 empty] | provided |  | project |  | development |  |  | assistance, | design, |  | and
included |  | 135 | utility |  | relocations, |  |  | 2.9 | acres | of | wetlands
construction.
creation and mitigation, lighting, signing, and landscaping
as well as design and installation of 60 lanes of electronic
PROJECT COST:
toll | collection |  |  | equipment. |  |  | Washington |  |  | Group |  | self-
$567 million for the two design-build contracts
performed |  | grading, |  |  | drainage |  |  | work, | paving, |  |  | bridge
construction, signage, and emergency services coordination
COMPLETION DATE:
and | managed |  |  | the | subcontracted |  |  | portions |  | of | the | work.
2003
Washington Group also assisted in securing new right-of-
way was for essentially the entire length of the project and
REFERENCE:
managed |  | hazardous |  |  | materials |  |  | encountered |  |  |  | during
E-470 Public Highway Authority
construction. Segments II and III work was completed with
over two million work hours and no lost-time accidents. | [12 empty] | Matt McDole, Segments II & III
The | project |  | received |  | state |  | and | national |  | quality |  | award | (303) 537-3470
recognition for asphalt paving and state and | [12 empty] | Ed Delozier, Executive Director, Segment IV
local recognition for sensitivity to endangered species in | [12 empty] | (303) 537-3470
the corridor, and no litigation or claims.
THI2R7D HAMPTON ROADS CROSSING | [22 empty] | 27
CONCEPTUAL PROPOSAL

## Page 38
Name: “Table 1 of 1 on page 38 of 80”
Table: 36
[11 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[23 empty] | 1 . b | Ex pe r i e nc e
HUDSON-BERGEN LIGHT RAIL TRANSIT PROJECT
Hudson and Bergen Counties, New Jersey
active Hoboken Terminal and Rail Yard to the north; the
[13 empty] | Hudson |  | River |  | to | the | east; |  | the | navigable |  |  | Long |  | Slip
Channel to the south and west. The area was so restrictive
[13 empty] | that | Washington |  |  |  | Group |  | provided |  | a | temporary |  |  | access
[13 empty] | bridge |  | across |  | the | Long |  | Slip |  | Channel |  |  | to | support
construction.
In October 2000 Washington Group was awarded Phase II
[13 empty] | (MOS-2), |  | which |  |  | adds | 6.1 | miles |  | and |  | involves |  | seven
passenger stations including three intermodal stations, four
park-and-ride facilities, a 1,000-foot viaduct, a 4,000-foot
[13 empty] | tunnel, |  | and | the |  | construction |  |  | and | rehabilitation |  |  |  | of | 12
[13 empty] | bridges. |  | Washington |  |  | Group |  |  | has | completed |  |  | the | design,
[13 empty] | plans, | and |  | specifications |  |  |  | for | these |  | two | extensions. |  |  | In
[13 empty] | addition |  | to | managing |  |  | subcontractors |  |  |  | performing |  |  | certain
Washington Group heads 21 st Century Rail Corporation, a | [12 empty] | civil, electrical and tunneling work, Washington Group is
consortium |  | contracted |  |  | to | design, |  | build, | operation |  |  | and | self-performing the civil and architectural work for the light
maintain (DBOM) the $1.8 billion Hudson-Bergen Light | [12 empty] | rail | stations, |  | as | well | as | some |  | of | the | rail | systems |  | work.
Rail | Transit | system. |  |  | The |  | Hudson-Bergen |  |  | Light |  | Rail | Construction |  |  | of | the | southern |  |  | extension |  | is | complete |  |  | and
Transit | System |  | is | unique |  | in | two | ways: | it | was | the | first | Revenue Service began in November 2003. The northern
DBOM | project |  | in | the | United |  |  | States | for | a | "transit" |  | extension |  | is | scheduled |  |  | to | be | complete |  | and |  | in | Revenue
application, and it was the first time such a contract was | [12 empty] | Service by late 2005.
awarded to a single consortium. The project team remains
on schedule since construction began in December 1996 | [12 empty] | ACTIVITIES FOR WHICH THE FIRM IS
and the latest extension, 22nd Street Station, opened two | [12 empty] | RESPONSIBLE:
years | ahead | of | schedule. |  |  | At | completion, |  |  | the | 20.5-mile |  | As | the | DBOM |  | Program |  | Manager |  |  | and | Prime |  | Contractor.
system | will | include |  | 32 | stations, |  |  | six | intermodal |  | transfer |  | Washington Group is responsible for fast-track engineering
sites, | and | six | park-and-right |  |  |  | lots | and | will | serve |  | over | and | design; |  | procurement; |  |  |  | construction |  |  | management; |  |  |  | and
100,000 riders daily. | [12 empty] | startup and commissioning. As the Program Manager and
[13 empty] | prime |  | contractor, |  |  | Washington |  |  |  | Group |  | is | performing
Since its opening in April 2000, Washington Group has | [12 empty] | engineering |  |  | design |  | for |  | bridges, |  | stations, |  |  | the | vehicle
operated | Hudson-Bergen |  |  |  | Light |  | Rail | Transit |  | System |  | and | maintenance |  |  | facility, |  | utilities, |  |  | and | track. |  | In | addition |  | to
maintained |  | the | infrastructure, |  |  |  | rail | system, |  | stations |  | and | managing subcontractors performing certain civil, electrical
facilities. The operation and maintenance of the Light Rail | [12 empty] | and tunneling work, Washington Group is self-performing
Transit System will continue through April 2015. | [12 empty] | the civil and architectural work for the light rail stations, as
[13 empty] | well | as | some |  | of | the | rail | systems |  | work. |  | PB |  | provided
Phase | I, | awarded |  | in | 1996 |  | and | completed |  |  | in | 2002, | engineering services for the owner.
involved fast-track design and construction of the initial
9.5-mile | segment. |  |  | The | first |  | 7.5 | miles | of | the | light | rail | PROJECT COST:
system went into revenue service in the spring of 2000. | [12 empty] | $1.8 billion
This | initial | Minimum |  |  | Operating |  |  |  | Segment |  | (MOS-1)
currently serves 17 stations (five of which are intermodal | [12 empty] | COMPLETION DATE:
transfer | locations), |  |  | rail | and |  | bus | transit, |  | ferries, |  | and | 2005
another | four | stations |  |  | with |  | park | and | ride | facilities. |  | A
maintenance complex was also constructed and includes a | [12 empty] | REFERENCE:
100,000 square foot maintenance shop, a 75,000 square | [12 empty] | Charles Dickerson
foot LRV storage building, and a storage yard. | [12 empty] | Director HBLRTS
New Jersey Transit
The | final | build-out |  | of | MOS-1 |  | involved |  | a | 4,000+ |  | foot | One Penn Plaza
extension of the light rail. Although less than a mile in | [12 empty] | Newark, NJ 07105-2246
length, | this | final |  | portion |  | of | the | route | presented |  |  | many | (973) 491-8480
challenges |  | due | to | the | close |  | proximity |  | of | NJ | Transit's
THI2R8D HAMPTON ROADS CROSSING | [26 empty] | 28
CONCEPTUAL PROPOSAL

## Page 39
Name: “Table 1 of 1 on page 39 of 80”
Table: 37
[10 empty] | TA B 1 : |  |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[14 empty] | 1 . b | Ex pe r i e nc e
REPLACEMENT OF THE COOPER RIVER BRIDGES
Charleston, South Carolina
Skanska USA Civil and Flatiron are joint venture partners | [12 empty] | ACTIVITIES FOR WHICH THE FIRMS ARE
on | the | Replacement |  |  | of | the | Cooper |  | River | Bridges. |  |  | RESPONSIBLE:
Execution |  | for | the | joint | venture |  | is | being | carried |  | out | by | Skanska USA and Flatiron are the joint venture design-
operating |  | companies |  |  | Tidewater |  | Skanska |  | and |  | Flatiron |  | builders; PB is the designer for the project.
Structures. PB is the designer for the joint venture. The
contract is for a design-build project to replace two old | [12 empty] | PROJECT COST:
bridges on US 17 in Charleston County, South Carolina. | [12 empty] | $531 million
The bridge will provide for eight lanes of traffic plus a
pedestrian/bike lane. It will rise 186 feet above the water | [12 empty] | COMPLETION DATE:
and | have | the | longest |  | cable-stayed |  |  | main | span | in | North |  | 2005
America. There will be a major interchange at each end of
the | bridge, |  | resulting | in | a | total | bridge |  | length | of | over | 2 | REFERENCE:
miles. | The |  | main | span | towers |  | are | founded | on | 10 | foot- |  | South Carolina Department of Transportation
diameter drilled shafts surrounded by rock islands. The | [12 empty] | Bobby Clair, Project Director
towers will stand 570 feet above the water. Some of the | [12 empty] | 212 Huger St.
required |  | right-of-way |  |  | is | being | procured |  | by | the | design- |  | Charleston, SC | 29403
build | contractor. |  |  | The |  | contractor |  | is | also | managing |  |  | (843) 534-5004
relocation |  | of | existing |  | utilities. |  | Protection |  | of | the | fragile
low country environment is being given a high priority.
Design |  | and | construction |  |  | is being |  | fast | tracked, with |  |  | the
bridge opening for traffic in 44 months. Extensive use is
being | made |  | of | local | contractors |  |  | and | suppliers |  | in | the
Charleston area.
THI2R9D HAMPTON ROADS CROSSING | [14 empty] | 29
CONCEPTUAL PROPOSAL

## Page 40
Name: “Table 1 of 1 on page 40 of 80”
Table: 38
[9 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . b | Ex pe r i e nc e
WOODROW WILSON BRIDGE FOUNDATIONS
Oxon Hill, Maryland
Tidewater Skanska, a subsidiary of Skanska USA Civil, is | [10 empty] | ACTIVITIES FOR WHICH THE FIRM WAS
leading a joint venture to construct the foundations of the | [10 empty] | RESPONSIBLE:
new Woodrow Wilson Bridges. The award of the $125 | [10 empty] | Tidewater Skanska was the general contractor for
million Bridge Foundation contract on May 17, 2001 for | [10 empty] | foundation construction.
the | new | Woodrow | Wilson |  | Bridge |  | was | the | first | major
contract of the $2.2 billion, eight-year project. The project | [10 empty] | PROJECT COST:
will replace the existing single 6 lane bridge with two 6 | [10 empty] | $125 million
lane bridges to ease the congestion of the I95/I495 main
artery | that | crosses | the |  | Potomac | River. |  | This | fast-track |  | COMPLETION DATE:
contract with a completion date of July 2003 consisted of | [10 empty] | April 2003, three months early
the construction of 17 bridge piers, 11 of which are in the
Potomac River. The construction involved 35 cofferdam | [10 empty] | REFERENCE:
cells and 48-in., 66-in., and 72-in. steel pipe piles ranging | [10 empty] | Maryland State Highway Administration
from 160 to 210 feet long. | [10 empty] | Mr. Paul Gudelski, District Engineer
6009 Oxon Hill Road
The | construction |  | of | the | Bascule | Piers | was |  | particularly |  | Suite 404
demanding |  | based | on | the | requirement |  | of | homogeneous |  |  | Oxon Hill, Maryland 20745
concrete |  | placements |  | in | excess | of | 6,000 | cy | with | tight | (301) 749-8801 ext. 229
temperature control to minimize thermal cracking.
THI3R0D HAMPTON ROADS CROSSING | [11 empty] | 30
CONCEPTUAL PROPOSAL

## Page 41
Name: “Table 1 of 1 on page 41 of 80”
Table: 39
[6 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[13 empty] | 1 . b | Ex pe r i e nc e
PINNERS POINT CONNECTOR
Portsmouth, Virginia
The Pinners Point Connector will provide a new four-lane | [7 empty] | ACTIVITIES FOR WHICH THE FIRM IS
road | and | interchange | from | the | Western | Freeway | (VA- | RESPONSIBLE:
164) | in | Portsmouth, | VA | to | the | Portsmouth | Marine | Tidewater | Skanska | is | the | General | Contractor | for | this
Terminal, Martin Luther King Expressway (VA-58) and | [7 empty] | project.
the Midtown Tunnel. The project will have six bridges
traversing |  | through | residential |  | and | industrial | areas | PROJECT COST:
covering both water and land. The bridges will consist of | [7 empty] | $136 million
concrete piles, drilled shaft foundations, reinforcing steel,
structural |  | steel | beams, | concrete | beams, | concrete | deck, | COMPLETION DATE:
parapets and dredging an access channel for construction | [7 empty] | 2005
of the water bridge.
REFERENCE:
Also included in the project is a new Midtown Tunnel | [7 empty] | Virginia Department of Transportation
Building |  | Complex | and | roadwork |  | consisting | of | Mr. P.D. Gribok, Resident Engineer
excavation, |  | clearing, | grading, |  | paving, | utilities, | wick | Mr. Michael Johnson, Engineering Manager
drains, fence/guardrails, sound walls, electrical, signs and | [7 empty] | 1992 South Military Highway
traffic management system. Construction is scheduled for | [7 empty] | Chesapeake, VA 23320
1,000 days. | [7 empty] | (757) 494-2451
THI3R1D HAMPTON ROADS CROSSING | [14 empty] | 31
CONCEPTUAL PROPOSAL

## Page 42
Name: “Table 1 of 1 on page 42 of 80”
Table: 40
[8 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[9 empty] | 1 . b | Ex pe r i e nc e
ORLANDO-ORANGE COUNTY EXPRESSWAY TOLL O&M
Orlando, Florida
Florida | Toll | Services—a |  | Washington |  |  | Group-led | joint | ACTIVITIES FOR WHICH THE FIRM WAS
venture—under a $123.7 million contract, operates 100- | [8 empty] | RESPONSIBLE:
miles of limited-access toll roads serving customers in the | [8 empty] | Operations and maintenance.
Orlando-Orange |  |  | County | area. | The | road | system | serves
PROJECT COSTS:
featured attractions such as Disney World and the Florida
$123.7 million
Citrus | Bowl. | It | includes | the | East-West |  | Expressway,
Central Florida Greene-Way, the Bee Line Expressway, | [8 empty] | COMPLETE DATE:
and | the | Western | Expressway. |  |  | Washington |  | Group | 2004
established the performance benchmarks for maximizing
revenues, violation enforcement capture, and increasing | [8 empty] | REFERENCE:
customer |  | satisfaction | levels, | as | well | as | designed | and | Michael Snyder, PE, Exec. Dir.
Orlando-Orange County Expressway Authority (OOCEA)
maintained |  | the | measurement | system |  | to | collect | relevant
(407) 316-3800
data. As a result, as the volume of traffic has increased by
92% since the beginning of the contract in 1995, we have
saved the client $2.8 million over the life of the contract,
saved 190,000 man-hours, and customer satisfaction has
increased by 61%.
THI3R2D HAMPTON ROADS CROSSING | [9 empty] | 32
CONCEPTUAL PROPOSAL

## Page 43
Name: “Table 1 of 1 on page 43 of 80”
Table: 41
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . b | Ex pe r i e nc e
Alameda Corridor Transportation Authority |  | ACTIVITIES FOR WHICH THE FIRM WAS
RESPONSIBLE:
Goldman Sachs & Co. was hired in 1992 by the Alameda |  | Senior Manager and Co-Senior Manager
Corridor Transportation Authority (ACTA) to help
develop a finance plan for a $2.2 billion rail corridor to |  | PROJECT COSTS:
link the Ports of Los Angeles and Long Beach to the |  | $2.2 billion
central rail yards in downtown Los Angeles.
Goldman Sachs was hired based on our experience in the |  | REFERENCE:
Port/Railroad community and our experience in helping |  | Alameda Corridor
develop plans of finance for major infrastructure projects |  | Transportation Authority
among other items, we specifically aided the transaction |  | Dean Martin, Chief Financial Officer
in the following ways: |  | One Civic Plaza, Suite 650
Carson, California 90745
1. | Identification of Funding Sources – Goldman Sachs | (310) 233-7480
worked with the Ports, the LACMTA, and the USDOT to |  | (212) 878-7278
identify potential funding sources for the project. In
addition, our modeling work, combined with several
studies from outside consultants also allowed us to create
a set of proposed use fees for each type of cargo traveling
through the corridor to be paid by the railroads.
2. | Developed an extensive cash flow model which
served as the central decision-making tool for the
financing team
3. | Development of Feasible Financing Plan – Key
funding sources include equity contributions from the
two Ports, use fees paid by the railroads and an
innovative federal loan.
4. | Negotiation of Use and Operating Agreement with
Railroads
5. | Assisted in negotiating a federal loan which is being
used as the model for future TIFIA loan financings.
6. | Design/Build Contract – Helped ACTA determine a
project plan that will finish project 22 months ahead
of schedule.
7. | Tax Analysis – Together with tax counsel, Goldman
Sachs helped develop a tax strategy that allowed ACTA
to use a special Private Letter Ruling from the Internal
Revenue Service to sell a substantial portion of the bonds
tax-exempt.
8. | Financing Structure – Achieved investment grade
ratings on both the senior and subordinate lien bonds
9. | Developed an effective marketing plan, resulting in a
very successful financing in which the tax-exempt
bonds were 4 times oversubscribed.
On the pricing date, the tax-exempt bonds were 4 times
oversubscribed.
THI3R3D | HAMPTON ROADS CROSSING |  | 33
CONCEPTUAL PROPOSAL

## Page 44
Name: “Table 1 of 1 on page 44 of 80”
Table: 42
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . b | Ex pe r i e nc e
CITY OF RENO , NEVADA – RETRACT PROJECT |  | contribution package from the Union Pacific Railroad. In
July of 2000, Goldman Sachs took the ReTRAC team to
In October 1997, Goldman Sachs was appointed senior
the U. S. Secretary of Transportation and applied for
manager for the City of Reno on its ReTRAC project.
TIFIA assistance. In December of 2000, ReTRAC was
The City has been attempting for the past 45 years to
awarded a $73.5 million TIFIA loan package as part of
relocate the transcontinental mainline that was owned by
the project’s funding. The final environmental Record of
the Southern Pacific (and now owned by Union Pacific)
Decision (ROD) was issued on February 26, 2001 and the
that runs directly through the heart of the City and within
TIFIA loan package was successfully completed for the
one block of 1,500 hotel rooms. Goldman Sachs was
first funding package in June of 2002. This project is the
appointed to help craft a finance plan for the $250 million
first senior/subordinated use of the TIFIA program, an
public-private partnership to drop the rail line into a 35-
innovative funding initiative created by the USDOT to be
foot deep trench through a 9-intersection corridor. Three
used in senior/subordinated leveraging of private
blocks in the central business district will be capped and a
investment dollars for complicated transportation projects
parkway/esplanade will appear in what has been a
of national significance.
railroad right-of-way for over 135 years. An AMTRAK
passenger rail station will be built in the new corridor as |  | The project is being built under a design-build contract
part of the overall transit plan for Reno. |  | with Granite Constructors, and was awarded in June of
2002. The notice to proceed was given September 15,
The now-final funding plan includes:
2002 and the project is expected to take almost four years
a. | 0.125% sales tax throughout Washoe County; | to complete.
b. | 1% room tax on downtown hotel properties;
ACTIVITIES FOR WHICH THE FIRM WAS
c. | Benefit Assessment District on all downtown
RESPONSIBLE:
properties;
Senior Manager
d. | $60 million settlement with the Union Pacific
| Railroad, which includes a lease on a number of | PROJECT COSTS:
| property parcels transferred from Union Pacific to the | $250 million
City of Reno;
REFERENCE:
e. | TEA-21 pass-through funding from Nevada DOT;
City of Reno
f. | Tax-exempt Municipal Revenue Bonds; and | Andrew Lireen, Finance Director
490 South Center Street, Room 108
g. | A USDOT loan under the TIFIA program.
Reno, Nevada 89501
Three different financing packages will be used to |  | (775) 334-2410
complete the project’s funding plan. The first is a
senior/subordinate financing that includes a senior-lien
tax-exempt revenue bond secured by sales and hotel taxes
and a TIFIA loan from the USDOT secured by a
subordinate lien pledge on the same sales and hotel tax
base. The second financing is a TIFIA loan secured by
the downtown assessments. The third financing, which is
not expected to be offered until 2004, is another
senior/subordinated bond/TIFIA loan package paid from
the lease income on railroad property transfers. Cash and
pay-as-you-go financing make up the balance of the
funding.
Goldman Sachs has modeled cash flows, planned funding
steps, and supported the City staff in communicating
funding plan elements to citizens’ groups and policy
makers, including members of Congress, members of the
Nevada legislature and the staff of the USDOT.
Two separate legislative packages were passed in two
different biennium to allow the project to move forward.
Goldman Sachs was an integral member of the
negotiating team working to gain a $60 million
THI3R4D | HAMPTON ROADS CROSSING |  | 34
CONCEPTUAL PROPOSAL

## Page 45
Name: “Table 1 of 1 on page 45 of 80”
Table: 43
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . b | Ex pe r i e nc e
Metropolitan Transportation Authority |  | ACTIVITIES FOR WHICH THE FIRM WAS
RESPONSIBLE:
Goldman Sachs was named financial advisor to the New |  | Financial Advisor
York Metropolitan Transportation Authority (MTA) in
August 2000. Under MTA's historic debt restructuring |  | REFERENCE:
program, MTA [and its Triborough Bridge and Tunnel |  | Stephen Kessler, Chief Financial Officer
Authority (TBTA) affiliate] has issued $15 billion of debt |  | 347 Madison Avenue
as of May 2003. In addition, MTA/TBTA expects to |  | New York, NY, 10017
issue over $2 billion of new money bonds under the |  | (212) 878-7278
program in 2003 and 2004. The 2002 issues are
comprised of 18 inter- related and coordinated, yet
separate series of bonds, including insured and uninsured
fixed rate bonds, senior and subordinate bonds, taxable
and tax-exempt bonds, variable rate demand notes,
auction rate securities and commercial paper. MTA also
entered into various interest rate swaps ( including BMA
and LIBOR-based swaps) to pre- hedge portions of its
issuance and hedge a portion of its longer-term variable
rate exposure. MTA also utilized special federal
legislation passed in the wake of September 11 to
advance refund several billion of bonds otherwise not
advance refundable.
Goldman Sachs is involved in the development of new
credits, drafting of resolutions, structuring of debt and the
assurance of a successful marketing program. The
restructuring simplified the MTA's credit structure by
consolidating sixteen old credits into four new primary
credits, modernizing old resolutions, releasing
unnecessary reserves, increasing bonding capacity and,
most importantly, providing approximately $4.5 billion of
funding capacity for the MTA's $17.2 billion 2000-2004
Capital Program without increasing maximum annual
debt service.
THI3R5D | HAMPTON ROADS CROSSING |  | 35
CONCEPTUAL PROPOSAL

## Page 46
Name: “Table 1 of 1 on page 46 of 80”
Table: 44
TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
| 1 . c | Po i nt o f Co nt a c t
Provide the names, addresses and phone numbers of persons within the firm or consortium who
may be contacted for further information.
The following person may be contacted for further information regarding this conceptual proposal:
` Francis X. (Buddy) Watson, P. E.
Tidewater Skanska, Inc.
809 S. Military Highway
Virginia Beach, VA 23464
(757) 420-4140
Mr. Watson will serve as the SWB Project Director and member of the joint venture executive board.
Please contact Mr. Watson regarding any questions or requests for additional information regarding this
proposal.
THI3R6D HAMPTON ROADS CROSSING |  | 36
CONCEPTUAL PROPOSAL

## Page 47
Name: “Table 1 of 1 on page 47 of 80”
Table: 45
[5 empty] | TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[11 empty] | 1 . d | Re f e r enc e s
Include the address, telephone number, and the name of a specific contact person for an entity
for | which | the | firm/consortia | or | primary | member | of | the | consortia | have | completed | a | similar
project.
The SWB Team members are proud of the infrastructure that they have designed and constructed. Please
contact any of the references shown the project sheets included in Tab 1.B, Experience, for further
information regarding the outstanding capabilities of the SWB Team members.
THI3R7D HAMPTON ROADS CROSSING | [12 empty] | 37
CONCEPTUAL PROPOSAL

## Page 48
Name: “Table 1 of 1 on page 48 of 80”
Table: 46
| TA B 1 : | QUA LI FI CA TI ON S AN D E XP ERI E NC E
|  | 1 . e | Fi na nc ia l St a t em e nt s
Provide a financial statement of the firm/consortia and each major partner. |  |  | Submit the most
recent Securities and Exchange Commission 10-K and 10-Q reports, if such reports have been
filed.
 | Appendix E contains the 2003 Annual Report of Skanska AB
 | Appendix F contains the audited financial statement of Skanska USA Civil, Inc.
 | Appendix G contains the audited financial statement of Tidewater Skanska, Inc.
 | Appendix H contains the Form 10-K Annual Report of Washington Group International, Inc.
 | Appendix I contains the Annual Report 2003 of Royal Bam Group nv.
THI3R8D HAMPTON ROADS CROSSING |  |  | 38
CONCEPTUAL PROPOSAL

## Page 49
Name: “Table 1 of 1 on page 49 of 80”
Table: 47
[7 empty] | TA B 1 : |  | QUA LI FI CA TI ON S AN D E XP ERI E NC E
[6 empty] | 1. f | Sm a l l , W o m e n a nd M i no r i t y O wne d Bus i ne s s Pa r ti ci pa t i o n
Include | any | planned |  | participation |  | of | small, |  | woman | and | minority | owned |  | businesses |  | during
project development and implementation.
The SWB Team is committed, as a matter of policy, to the spirit and intent of socio-economic programs
that are intended to ensure adequate opportunities for small, women, and minority owned businesses.
SWB | will | provide | written | notification |  |  | to | all | known | small, | women | and | minority-owned |  | (S/W/M)
businesses that specialize in the areas that will be subcontracted and will conduct workshops for these
firms to broaden their level of participation. Drawings and specifications will be made available to all
firms | that | express | an | interest | in | bidding | opportunities. |  |  | SWB | will | negotiate | in | good | faith | with | all
potential subcontractors.
All SWB team members have a history of meeting S/W/M business goals. SWB will advertise in a
variety of media to ensure that S/W/M businesses are notified of business opportunities and plans will be
reviewed to ensure that opportunities exist for participation by a variety of suppliers and subcontractors.
SWB has already identified potential contracting opportunities for this project: demolition; excavation
and grading; steel fabrication and installation; electrical; fencing and guardrail; traffic control; trucking
services; asphalt concrete paving; survey services; and painting. SWB plans to implement the following
actions to encourage S/W/M business participation.
 | Organize pre-proposal conferences to make S/W/M businesses aware of contract opportunities.
 | Develop a S/W/M mailing list to advise S/W/M businesses of bid dates and the location of the
procurement documents.
 | Identify construction packages where subcontracting opportunities exist.
 | Contact firms with whom SWB has successfully worked together in the past to ensure that they are
included on the bidding lists.
 | Contact Commonwealth certified firms using published S/W/M listings.
 | Identify contract/procurement packages that can be used to target S/W/M firms during the design
process. In some cases, these packages can be reduced to a monetary level that will encourage
S/W/M participation.
 | Advertise | in | local | newspapers |  | and | trade |  | magazines | to | encourage |  | S/W/M | awareness |  | and
participation.
 | Provide flexible payment provisions in S/W/M business contracts. Early payment clauses may be
included in certain contracts to alleviate cash flow problems.
SWB’s S/W/M business outreach program will be managed by a small and disadvantaged business
specialist who has developed identical programs in the past. SWB members, in the normal course of
business, have successfully addressed these requirements and have established relationships with S/W/M
businesses.
THI3R9D HAMPTON ROADS CROSSING | [16 empty] | 39
CONCEPTUAL PROPOSAL

## Page 50
Name: “Table 1 of 1 on page 50 of 80”
Table: 48
[9 empty] | TA B 2 : |  |  | P ROJ E CT CHA RA CT ERI S TI CS
[14 empty] | 2 . a | Pr o j e c t De s c r i pt i o n
Provide a description of the transportation facility or facilities, including the conceptual design
and all proposed interconnections with other transportation facilities. | [13 empty] | Identify communities that
may be affected and the assumptions used in developing the project.
Project Description
The Third Hampton Roads Crossing will connect the Hampton and Newport News areas with Suffolk,
Portsmouth, Chesapeake, Norfolk, and Virginia Beach. The project will reduce current congestion and
meet projected traffic demand, foster economic development, maintain the region’s quality of life, and
include the first Hampton Roads High Occupancy Vehicle (HOV)/Busway crossing which provides
space for the future addition of rail transit service. The Third Hampton Roads Crossing will also more
than double the capacity to evacuate low lying areas in the event of a hurricane.
Various alternatives to achieve this purpose have been evaluated by a Major Investment Study (MIS). A
Locally Preferred Alternative (LPA) has been selected as part of the MIS process and was approved by
the | Commonwealth |  |  | Transportation |  |  |  | Board | (CTB) | in | September |  | 1997. | The | Environmental | Impact
Statement (EIS) was approved in March 2001, and the Record of Decision was issued in June 2001. The
EIS supported the LPA that is defined by the five phases outlined below. SWB is proposing to develop,
design, construct, and finance all five phases.
 | Phase | I | – | Create | a | new | intermodal | connector |  | (I-564) |  | from | Terminal | Boulevard | past | Hampton
Boulevard in Norfolk to a new interchange with I-664 that is located south of Monitor-Merrimac
Memorial Bridge Tunnel. This section would consist of four general-purpose and two multi-modal
lanes constructed as a bridge-tunnel. This section will ultimately connect to a fourth cargo port at
| Craney | Island |  | (Phase |  | III) | and | provide | access | to | the | Norfolk | International |  | Terminals | and | I-564.
Direct access to the facility would also be provided from the Naval Operating Base.
 | Phase II - Widen the I-664, Monitor Merrimac Memorial Bridge Tunnel from Newport News to the
I-664/ I-564 Interchange with the addition of four general purpose and two multi-modal lanes. This
section will be a bridge tunnel that is constructed west of the existing facility.
 | Phase III - Construct a new four-lane road intersecting the extended I-564 and traversing Craney
| Island | to | an | interchange |  | with | the | Western | Freeway |  | (VA-164) |  | in | Portsmouth. | This | roadway | will
provide direct access to Craney Island, the Maersk Sealand terminal in Portsmouth, and also the
| Portsmouth Marine Terminal. Access to the Midtown Tunnel and the | [12 empty] | Downtown Tunnel will be
| provided |  | when | the |  | Pinners | Point | and | Martin | Luther |  | King | Expressway |  | extension | projects | are
completed.
 | Phase IV - Widen I-664 from its current interchange with I-64 in Hampton to the Newport News
end of the Monitor Merrimac Memorial Bridge Tunnel. This section will consist of eight general-
purpose and two multi-modal lanes, adding two lanes in each direction.
 | Phase V - Widen I-664 from its intersection with I-564 to the I-64/I-264 Interchange in Portsmouth.
The improvement would add one lane in each direction, resulting in six general-purpose lanes. This
THI4R0D HAMPTON ROADS CROSSING | [16 empty] | 40
CONCEPTUAL PROPOSAL

## Page 51
Name: “Table 1 of 1 on page 51 of 80”
Table: 49
[9 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[14 empty] | 2 . a | Pr o j e c t De s c r i pt i o n
phase will complete an improved connection from I-64 to the growing US 58/US 460 corridor and
includes about 3 miles of roadway on a trestle over Hampton Roads.
Figure | 2.1, | EIS | Alignment, |  | shown |  | on | the | following |  | page, | describes | the | general | alignment | that | is
included in the Final Environmental Impact Statement (FEIS). This alignment satisfies all of the needs
that are defined by the MIS.
The | EIS | has | been | the | subject | of | intense |  | review | to | comply | with | all | federal | and | Commonwealth
requirements. Commonwealth, federal, and local government agency efforts are chronologically listed
below:
 | July 1997 – Hampton Roads Metropolitan Planning Organization (MPO) selects the LPA.
 | September 1997 – Commonwealth Transportation Board endorses the LPA.
 | October 1997 – the Final Major Investment Study is completed.
 | October 1999 – the Draft Environmental Impact Statement (DEIS) is completed.
 | Early 2000 – Public Hearings are held.
 | July 2000 – the Commonwealth Transportation Board approves the DEIS.
 | March 2001 – the Final Environmental Impact Statement (FEIS) is completed.
 | June 2001 - Record of Decision is issued.
 | 2001 and early 2002 – Proposals received by VDOT for design and construction under provisions of
PPTA
 | Third Hampton Roads Crossing Commission, established by House Joint Resolution 125/2000, has
reviewed the project on several occasions
 | August 2002 – VDOT returns proposals submitted under PPTA
 | November 2002 – Voter Referendum rejects extra taxes for highway construction
 | August 2003 – Hampton Roads Metropolitan Planning Organization (MPO) includes Phase I as a
toll road in the 2026 Regional Transportation Plan, which was subsequently approved by VDOT and
FHWA.
THI4R1D HAMPTON ROADS CROSSING | [16 empty] | 41
CONCEPTUAL PROPOSAL

## Page 52
Name: “Table 1 of 1 on page 52 of 80”
Table: 50
TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
| 2 . a | Pr o j e c t De s c r i pt i o n
Figure 2.1 Environmental Impact Statement (EIS Alignment)
THI4R2D HAMPTON ROADS CROSSING |  | 42
CONCEPTUAL PROPOSAL

## Page 53
Name: “Table 1 of 1 on page 53 of 80”
Table: 51
[7 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[12 empty] | 2 . b | VDO T Pa r t i ci pa t i on
Identify and fully describe any work to be performed by VDOT.
SWB expects that the following work will be performed by VDOT:
` | Development
As a public-private transportation venture participant, VDOT will act as the lead agency, or project
sponsor. This effort will extend to participating in the creation of an IRS 63-20 corporation. VDOT
will also be responsible for the management and administration of the Comprehensive Agreement.
VDOT’s participation will be required for coordination with the Federal Highway Administration
(FHWA) because the crossing involves interstate highways. The involvement will likely include new
connection agreements as the project includes I-564, I-664, I-64, and the I-64/I-264 Interchange.
Coordination with other federal agencies will also be required since permits will be obtained from the
U.S. Army Corps of Engineers, the U.S. Coast Guard, and other federal agencies. Additionally, a
number of other Commonwealth agencies will be involved.
` | Design
VDOT will also be involved in various reviews and approvals during engineering and design. This
includes conducting design reviews to ensure adherence to the adopted design criteria and standards.
VDOT will also approve the crossings geometric design as part of this effort.
It is anticipated that VDOT will provide dedicated engineers during the design phase in the Project
Office. The VDOT staff will be responsible for providing technical guidance and design reviews for
| the | various | construction |  | packages. | VDOT’s | presence |  | will | be | critical | to | maintaining | the | design
schedule since design-build projects are executed on a fast-track basis. The reviewers need to be
| familiar | with | each | construction | package’s |  | development |  | through |  | continuous |  | “over-the-shoulder”
reviews, and develop a comfort level with the incremental development and release of plans. This
coordination is needed on a day-to-day basis rather than the periodic reviews typical of the design-
bid-build approach.
` | Construction and Acceptance
| Finally, | VDOT | will | be | responsible | for | accepting | the | completed |  | transportation |  | facility. | Specific
responsibilities will be defined prior to the execution of the Comprehensive Agreement. The Quality
Assurance and Quality Control Inspection Program will define responsibilities for quality control
and quality assurance including acceptance testing and final acceptance. SWB will coordinate its
efforts with VDOT to define these responsibilities. It is assumed that acceptance testing and final
acceptance will be performed by VDOT.
THI4R3D HAMPTON ROADS CROSSING | [14 empty] | 43
CONCEPTUAL PROPOSAL

## Page 54
Name: “Table 1 of 1 on page 54 of 80”
Table: 52
[7 empty] | TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
[12 empty] | 2 . c | Pe r m it s
Include a list of all federal, state and local permits and approvals required for the project and a
schedule for obtaining such permits and approvals.
Federal | and | Commonwealth |  | laws | and | regulations |  | require | that | various | environmental |  | permits | or
approvals be acquired prior to the start of construction activities:
 | Compliance with Executive Order 11990, Protection of Wetlands, and Section 404 Permits, Clean
Water Act, from the U.S. Army Corps of Engineers
 | Section 10 Permit, Rivers and Harbors Act, from the U.S. Army Corps of Engineers
 | Virginia | Water | Protection | Permit |  | from | the | Commonwealth |  | of | Virginia, | Department |  | of
Environmental Quality
 | Subaqueous Bed Permit, Virginia Water Law, from the Virginia Marine Resources Commission
 | U.S. Coast Guard Permit
 | Compliance with the Endangered Species Act (ESA)
 | Compliance with Section 106 of the Natural Historic Preservation Act
 | Compliance with Section 4(f) of the 1966 Department of Transportation Act
 | Compliance with Executive Order 12898 on Environmental Justice
 | Storm water management, erosion and sediment control permits from the Virginia Department of
Conservation and Recreation
Permits from local agencies will be identified during preliminary engineering. A local permit matrix will
be | prepared | as | public | agencies | are | contacted | to | determine |  | their | involvement | and | permitting
requirements. SWB will assign a permit specialist to the project during final engineering and design to
coordinate with PB/Jacobs and to manage the permit acquisition process. The permit specialists will be
the contact for all government agencies, ensuring that the proper permits are obtained prior to the start of
construction and that all permit requirements are met.
A permit acquisition schedule will be prepared during preliminary engineering once the required permits
have been identified and their requirements made known. Construction planning that will occur during
this timeframe will include the definition of construction packages and their scheduling requirements.
This scheduling effort will also consider permit requirements. Some permits are time sensitive and have
expiration dates. Their acquisition will be scheduled appropriately to avoid schedule delays.
THI4R4D HAMPTON ROADS CROSSING | [13 empty] | 44
CONCEPTUAL PROPOSAL

## Page 55
Name: “Table 1 of 1 on page 55 of 80”
Table: 53
[7 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[11 empty] | 2 . d | Env i r o nm e nt a l Impa c t s
Without completing an Environmental Impact Statement, identify any anticipated adverse social,
economic and environmental impacts of the project. | [7 empty] | Specify the strategies or actions to mitigate
known impacts. |  | Identify the projected positive social, economic and environmental impacts of
the project.
A Final Environmental Impact Statement (FEIS) was approved by the Federal Highway Administration
on March 1, 2001 and a Record of Decision (ROD) for the project was issued in June 2001. These
documents have been used to prepare SWB’s conceptual proposal.
The Hampton Roads area is a growing metropolitan region with a diverse population involved in ship
building, shipping, heavy industrial, military, tourism and a broad range of commercial enterprises. The
continuing | sustenance, | quality |  | of | life | and | continued | growth | of | the | region’s |  | financial |  | base | will | be
severely hindered by limited access across major navigable waterways that dominate the area.
Hampton Roads is crossed by the Hampton Roads Bridge Tunnel and the Monitor Merrimac Memorial
Bridge Tunnel. Each of these facilities provides two mixed flow lanes in each direction and serves
different | activity | centers. | These | facilities |  |  | provide | limited | alternate |  | use | selection |  | during |  | the | ever-
increasing peak congestion periods and also provide extremely limited public transit. The MIS and the
EIS process provided startling data, portraying a region in perpetual gridlock with stifled economic and
population growth before 2015 without expanding the Hampton Roads crossings.
This lack of traffic handling capacity has been recognized and extensively documented. Various studies
have concluded that a Third Hampton Roads Crossing that provides added capacity for vehicles and
bus/rail transit access from Newport News across the Craney Island portion of Portsmouth to Norfolk is
the best solution. This crossing concept with the widening of I-664 and I-564, and a direct connection to
the Western Freeway, VA-164, has been adopted as the Locally Preferred Alternative (LPA) by the
Hampton | Roads | Metropolitan |  | Planning |  | Organization |  | (MPO). | The | LPA |  | has | been | approved |  | by | the
Commonwealth Transportation Board, and was endorsed by the Governor of Virginia in July 2000. The
EIS alignment has been selected as the LPA.
The EIS addresses environmental impacts and suggests appropriate mitigation measures and strategies.
To summarize, mitigation can be accomplished by refining the alignment during engineering and design,
including | provision | for | sound | attenuation |  |  | features | where | appropriate, |  | and | phasing |  | construction |  |  | to
minimize | wildlife | impacts. | Vehicle |  | emissions |  | will | actually | decrease |  | after | the | opening |  | of | the | Third
Hampton | Roads | Crossing | project |  | as | compared | with | the | no-build |  | option. |  | SWB | is | committed |  | to
environmental | quality, | as | evidenced |  |  | by | Skanska’s | ISO14001 | certification. |  |  |  | SWB | will | incorporate
appropriate features in the facility’s design that address the requirements that are defined by the EIS and
the environmental permits. SWB will also phase construction to avoid disturbing wildlife during critical
seasons.
The impact to residences and businesses is relatively minor. The project will involve the relocation of 38
residences and 11 businesses as the alignment is primarily over water or in existing right-of-way. This
alignment requires very minor noise mitigation measures, which will be incorporated during design and
construction.
THI4R5D HAMPTON ROADS CROSSING | [16 empty] | 45
CONCEPTUAL PROPOSAL

## Page 56
Name: “Table 1 of 1 on page 56 of 80”
Table: 54
[8 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[13 empty] | 2 . d | Env i r o nm e nt a l Impa c t s
The project will significantly improve the quality of life for the region’s inhabitants with no adverse
environmental |  | impacts. |  | Quality | of | life | also | means | that | there | will | be | an | equitable | distribution |  | of
employment opportunities and contracts among the region’s diverse cultures. SWB will use locally hired
employees and regional subcontractors to the maximum extent possible and is committed to an equitable
distribution of contracting opportunities.
The | Third | Hampton |  | Roads | Crossing | provides |  | the | region | with | the | capability |  | to | grow | and | prosper
economically in the domestic and worldwide markets. The direct connection of Newport News, Norfolk,
and Portsmouth will substantially improve shipping links between the three major port complexes. The
connector link, between the extended I-564 and VA-164, Western Freeway, will provide the capability to
develop a significant fourth port at Craney Island with truck access to the other three Hampton Roads ports
and rail facilities.
The tourism industry will continue to thrive and be a major economic factor in the region with the
completion of a third crossing. Less congestion, alternate route selection and bus/rail transit capacity
will attract more visitors and tourists who will be better able to enjoy the regions’ many attractions.
The | EIS | considers | these | long-term |  | social | and | economic |  | enhancements. |  |  | On | a | short-term | basis | the
negative impacts that are normally associated with construction will be comparatively minor because
almost the entire footprint of the project is in previously purchased right-of-way and unencumbered
maritime |  | areas. | The | short-term |  | negative | impacts |  | will | be | offset | by | the | creation | of | employment
opportunities, |  | the | magnitude |  | of | business | growth/development |  |  |  | that |  | will | occur, | and | the | positive
environmental impacts such as cleaner air.
This project is definitely in the best interests of the region’s population. Citizens and businesses await
the completion of this critically needed transportation facility. An effective public information program,
including extensive outreach efforts, will be provided by SWB to continue fostering public support. The
public information program will respond to environmentally related public concerns. SWB will make
every effort to inform the public of protective measures that are being taken to protect the Hampton
Roads area.
THI4R6D HAMPTON ROADS CROSSING | [16 empty] | 46
CONCEPTUAL PROPOSAL

## Page 57
Name: “Table 1 of 1 on page 57 of 80”
Table: 55
[10 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[15 empty] | 2 . e | Cr i t ic a l Suc c e s s Fa c t o r s
List the critical factors for the project’s success.
The | success |  | of | the | Hampton |  |  | Roads | Third | Crossing | is | contingent |  | upon |  | several | important |  | factors
including the composition of the Project Team, a viable financing plan, public support, and institutional
support. These factors are discussed as follows.
` | The SWB Team - SWB was formed specifically to undertake this project. The member companies
and | designated |  | designers |  |  | have |  | more | contemporary waterfront and highway design | [7 empty] | and | construction
experience in the Hampton Roads area than any other imaginable team. The SWB members know the
area well, and are acutely aware of the social and economic issues and benefits that are associated with a
third crossing. SWB has started the process of assembling an experienced and dedicated staff of long-
term employees to undertake the development of the Third Hampton Roads Crossing. SWB will execute
the project at the lowest possible cost and with minimal social, environmental, and economic impact.
The skills of the SWB Team, immense assets and capabilities of the parent firms and the commitment of
these firms to dedicate their best resources to the SWB Team will ensure success.
The Third Hampton Roads Crossing success requires that high quality be built in from the start. The
SWB | Team |  | has | a | proud | history |  | of | executing | well-controlled |  |  | and | complex |  | projects | that | have | been
constructed to exacting standards, while meeting cost and schedule goals. Minimizing time requirements
and constructing a high-quality project safely will encourage public support, reduce inconvenience to the
traveling public, while also reducing construction costs.
Local and regional workers and subcontractors will be employed to the maximum extent possible. They
will be fully integrated into the SWB Team and contribute to the project’s success.
The SWB Team will also establish and maintain mutually beneficial relations with VDOT, a proposed
IRS 63-20 organization or a public agency, the regional governing bodies, regional organizations, and a
myriad of civic, social, economic, professional, business and special interest groups. SWB is committed
to partnering with all stakeholders for mutual success.
` | Project | Financing |  |  | - | VDOT |  | has | estimated | the | Third | Hampton |  | Roads | Crossing |  | would | cost | $4.4
billion if it were designed and constructed between 2001 and 2014. The SWB estimated cost of the
Third Hampton Roads Crossing and the planned method of financing are discussed in Tab 3. Under
SWB’s plan, the cost of the crossing can be reduced substantially and the duration shortened. The
traveling public will be able to use the completed facility earlier than planned, and the taxpayer will not
have to bear the burden of a much more expensive facility.
` | Project | Financing |  |  | - | Testimony |  |  | provided | during | the | public | comment |  |  | and | community | outreach
programs |  | of | the | MIS |  | and | EIS | and | input | from | government |  | officials, |  | private |  | sector | groups, | and
individuals indicate overwhelming support for the project. Many people recognize that it is needed now,
and it is widely recognized that it is needed several years before VDOT’s estimated completion date if
the region is to experience a reasonable quality of life.
The | public | is | justified |  |  | in | its | concern | regarding | how | to | pay | for | this | urgently |  | needed, | but | fiscally
constrained project. A study published by the Hampton Roads Partnership in 2000 indicates that a
majority of residents are willing to finance transportation improvements through the imposition of tolls,
THI4R7D HAMPTON ROADS CROSSING | [18 empty] | 47
CONCEPTUAL PROPOSAL

## Page 58
Name: “Table 1 of 1 on page 58 of 80”
Table: 56
[8 empty] | TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
[11 empty] | 2 . e | Cr i t ic a l Suc c e s s Fa c t o r s
a dedicated sales tax increment, a dedicated gas tax increment, or a combination of these financing
alternatives. The November 2002 referendum provided mixed results on similar questions but there
remains strong support for a viable Third Hampton Roads Crossing. Gaining additional public support
for financing the project during the next six years is critical, otherwise the project’s cost could nearly
double without any tangible benefit to the public. TAB 3 discusses SWB’s proposed financial plan.
` Forming | Coalitions |  | - | VDOT | and | the | SWB | Team | must | form | stakeholder | coalitions | during |  | the
development | process | to | develop |  | mutually |  | beneficial | solutions |  | and | foster | communication. | The | major
participants will include the FHWA, the U.S. Army Corps of Engineers, the U.S. Navy, the Hampton
Roads | Metropolitan | Planning | VDOT: Organization,; SWB: local; Team: jurisdictions,; form: and | other | local | agencies | and | port
authorities, as well as business interests and the public at large. Defining mutual interests and developing
plans to address those interests will be of paramount importance. SWB has dealt effectively with all of the
involved parties in the past. Relationships already exist that will allow SWB to quickly move forward.
THI4R8D HAMPTON ROADS CROSSING | [14 empty] | 48
CONCEPTUAL PROPOSAL

## Page 59
Name: “Table 1 of 1 on page 59 of 80”
Table: 57
[7 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[14 empty] | 2 . f | Sc he dul e
Identify the proposed schedule for operator’s work on the project, including the estimated time
for completion.
VDOT’s fiscally constrained schedule in 2001 reflected a 14-year construction period, resulting in a
2014 completion date. This schedule is dependent upon the availability of direct funding from already
strained Commonwealth and federal sources. It is clear that limited funding is available at this time and
the | project’s | multi-phase |  |  | development | would | depend | on | incremental |  | funding | over | several |  | decades,
assuming that it was available.
SWB has developed financing and construction plans for the Third Hampton Roads Crossing that are
presented in TAB 3. Recognizing that time is of the essence, this proposal is based upon executing a
Comprehensive Agreement with VDOT and receiving a notice-to-proceed by 2007. The intervening
months will be used to further define the project sufficiently to allow the preparation of a fixed price
estimate. Given that a notice-to-proceed shortly after the Comprehensive Agreement is executed, final
engineering and design could proceed shortly thereafter. This accelerated schedule will allow the facility
to be completed in significantly less time than planned, resulting in several important benefits:
 | Greatly reduced construction costs
 | Improved quality of life
 | Greatly reduced interest costs
 | Added capacity years earlier
 | Economic benefits are realized years earlier
Once final engineering and design begins three levels of schedules will be used to plan, monitor and
control the design program: Level 1 (Master Schedule); Level 2 (Critical Path Method Schedule); and
Level | 3 | (Control | Level | Schedules). |  | This | schedule | system | will | be | fully | integrated | and |  | define | the
objectives of the plan of execution for each level of the organization.
The | Master | Schedule |  | will | define | major | milestones | for | each | construction |  | package. | A | project-level
schedule will further define the major activities that are associated with each milestone that is shown on
the | Master | Schedule. |  | This | Precedence |  | Diagram | Method | Schedule |  | will | be | used | to | define | the
interrelationship |  |  | of | planning, | design, | procurement, |  | and | construction |  | activities, |  | including |  | activities
performed |  | by | others | and | permitting | activities. | Control-level |  |  | schedules | will | be | developed |  | for | each
construction package to define all activities to use as the basis of status and progress reporting.
THI4R9D HAMPTON ROADS CROSSING | [15 empty] | 49
CONCEPTUAL PROPOSAL

## Page 60
Name: “Table 1 of 1 on page 60 of 80”
Table: 58
[9 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
[11 empty] | 2 . g | Ti m e l y Co m pl e t i o n o f t he Pr o je c t
Propose | allocation |  | of | risk | and | liability |  | for | past | agreement |  | work | and | assurances | for | timely
completion of the project.
Skanska/Washington/BAM (SWB), PB, and Jacobs will bear all design and construction liability in
accordance with existing professional standards and statutory requirements. The project will meet or
exceed all applicable laws and regulations.
The | SWB | Team has |  | extensive |  | experience |  | in executing the type of project envisioned as the Third
Hampton |  | Roads | Crossing |  | and | have | undertaken |  | numerous |  | projects |  | together. | Based | on | the | Team
experience |  | in | design | and | construction |  | in | the | Hampton |  | Roads | area | with | projects | that | bear | many
similarities to all phases of the Third Crossing Project, SWB is confident the project can be completed
by 2013. SWB expects to provide a firm price during finalization of a Comprehensive Agreement by
December 2006.
SWB recognizes that environmental considerations will limit timeframes for dredging operations and
that | weather |  | factors | are | always | more | pronounced |  |  | for | maritime | construction. |  | SWB’s |  | collective
experience in the Hampton Roads area demonstrates the Team’s proven capability to control schedules
and produce quality facilities in this environment. Based on a proven record, SWB is willing to accept
liquidated damages as part of the finalization of the Comprehensive Agreement.
THI5R0D HAMPTON ROADS CROSSING | [16 empty] | 50
CONCEPTUAL PROPOSAL

## Page 61
Name: “Table 1 of 1 on page 61 of 80”
Table: 59
[8 empty] | TA B 2 : |  | P ROJ E CT CHA RA CT ERI S TI CS
|  | 2 . h | As s um pt i o ns Re l at e d t o O wne r s hi p, Li abi l i t y and Ope r a t i o na l Re s po ns i bi li t y
Clearly state the assumptions related to ownership, legal liability, law enforcement and operation
of the facility.
As | currently | envisioned |  | VDOT | will | have | ownership |  | and | police | responsibility |  | upon | completion |  | of
construction |  | except | for | certain | specialty |  | items. | Law | enforcement |  | and | legal | liability | will | be | the
responsibility of appropriate governmental agencies.
SWB will be responsible for operations and maintenance of the new facilities.
THI5R1D HAMPTON ROADS CROSSING | [15 empty] | 51
CONCEPTUAL PROPOSAL

## Page 62
Name: “Table 1 of 1 on page 62 of 80”
Table: 60
[6 empty] | TA B 2 : | P ROJ E CT CHA RA CT ERI S TI CS
[10 empty] | 2 . i | Pr o j e ct Pa r t i a l O peni ng s
Provide | information | relative | to | phased | or | partial | openings | of | the | proposed | project | prior | to
completion of the entire works.
Openings are scheduled to coincide with the completion of operable segments. | [10 empty] | Interfacing of operable
segments is addressed in Tab 3.
THI5R2D HAMPTON ROADS CROSSING | [12 empty] | 52
CONCEPTUAL PROPOSAL

## Page 63
Name: “Table 1 of 1 on page 63 of 80”
Table: 61
CONFIDENTIAL | [9 empty] | TA B 3 : | P ROJ E CT FI NA NCI NG
[12 empty] | 3 . a | Pr o j e c t Co s t Es t i ma t e
INTRODUCTION
This section presents the schedule, estimates and financing plans for the alignment approved in the
Record of Decision (ROD). There are numerous alternatives based on selected phasing, selected scope,
toll levels and availability of funds in addition to toll revenue. Financially appealing alternatives to the
ROD-approved |  |  | alignment |  | are | available | to | explore | through | later | phases | of | the | PPTA | process. | The
following assumptions were used to prepare Skanska/Washington/BAM’s (SWB) proposal:
 | Primary funding will be provided through tax-exempt toll revenue bonds. Secondary funding will be
obtained by VDOT from other sources.
 | Tolls will be placed on the Hampton Roads Bridge Tunnel and the Monitor Merrimac Memorial
Bridge Tunnel in July 2008, 18 months after Notice to Proceed.
 | The | project | will | be | accomplished |  | on | a | develop-finance-design-build-operate |  |  |  |  | and | maintain | basis
rather than the traditional design-bid-build basis.
 | A Comprehensive Agreement, as described in the Public Private Transportation Act of 1995, will be
executed during December 2006, followed by a Notice to Proceed in January 2007.
 | VDOT estimated right-of-way costs of $70 million are reasonable and include right-of-way owned
by governmental agencies. VDOT will execute its right of eminent domain if necessary
 | All costs for toll collection are included in the SWB proposal. The primary means of toll collection
will be via electronic scanning such as EZ-Pass or Smart Tag.
 | SWB will be responsible for operations and maintenance of the new facilities.
 | Craney Island will be available as a dredge disposal site.
 | Bond interest rates and other financial terms are based on the April 30, 2004 market conditions for
35-year term, tax-exempt toll revenue bonds.
The | estimate | and | schedule |  | for | the | SWB | concept | proposal | compared | to | the | current |  | (2001) | VDOT
proposal is as follows:
[7 empty] | VDOT Plan (2001) |  |  | SWB Plan (2004)
|  | Estimated Cost ($M) | [5 empty] | $4,400M* |  |  | $3,671M
|  | Completion Date | [5 empty] | 2014* |  |  | 2013
*Note: Excludes Intermodal Connector from Hampton Boulevard to I-564 and is based on
|  |  | a project start in 2001. |  |  |  | If costs were escalated to 2004, the SWB proposal would
save greater than $1B
THI5R3D HAMPTON ROADS CROSSING | [15 empty] | 53
CONCEPTUAL PROPOSAL

## Page 64
Name: “Table 1 of 1 on page 64 of 80”
Table: 62
CONFIDENTIAL | [9 empty] | TA B 3 : | P ROJ E CT FI NA NCI NG
[12 empty] | 3 . a | Pr o j e c t Co s t Es t i ma t e
Provide a preliminary estimate and estimating methodology of the cost of the work by phase
and/or segment (e.g. planning, design, construction).
This | section |  | addresses | the | cost | estimates | for | the | financing, | design | and | construction |  | of | the | Third
Hampton Roads Crossing. Estimated costs are also provided to finance, design and build the project by
phases. The breakdown of total project cost, by percentage is:
| Planning |  |  |  | 1.5%
| Design |  |  |  | 5.0%
| Construction |  |  | 93.5% (Including Construction Engineering & Inspection)
The alignment of the Third Hampton Roads Crossing is illustrated in Figure 3-1. This alignment and the
five phases were approved in the June 2001 Record of Decision culmination of the Environmental
Impact Study. This alignment has also been approved by the Commonwealth Transportation Board and
the Metropolitan Planning Organization (MPO). In August 2003, the MPO added the four non-restricted
access lanes of the intermodal connector from Hampton Boulevard in Norfolk to the intersection of I-
564 to Phase I. This intermodal connector is included in the SWB proposal.
Based | on | a | January | 2007 | Notice | to | Proceed, | SWB | can | complete | the | entire | project | in | 2013 | at | an
estimated cost of $3,671M. The same scope and phasing, exclusive of the intermodal connector, was
presented to the Third Hampton Roads Crossing Commission by VDOT on January 15, 2001 with an
estimated cost of $4,400M and a projected completion date of 2014, assuming a project start in early
2001.
The project can be built in phases to provide operational segments as needed to meet the growing traffic
demand. If VDOT elects to construct the project in phases, SWB recommends that Phase II be built
concurrently with the redefined (August 2003) Phase I to minimize costs, to meet the growing traffic
demands on the Monitor Merrimac Memorial Bridge Tunnel, and to avoid significant extra costs for
temporary facilities that are needed to make Phase I feasible as a stand-alone facility. The costs by
phases are illustrated in Table 3.1.
Table 3.1 |  | Estimated Cost by Phase
| PHASES |  |  |  |  | SWB Plan
Phases I and II | [6 empty] | $2,499M
Phase III | [6 empty] | $551M
Phase IV | [6 empty] | $305M
Phase V | [6 empty] | $316M
Total | [6 empty] | $3,671M
Completion Date | [6 empty] | July 2013
THI5R4D HAMPTON ROADS CROSSING | [16 empty] | 54
CONCEPTUAL PROPOSAL

## Page 65
Name: “Table 1 of 1 on page 65 of 80”
Table: 63
CONFIDENTIAL | [9 empty] | TA B 3 : |  | P ROJ E CT FI NA NCI NG
[12 empty] | 3 . a | Pr o j e c t Co s t Es t i ma t e
Phases I and II represent the backbone of the Third Hampton Roads Crossing and provide the basic
functionality of the project. Phases III, IV, and V are independent of each other but depend on Phases I
and II to achieve the required capacity. The start of these three phases could be scheduled as shown in
Figure | 3.2 | to | achieve | completion | of | all | five | phases | by | 2013. | Phases | III, | IV, | and | V | could | also | be
scheduled independently to meet ridership demands or the availability of funds.
THI5R5D HAMPTON ROADS CROSSING | [17 empty] | 55
CONCEPTUAL PROPOSAL

## Page 66
Name: “Table 1 of 1 on page 66 of 80”
Table: 64
CONFIDENTIAL |  | TA B 3 : | P ROJ E CT FI NA NCI NG
|  |  | 3 . a | Pr o j e c t Co s t Es t i ma t e
Figure 3.1 | Project Alignment
THI5R6D HAMPTON ROADS CROSSING |  |  |  | 56
CONCEPTUAL PROPOSAL

## Page 67
Name: “Table 1 of 1 on page 67 of 80”
Table: 65
CONFIDENTIAL | [7 empty] | TA B 3 : |  | P ROJ E CT FI NA NCI NG
[11 empty] | 3 . b | Fi na nc i ng Pl a n
Submit | a | plan | for | the | development, | financing | and | operation | of | the | project, | showing: | the
anticipated schedule on which funds will be required; and proposed sources and uses for such
funds.
Figure 3.2, Project Schedule, illustrates the timeframe for major activities associated with the
development, design and construction of the Third Hampton Roads Crossing. A further breakdown of
key elements germane to project financing is outlined below:
Period |  | Activity
7/04–11/04 |  |  | VDOT issues public notice that an unsolicited proposal has been received.
12/04–01/05 |  |  | Initial Review Committee review and recommendation
2/05 |  |  | Commonwealth Transportation Board decision.
2/05-3/05 |  |  | Resolve requirements for the detailed Technical Proposal phase and execute an initial
agreement.
3/05-3/06 |  |  | SWB develops concept engineering and studies.
4/06 |  |  | Detailed Technical Proposal and preliminary engineering submitted for Advisory Panel
review.
|  |  | Detailed Technical Proposal submitted to local governments for their 60 day review period.
|  |  | VDOT, with SWB assistance, submits analysis to FHWA for tolling existing interstate
highways.
8/06 |  |  | Negotiations complete and approved. Initiate efforts for bond offering.
12/06 |  |  | Comprehensive Agreement executed.
1/07 |  |  | Notice-to-proceed issued.
2/07 |  |  | Funding in place.
6/07 |  |  | Complete toll facility design and begin construction.
|  |  | Design for islands complete and permits for Island construction issued.
1/08 |  |  | Island construction starts.
7/08 |  |  | Begin toll collection.
12/09 |  |  | Initiate second bond offering.
12/10 |  |  | Complete project design.
7/13 |  |  | Complete facility open to public.
While Phases I and II must start at the earliest possible date, the remaining phases can be scheduled with
Phases I and II to maximize construction efficiency. Table 3.2, Schedule of Funds Required for Each
Alternative, illustrates the funding required for each year for the complete scope of the project if all
phases are to be completed by 2013. Table 3.2 also provides the funding required for each year if VDOT
elects to authorize completion of only Phases I and II.
THI5R7D HAMPTON ROADS CROSSING | [12 empty] | 57
CONCEPTUAL PROPOSAL

## Page 68
Name: “Table 1 of 1 on page 68 of 80”
Table: 66
CONFIDENTIAL | [5 empty] | TA B 3 : | P ROJ E CT FI NA NCI NG
[7 empty] | 3 . c | Fi na nc ia l As s um pt io ns
Figure 3.2 | Project Schedule
Description |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013
Third Crossing
Preliminary Engineering
Notice to Proceed
Phase I + II
Engineering
Mobilization
Graving Dock
Tunnel Islands
Elizabeth River Tunnel
MM Tunnel
Roadwork and Bridges
Trestles
Phase III
Engineering
Roadwork and Bridges
Phase IV
Engineering
Roadwork and Bridges
Phase V
Engineering
Roadwork and Bridges
Project Completion
THI5R8D HAMPTON ROADS CROSSING |  | 2013: 58
CONCEPTUAL PROPOSAL

## Page 69
Name: “Table 1 of 1 on page 69 of 80”
Table: 67
CONFIDENTIAL |  | TA B 3 : | P ROJ E CT FI NA NCI NG
|  |  | 3 . c | Fi na nc ia l As s um pt io ns
Table 3.2 | Schedule of Funds Required for Each Alternative
|  | COMPLETE PROJECT | PHASES I AND II ONLY
YEAR
|  | $ in Millions | $ in Millions
| 2007 | 179 | 179
| 2008 | 465 | 457
| 2009 | 550 | 501
| 2010 | 733 | 546
| 2011 | 763 | 400
| 2012 | 645 | 300
| 2013 | 336 | 116
| Total | $3,671 | $2,499
The proposed funding source for this project is through a combination of toll collection and VDOT
obtaining external funding. The financial model utilizes non-recourse toll revenue bonds issued by a
non-profit organization (IRS 63-20 or public agency). Bond offerings will be in 2006 and 2010.
Toll Revenue will be provided from toll collection facilities at the Hampton Roads Bridge Tunnel and
the Monitor Merrimac Memorial Bridge Tunnel starting in July 2008.
Sources and uses of funds for the SWB alternatives outlined above are included in TAB 3f.
THI5R9D HAMPTON ROADS CROSSING |  |  |  | 59
CONCEPTUAL PROPOSAL

## Page 70
Name: “Table 1 of 1 on page 70 of 80”
Table: 68
CONFIDENTIAL | [9 empty] | TA B 3 : |  | P ROJ E CT FI NA NCI NG
[13 empty] | 3 . c | Fi na nc ia l As s um pt io ns
Include a list and discussion of assumptions (user fees or toll rates, and usage of the facility)
underlying all major elements of the plan.
The EIS provides traffic projections for the Hampton Roads Bridge Tunnel and the Monitor Merrimac
Memorial |  | Bridge | Tunnel. |  | These |  | figures | suggest | that the | aggregate |  | traffic | for these facilities would
increase at 2.9 percent per year after the 1994 base year. VDOT’s traffic volume measurements through
2003 confirm that the growth is in line with these projections. For the purposes of the financial analysis
SWB has assumed:
| 1. | A conservative traffic growth rate of approximately 2 percent per year after 2002.
| 2. | Execution of the Comprehensive agreement during December 2006.
| 3. | Instituting tolls on Hampton Roads Bridge-Tunnel and the Monitor Merrimac Memorial Bridge
Tunnel in July 2008.
| 4. | An average toll for each vehicle, regardless of the type of vehicle or hour of the day. A more
diversified toll structure will be developed during preparation of the detailed technical proposal.
| 5. | All costs associated with the toll collection function will be paid out of the toll revenues. Toll
collection would be done primarily by electronic means such as EZ-Pass or Smart Tag.
| 6. | All right-of-way can be obtained within the VDOT estimate of $70 million.
| 7. | An escalation rate for construction costs of 3.5 percent per year.
| 8. | VDOT will be able to obtain the required authority to place tolls on the Monitor Merrimac
Memorial Bridge Tunnel and the Hampton Roads Bridge Tunnel.
| 9. | A conservative financing package based on April 30, 2004 market conditions.
| 10. | Imposing tolls reduces projected traffic by 3 percent per $0.50 toll increment.
| 11. | VDOT will obtain funds from other sources in accordance with the timeframe of the selected
alternative.
| 12. | The average toll increases $0.50 every five years after completion in 2013 to compensate for
inflation.
| 13. | The | above | toll | rates | are | averages | between | cars | and | trucks | and | the | selected | method | of | toll
payment (cash or electronic).
Based on the assumptions above, SWB has determined that:
| Case 1. |  | Phases I and II can be financed without funds from other sources if the starting toll in
2008 is set at $2.00/trip and the toll is increased to $5.75/trip upon project completion in
2013.
| Case 2. |  | The complete project (Phases I through IV) will require $900 million in funds from other
sources, even with a starting toll of $2.00/trip in 2008 and an increased toll of $8.50/trip
in 2013.
The toll rate may be reduced or the debt retired earlier if:
 | External funding is increased.
 | Interest rate is lower.
 | Actual traffic is greater than expected.
 | Certain loan guarantees are obtained.
THI6R0D HAMPTON ROADS CROSSING | [16 empty] | 60
CONCEPTUAL PROPOSAL

## Page 71
Name: “Table 1 of 1 on page 71 of 80”
Table: 69
CONFIDENTIAL |  | TA B 3 : | P ROJ E CT FI NA NCI NG
|  |  | 3 . c | Fi na nc ia l As s um pt io ns
Some of these funding options could be explored further during the preparation of the detailed technical
proposal. For illustration purposes, the following examples show two of a virtually infinite number of
potential alternatives with external funds, the impact of varying the initial tolls (July 2008), and the
amount of external funds:
Alternate A. | If Phases I through V were built:
|  | Initial (2008) toll is $2.00/Trip
|  | Toll upon completion in 2013 is $3.00/Trip
|  | External funds required are $1,850M
Alternate B. | If Phases I and II were built:
|  | Initial (2008) toll is $2.00/Trip
|  | Toll upon completion in 2013 is $3.00/Trip
|  | External funds required are $600M
Note: | Funding generated by required debt/service ratio could be used as a fund source for remaining
phases.
THI6R1D HAMPTON ROADS CROSSING |  |  |  | 61
CONCEPTUAL PROPOSAL

## Page 72
Name: “Table 1 of 1 on page 72 of 80”
Table: 70
CONFIDENTIAL | [9 empty] | TA B 3 : |  | P ROJ E CT FI NA NCI NG
[14 empty] | 3 . d | Ri s k Fac t o r s
Identify the proposed risk factors and methods for dealing with these factors.
SWB | is | confident |  | that | the | Third | Hampton | Roads | Crossing | can | be | built | by | 2013 | based | on |  | the
assumptions |  | in | this | submittal. |  | This | conceptual | proposal |  | demonstrates |  | that | the | project | is | financially
feasible and satisfies a demonstrated need. SWB is prepared to begin negotiations with VDOT to arrive
at a mutually acceptable price and schedule that will result in the SWB assuming risk commensurate
with anticipated returns. Four major areas of risk have been identified as outlined below.
` Availability of Funds – The presentation of financial alternatives depends on the acceptability of
tolls to a certain level and the availability of other funding to finance the remainder of the costs. The
MPO and various public opinion polls indicate that tolls will be acceptable to a certain extent, but the
Third Crossing will require a significant amount of funds from other sources even if the maximum
public acceptability of tolls is $3.00 per crossing in 2013. VDOT’s ability to obtain the required funds
from other sources is essential to the success of the proposed project.
VDOT | and | the | Hampton |  | Roads |  | Planning | District | Commission |  | are | currently | contracting |  |  | for | a | Toll
Feasibility Study. The results of this study will be incorporated in the detailed Technical Proposal.
The | proposal | also |  | assumes |  | that | The | Hampton | Roads | Bridge | Tunnel | and | the | Monitor |  | Merrimac
Memorial Bridge Tunnel will be tolled. VDOT needs to obtain the required approvals to institute toll
collection on these existing Interstate Highways for the purpose of reducing congestion at these facilities
by using an improved traffic management system and constructing the Third Crossing. The capability of
VDOT to obtain the requisite authority in the time frames indicated is critical to the success of the
undertaking.
` | Rising Construction Costs - Starting the project as quickly as possible is integral to the success of
the financial plan. Inflation will increase project costs by over $100 million per year. Time is of the
essence. SWB is ready to move quickly. The SWB proposal includes escalation commensurate with the
proposed schedule and assumes a Comprehensive Agreement is in place by December 2006.
` Actual Traffic - A major concern for any project using private financing is that the projected traffic
will not materialize. For the Third Crossing the risk is minimized because traffic history is known and
the tolling plan minimizes diversion alternatives. SWB has made a conservative traffic projection based
upon long-term historic data for all the existing crossings and industry accepted traffic suppression rates.
All Hampton Roads crossings are to be tolled. SWB is confident that the projected toll revenues will
support the assumption of debt through sale of non-recourse toll revenue bonds.
` Obtaining Permits - The Third Hampton Roads Crossing Project requires numerous permits from
various agencies, which can be a long process. SWB anticipates that permits will be approved in a
timely manner by working with appropriate agencies during the detailed technical proposal and design
phases. The EIS addresses this risk factor in detail and concludes that environmental factors can be
mitigated by appropriate design and construction considerations.
SWB anticipates the risk of not obtaining permits in a timely manner is low based upon the Approved
Environmental Impact Statement.
THI6R2D HAMPTON ROADS CROSSING | [17 empty] | 62
CONCEPTUAL PROPOSAL

## Page 73
Name: “Table 1 of 1 on page 73 of 80”
Table: 71
CONFIDENTIAL | [6 empty] | TA B 3 : | P ROJ E CT FI NA NCI NG
[9 empty] | 3 . e | Addi t i ona l Re s o ur c e s
Identify any local, state and federal resources that the proposer contemplates requesting for the
project. | Describe the total commitment (financial, services, property, etc.), if any, expected from
governmental sources; and the timing of any anticipated financial commitment.
In order to finance the Third Hampton Roads Crossing project with non-recourse toll revenue bond, the
Hampton Roads Bridge Tunnel and the Monitor Merrimac Memorial Bridge Tunnel will have to be
tolled and clearly recognized as part of the same vital transportation system as the Third Hampton Roads
Crossing. | VDOT | must | obtain | approval to toll these facilities. Various combinations of tolls on the
Hampton | Roads | Bridge | Tunnel | and | Monitor | Merrimac | Memorial | Bridge | Tunnel | and | other | funding
would establish a base for construction of the Third Hampton Roads Crossing.
Certain right of way will be required for the project. It is assumed that all costs associated with this land
are included in the $70M VDOT right-of-way costs. This $70M VDOT estimate has been incorporated
into the SWB project budget. SWB may need assistance from VDOT in obtaining this land through the
eminent domain process.
The SWB analysis is based on using non-recourse toll revenue bonds as the primary use of funds. This
analysis indicates that the necessary toll levels to support construction would probably not be acceptable to
the general public. A combination of an acceptable level of tolls and other funding is required. VDOT will
have to obtain any funds necessary to supplement the toll revenue financing from other sources.
THI6R3D HAMPTON ROADS CROSSING | [11 empty] | 63
CONCEPTUAL PROPOSAL

## Page 74
Name: “Table 1 of 1 on page 74 of 80”
Table: 72
CONFIDENTIAL |  |  |  |  | TA B 3 : | P ROJ E CT FI NA NCI NG
[6 empty] | 3 . f | So ur c e s a nd Us e s o f Funds
Case 1 | Phase I & II Only |  |  | Case 2 | Phase I Through V
| Toll Rate: |  | $2.00 (2008) |  | Toll Rate: |  | $2.00 (2008)
|  |  | $5.75 (2013) |  |  |  | $8.50 (2013)
Sources: |  |  |  | Sources:
Bond Proceeds |  |  |  | Bond Proceeds
Par Amount |  |  | 2,918,793,864 | Par Amount |  |  | 3,205,828,744
Uses: |  |  |  | Uses:
Project Fund Deposits |  |  |  | Project Fund Deposits
Phases I & II Construction Draws (Net) |  |  | 2,326,231,129 | Phases I & II Construction Draws (Net) |  |  | 2,326,231,129
|  |  |  | Phases III - V Construction Draws (Net) |  |  | 1,146,192,490
Other Fund Deposits |  |  |  | Other Fund Deposits
Debt Service Reserve Fund |  |  | 291,879,386 | Debt Service Reserve Fund |  |  | 320,582,874
Capitalized Interest |  |  | 64,708,680 | Capitalized Interest |  |  | 65,413,042
Delivery Date Expenses |  |  |  | Delivery Date Expenses
Cost of Issuance |  |  | 43,781,908 | Cost of Issuance |  |  | 48,087,431
Bond Insurance |  |  | 174,937,456 | Bond Insurance |  |  | 190,311,121
Other Uses of Funds |  |  |  | Other Uses of Funds
Additional Funding for Phases I & II |  |  | 17,255,305 | Funding Shortfall for Phases III - V |  |  | -890,989,343
Total |  |  | 2,918,793,864 | Total |  |  | 3,205,828,744
Total Additional/(Shortfall of Funds) |  |  | 17,255,305 | Total Additional/(Shortfall) of Funds |  |  | -890,989,343
Alternate A | Phase I Through V |  |  | Alternate B | Phase I & II Only
| Toll Rate: |  | $2.00 (2008) |  | Toll Rate: |  | $2.00 (2008)
|  |  | $3.00 (2013) |  |  |  | $3.00 (2013)
Sources: |  |  |  | Sources:
Bond Proceeds |  |  |  | Bond Proceeds
Par Amount |  |  | 2,169,957,459 | Par Amount |  |  | 2,169,957,459
Uses: |  |  |  | Uses:
Project Fund Deposits |  |  |  | Project Fund Deposits
Phases I & II Construction Draws |  | (Net) | 2,326,231,129 | Phases 1 & II Construction Draws (Net) |  |  | 2,326,231,129
Phases III - V Construction Draws (Gross) |  |  | 1,242,450,000
Other Fund Deposits |  |  |  | Other Fund Deposits
Debt Service Reserve Fund |  |  | 216,995,746 | Debt Service Reserve Fund |  |  | 216,995,746
Capitalized Interest |  |  | 62,871,148 | Capitalized Interest |  |  | 62,871,148
Delivery Date Expenses |  |  |  | Delivery Date Expenses
Cost of Issuance |  |  | 32,549,362 | Cost of Issuance |  |  | 32,549,362
Bond Insurance |  |  | 131,219,941 | Bond Insurance |  |  | 131,219,941
Other Uses of Funds |  |  |  | Other Uses of Funds
Funding Shortfall for Phases I & II |  |  | -599,909,867 | Funding Shortfall for Phases I & II |  |  | -599,909,867
Funding Shortfall for Phases III - V |  |  | -1,242,450,000
Total |  |  | 2,169,957,459 | Total |  |  | 2,169,957,459
Total Additional/(Shortfall of Funds) |  |  | -1,842,359,867 | Total Additional/(Shortfall) of Funds |  |  | -599,909,867
THI6R4D HAMPTON ROADS CROSSING | [6 empty] | 64
CONCEPTUAL PROPOSAL

## Page 75
Name: “Table 1 of 1 on page 75 of 80”
Table: 73
[12 empty] | TA B 4 : | P UB LI C S UP PO RT
[13 empty] | 4 . a | Co m m uni t y Be ne fi t s
Identify who will benefit from the project, how they will benefit and how the project will benefit
the overall transportation system.
The Hampton Roads region of Virginia has 1.7 million residents and encompasses the area from James
City County, Surry County and Southampton County east to the Atlantic Ocean. The region is divided
by numerous waterways, foremost of which are the Chesapeake Bay, Hampton Roads, the York River,
the | James | River, | and | the | Elizabeth | River. | The |  | region | has | a | highly | diverse | social | structure |  | and
demographics. With the construction of the Hampton Roads Bridge Tunnel, James River Bridge and the
most recent Monitor Merrimac Memorial Bridge Tunnel, the mobility provided to the population has
improved significantly. People routinely traverse Hampton Roads for business, shopping, and recreation
purposes. The regions economy also employs individuals who reside outside the area, and the economy
of the area is greatly dependent upon continued and improved access across Hampton Roads.
The Hampton Roads Bridge Tunnel is the major link across Hampton Roads. Its four lanes are currently
operating at capacity with significant delays a routine occurrence. The only other interstate access across
Hampton | Roads |  | is | the | Monitor | Merrimac | Memorial |  |  | Bridge | Tunnel, | which | has | capacity |  | to | accept
additional |  | traffic | but | does | not | directly | serve | the | major | residential, |  | business, |  | and | military | areas | of
Virginia Beach or Norfolk. The James River Bridge is about five miles west of the Monitor Merrimac
Memorial Bridge Tunnel and has capacity for increased traffic but it also does not directly serve major
population centers. This traffic situation is limiting the growth of the region and impacts the required
mobility of U.S. Military in the area.
The | Major | Investment |  |  | Study | (MIS) | identified |  | the | need | to | increase | capacity | and | to | provide | a
transportation |  | facility |  | that | would | reduce | Hampton |  |  | Roads | Bridge | Tunnel | traffic |  | while | providing
improved access with greatly increased capacity from the peninsula to the southern Hampton Roads
area. The MIS also identified the need to provide linkage to major ports, existing highways and to serve
as a major freight corridor. The EIS (Locally Preferred Alternative) now proposed by SWB as the Third
Hampton Roads Crossing will satisfy these community needs by:
 | Reducing the traffic on the Hampton Roads Bridge Tunnel traffic by nearly 20 percent from the no
build alternative bringing the level of service on this route to acceptable levels.
 | Providing highways that are in tune with current and projected origin and destination patterns.
 | Providing access to all current and planned port areas.
 | Providing highways that will serve as a major freight corridor.
 | Providing direct connections with existing major highways in the area.
 | Providing a facility at significantly lower cost than planned.
 | Providing a facility significantly earlier than planned.
 | Providing the first facility that will have HOV access across Hampton Roads.
 | Providing a facility that can accommodate rail transit.
 | Making all of these improvements at a significantly lower cost and significantly earlier than planned.
THI6R5D HAMPTON ROADS CROSSING | [16 empty] | 65
CONCEPTUAL PROPOSAL

## Page 76
Name: “Table 1 of 1 on page 76 of 80”
Table: 74
[11 empty] | TA B 4 : |  |  | P UB LI C S UP PO RT
[14 empty] | 4 . a | Co m m uni t y Be ne fi t s
The proposed facility will also act as an emergency access/egress route in case of an emergency like a
hurricane. The Third Hampton Roads Crossing will more than double the capacity to evacuate people
from and to the peninsula or the US58/US460 corridor.
Construction of the Third Hampton Roads Crossing will benefit social and economic aspects of the
region and improve the quality of life of its inhabitants. The improved access will foster the continuing
growth of the region’s increasingly diverse economy by making it easier to ship goods into and out of
the | region | through | its | port | facilities | and | reduce |  | existing | industrial |  | traffic |  | in | residential | areas. |  | The
improved access will also aid the continuing growth of tourism, which is a key aspect of the area
economy. |  | The | crossing | will | improve |  | the | readiness | posture | of | the | U.S. | military |  | through |  | alternate
overland route capacity in case of emergency and the potential for transshipping through a fourth port
area. The project will foster the growth of a new Commonwealth port facility and the Maersk/Sealand
terminal which is currently moving into its construction phase. These new port facilities aid mobility and
permit | the | continuing | favorable |  |  | growth | of | the | maritime | industry | that | is | a | very | significant |  | business
interest in the region and the Commonwealth.
Maintaining economic growth and attracting new business to the area demands that employees have an
acceptable quality of life. Improved access across the waterways in the area is critical for the individual
mobility and choices for alternative routes for recreation, employment and shopping. The region will be
in | virtual | gridlock | surrounded |  | by | air | pollution |  | without | construction |  | of | the | Third | Hampton |  |  | Roads
Crossing. Without construction of the Third Hampton Roads Crossing the situation will degrade the
quality of life to a point that is unacceptable to both employees and employers and the increasing
numbers of retired residents. The alternative is for some of the businesses to leave the area. This is not
acceptable |  | from | local, | state | or | national | viewpoints. |  | All | depend | on | Hampton |  |  | Roads | as | a | major
international port, quality vacation area and home to the U.S. Navy’s largest operational base.
On a short-term basis, the construction of the Third Hampton Roads Crossing will provide employment
to numerous individuals and provide opportunities for a large variety of local and regional businesses.
SWB is committed to utilizing local resources to the maximum extent possible. The construction effort
will create some short-term growth in the local economy followed by the long-term growth in other
business areas created by improved access and quality of life.
THI6R6D HAMPTON ROADS CROSSING | [17 empty] | 66
CONCEPTUAL PROPOSAL

## Page 77
Name: “Table 1 of 1 on page 77 of 80”
Table: 75
[12 empty] | TA B 4 : |  |  | P UB LI C S UP PO RT
[10 empty] | 4 . b | G o v e r nm e nt a nd Co m m uni t y Suppo r t
Identify | any | anticipated | government |  |  | support |  |  | or | opposition, |  |  | or | general | public |  | support |  | or
opposition for the project.
The Major Investment Study (MIS) and the National Environmental Policy Act (NEPA) process have
investigated the problem of providing a suitable Third Hampton Roads Crossing for over a decade.
During this process there have been numerous opportunities for the public to comment on a variety of
routing alternatives that would foster economic growth while maintaining a suitable quality of life. The
resultant locally preferred alternative provides for the interests of virtually everyone in a manner which
has very minor impact on the environment.
The NEPA process and associated public hearings show the routing is acceptable to residents, business
interests | and | local | governments. | It | is | expected |  | that | there |  | may | be | occasional |  | concerns |  | about | some,
currently | unidentified, |  | issues | during | further |  | development |  |  |  | and | construction. |  |  | SWB | will | establish |  | and
maintain | a | community | relations | office |  | to | be | sensitive |  | to | these | types |  | of | issues | and | to | provide | all
stakeholders with continuous information as the project is developed and constructed.
Almost everyone concurs with the need for the project and the planned alignment. SWB recognizes that
concerns | have | been | voiced | regarding |  | methods |  | to | finance |  | the | facility. |  | Differing |  | opinions |  | regarding
financing alternatives are expected to continue, but due to the tremendous support for the project it is
expected that an acceptable method of financing can be found through dialogue with the relevant parties.
THI6R7D HAMPTON ROADS CROSSING | [18 empty] | 67
CONCEPTUAL PROPOSAL

## Page 78
Name: “Table 1 of 1 on page 78 of 80”
Table: 76
[11 empty] | TA B 4 : |  | P UB LI C S UP PO RT
[12 empty] | 4 . c | Publ i c Inv o l v e m e nt Pl a n
Explain the strategy and plans that will be carried out to involve and inform the agencies and the
public in areas affected by the project.
The success of the Third Hampton Roads Crossing project is contingent upon consensus among the
Virginia Department of Transportation, local businesses and interest groups, state and local officials, and
the general public.
SWB | will | cooperate |  | with | these | groups | to | ensure | cohesiveness |  | of | efforts | towards |  | the | successful
completion of the undertaking desired by all stakeholders. SWB will develop and maintain a high level
of positive communication and support by informing and educating the many segments of the public
prior to and during construction. SWB will also be involved in open dialogue with all affected civic
groups to keep them abreast of project status and to listen to any concerns. SWB’s goal, simply stated, is
to | ensure | that | all | citizens | and | political | groups, | as | important |  | stakeholders, |  | have | an | opportunity |  | to
comment and become involved with the success of the project.
A large portion of the SWB public involvement program will involve meeting with various groups,
coordinating with the media, issuing press releases and maintaining an updated internet web site. We
expect | the | Third |  | Hampton | Roads | Crossing |  | project | will | be | very | successful | and | SWB |  | wants | all
stakeholders to be satisfied with the status and to take pride in the fact that their support has lead to a
project that satisfies their needs for the foreseeable future.
This project is locally developed and strongly supported by the citizens of the Hampton Roads area.
SWB is headquartered in Hampton Roads and is well aware of the importance of continuing the positive
involvement of the citizens. SWB will do everything within its capability to ensure that the general
public remains informed and that they share in the success of the project.
THI6R8D HAMPTON ROADS CROSSING | [16 empty] | 68
CONCEPTUAL PROPOSAL

## Page 79
Name: “Table 1 of 1 on page 79 of 80”
Table: 77
[5 empty] | TA B 5 : |  | P ROJ E CT BE NE FI TS / C O M PA TI B I LI TY
[13 empty] | 5 . a |  | Publ i c Be ne f i t s
Describe the significant benefits to the community, region or state. | [11 empty] | Identify any state benefits
resulting from the project including the achievement of state transportation policies or other
state goals.
In the fall of 2000 the Virginia Department of Transportation (VDOT) estimated that the Third Hampton
Roads Crossing project would require a construction period of 14 years resulting in a completion date of
2014. | By that time it is expected that air pollution will have reached an unacceptable level, the region
will be in nearly constant gridlock, and that businesses would be leaving the area due to deterioration of
quality of life, which makes recruiting and retention of quality employees extremely difficult. One of the
areas major employers, the U.S. Navy, will continue to have less mobility than desired, as relocation is
not | an | option. | Clearly | delaying | completion |  | beyond |  | 2014 | is | not | acceptable. | The |  | Environmental
Assessment “no build” option is not acceptable to the inhabitants of the Hampton Roads area.
In the intervening years there has not been any progress on the project while the area has seen moderate
growth, increased congestion and growing concerns with environmental issues. SWB can still design
and | build | the | Third | Hampton | Roads | Crossing | and | have | it | complete |  | by | 2013, | or | earlier, | using | a
financing-design-build approach.
Even with a 2013 completion date congestion and environmental considerations will become far worse
than currently exist. The continued delay in executing the Third Hampton Roads Crossing project is
impacting business development and creating a reduced quality of life for residents and other workers in
the area. Recent incidents associated with Hurricane Isabel and a maritime incident serves to point out
just | how | fragile | the | transportation | system | is | in | the | 2003/2004 |  | timeframe. |  | Normal |  | growth | of | the
commercial, tourist and residential traffic will make transportation throughout the region intolerable by
the earliest time the facility can be available.
Current and future inhabitants of the area will clearly be the major benefactors of the project. The
transportation improvements will foster the development of existing businesses and create opportunity
for new industry while promoting those aspects of the area desirable for tourists. The continued growth
of the very successful commercial port will make Virginia a more favored port of call for international
commerce and create growth that is beneficial to the entire Commonwealth. The state would also benefit
in numerous other ways associated with the healthy development of the second largest economic region
in the Commonwealth.
The Third Hampton Roads Crossing will also provide the capability for improved transit operations.
High occupancy vehicle lanes and bus rapid transit capability will be available upon project completion.
THI6R9D HAMPTON ROADS CROSSING | [16 empty] | 69
CONCEPTUAL PROPOSAL

## Page 80
Name: “Table 1 of 1 on page 80 of 80”
Table: 78
[5 empty] | TA B 5 : |  | P ROJ E CT BE NE FI TS / C O M PA TI B I LI TY
[13 empty] | 5 . b | Ec o no m i c Be ne fi t
Describe the significant benefits to the state’s economic condition. | [10 empty] | Discuss whether this project is
critical to attracting or maintaining competitive industries and businesses to the state or region.
The proposed project will benefit the entire economy of the Commonwealth, including significant direct
benefits to the tourism, port, and military aspects of the local economy. Underutilized land will become
available/accessible |  | for | business, | residential |  | or | tourism |  | purposes. |  | The | project |  | will | also | affect | the
economic development of areas adjacent to Hampton Roads. The project’s capability for future transit
operations | between | jurisdictions |  | in | the | Hampton | Roads |  | area | will | provide |  | an | alternative |  | means | of
transportation throughout the region.
The project will provide direct access to Craney Island, which is to be developed into a port facility.
This | development | is | highly | advantageous |  | to | the | Commonwealth |  |  | and | the | nation’s |  | economy. | The
connecting roadways will provide direct access to other port facilities in the area and the entire highway
system of the United States through the I-64 link on the peninsula and the US 58 and Route 460 links
along the southern part of Virginia. This project will also provide vital alternate routes for trucking using
the Norfolk International Terminals (NIT) and Lamberts Point Ports, thus reducing heavy traffic on
residential streets.
The project will provide an additional crossing of the Elizabeth River to directly access Norfolk and
Virginia | Beach. | The | Hampton | Roads | Bridge |  | Tunnel | is | currently |  | operating |  | at | its | design | capacity.
Continual congestion impacts residents’ quality of life, while detracting visitors and businesses, with the
resultant limitation on further economic development. This project will provide direct access with HOV
and multi-modal capability, which will benefit the tourism industry and foster all aspects of the region’s
economic growth. This crossing will also benefit the military by enhancing their mobility by providing
an additional, more direct access to and from naval installations.
By improving the quality of life, the Third Hampton Roads Crossing project will ensure the growth of
businesses that depend on a highly skilled workforce. These types of businesses provide significant
benefits to the region and the state.
SWB’s proposal to build the project in less time and at a lower cost than planned will mitigate all
problems associated with a later completion and will stimulate positive economic growth for the region.
THI7R0D HAMPTON ROADS CROSSING | [16 empty] | 70
CONCEPTUAL PROPOSAL